Program & Project Plans: PLM-Excellence
Program Lead: Siegfried Bocionek

Program Start: Jan 06

Program End: Dec 06

Coach & Steering Board: Jochen Eickholt, tbd
	Project, P-Leader
	Project Plans & Milestones
	Status

28feb06
	Next Steps

	Uniform Communication in R&D;  Bocionek
	Start: Jan 06   ongoing

1. Establish regular all hands communication (Jan 06)

2. Engange in breakfast meetings and other activities (start Feb 06)
	Done

[image: image1]
	2nd all hands R&D meeting on March 06

	High-performing culture & commitment-driven behavior; Bocionek
	Start: Jan 06   End: Dec 06; repeat every year
1. KPI metrics (Jan 06)

2. Mgmt Objectives aligned and signed (Feb 06)

3. Balanced Score cards (Feb. 06; moved to April)

4. LQA analysis (R&D only: May 06; moved to March)

5. Peer Rating in Mgmt (R&D only; Sept 06)

6. 10 Basic Aspects (Oct 06)

7. Feedback rounds, EFA (Nov/Dec 06)
	Done
Done

[image: image2]
	LQA March 06

	Real Model-V: Introduce process culture and discipline; Assan

	Start: Jan 06   End: Sep 06
1. Name project lead (Feb. 06) – M. Assan
2. Project Plan (Mar 06)
3. Education starts (Mar 06)

4. Internal customer satisfaction metrics set (Mar 06)

5. CIP targets set (Apr. 06)

6. Process adaptations completed (Jun 06)

7. CMMI baseline available(Sep 06)
	Done

[image: image3]
	

	Going Agile; U. Schmitz, Faessler, Rudolph
	Start: Jan 06   End: Dec 06; continue from there

1. Kick-off for selected projects (Jan 06)

2. Broad Introduction of Methodology (Feb 06)

3. Start Ruby on Agile (Feb 06)

4. Start Jerry project on Agile (Feb 06)

5. Start Gemstone project on Agile (Mar 06)

6. Mentoring by OM starts (Mar 06)

7. Process change proposal (Jul 06)

8. First lessons learned session on Jerry (Oct 06)

9. Organization prepare for full Agile transition (Dec 06)
	Done
Done
Done
Done

[image: image4]
	

	Best-in-Test: Wacker
	Start: Jan 06   End: Jun 06; continue measuring

1. First metric setup (Feb 06)

??? defect injection analysis start ??
2. Complete metric setup (May 06)
3. Roll out “new bugs after S4” metric (May 06)
4. Test cases for TDD in scrum team in time (May 06)
5. Roll out “changed LOC” metric after C3 (May 06)
6. Roll out “first pass yield” metric (May 06)
7. CPI targets ST based on metrics data (June)
	Done

[image: image5]

	Alignment with QM, SWK, SWM (Mar 06)

	Best-in-IT tools; tbd
	Start: Jan 06   End: Jun 07

1. Project Plan (Feb 06)

2. Consolidate all teams for PLM (Mar 06)

3. Start centralizing support infra-structure (Mar 06)

4. Increase iautomation of tool chain (Jul 06) 
	
[image: image6]
	Project lead change to H. Thonhauser (acting); re-set

	Platform & Portfolio; SB + JE
	Start: Jan 06   End: Jun 06

1. Define alignment & change mgmt process (Feb 06), 2. clarify platform responsibilities/activities (Feb 06)

3. define re-use strategy (Mar 06)
	
[image: image7]
	QA‘able Portfolio doc by CM due

	Invent the future; Bauregger, Hartmann
	Start: Jan 06   End: Jun 06

1. Agree on invention disclosure targets (Jan 06)

2. Start invention initiative (Feb 06)

3. Implement incentive proposal (Mar 06)

4. 90 invention disclosures filed (Jul 06)

5. 180 invention disclosures filed (Dec 06)
	Done

[image: image8]

	Launch initiative (Feb 06)

	cleanApoxi platform; Faessler
	Start: Jan 06   End: Dec 06 (perhaps earlier)

1. Align all parties incl. IFX, Teleca (Feb 06)

2. Analysis workshop (Mar 06)

3. Diamond decision (Mar 06)

4. Publish formal platform concept, incl. technical

specification and usage model (Apr 06)

6. Start skills enhancement program (May 06)
7. Close gaps in Apoxi (tbd)

8. First Apoxi product (tbd; hopefully Apr 07)
	Done

[image: image9]

	Workshop (start 05-Mar-06), Diamond decision (latest EO March)

	U2 projects; Faessler, Rudolph
	Start: Jan 06   End: Mar 06; continue from there

1. Set up U2 for Polaris, Swift, Swan, Kestrel (Jan 06)

2. report metrics on weekly basis (since Jan ongoing)

3. establish U2 as practice in all projects (Apr 06)
	Done
Done

[image: image10]
	Continue with practice

	Quality Up of MD; Thonhauser
	Start: Jan 06   End: Jun 06

1. PLM MD excellence program and KPI‘s (Jan06)

2. Improvement project starts (Feb 06)

3. Visible results (Jul 06) 
	Done
Done

[image: image11]
	Track monthly KPI‘s

	
	
	
	

	Thin client phone; Bauregger

	Start: Jan 06   End: Aug 06

1. Start Feature definitions (Jan 06)

2. Interdisciplinary team starts (Feb 06)

3.

….
7. Prototype running (Jul 06)
8. Product decision (Aug 06)
	Done
Done

[image: image12]
	Overview of potential platform suppliers (HW/SW) started


	
	
	
	


