## Slide 1: BenQ Mobile Group Turnaround Program Initiative PLM-Excellence
BMG Program Office
26.01.2006

## Slide 2: Summary
Case for action and scope of initiative
Overall status of initiative
Detailed project plan

## Slide 3
TTM not satisfactory
Product quality at delivery date not satisfactory; return rates too high
Requirements mgmt and change request processes too volatile
Platform and re-use strategy needs more attention
Process understanding and maturity level too low (< CMM level 2)
Process metrics and derived CIP measures not part of routine PLM work
Low intake of invention disclosures
PLM Excellence Initiative Scope
Current PLM situation – case for action
Immediate drive PLM efficiency and TTM
For Top Management, summary, Current PLM situation & PLM Excellence project scope
Goals
quality and innovation position for all
products on the roadmap
Define quantified targets (from
benchmark considerations), and derive
PKIs and objectives for the suborganisations
w.r.t. People – Process – Products - Projects.
Launch series of specific improvement
projects to optimize whole PLM, not
only the R&D org or PHE
Start with PHE, involve PHA later when results can be
demonstrated
Levers
People: Motivation & Leadership
Process: Organization & Productivity
Products:Innovation & Technologies
Projects:
Responsibility
S. Bocionek
KPIs
19 KPI’s defined, clustered in the BSC (balanced scorecards) systematic: Financials, Process, People & innovation, Customers

## Slide 4
Achievements:
  New organization MD SP defined and implemented and operational
  Carve out project COM SP up and running
  Negotiation achievement tracking in place (11,6%)
  BenQ / MD team in place
Achievements:
Critical issues/Open topics to be solved:
Required decisions from Management Board
Next steps:
Overall status turnaround initiative PLM Excellence
PLM excellence program defined, agreed upon by CM, TPM, RD, and communicated within all R&D
KPI‘s for R&D org completed Jan-31
U2 projects launched to secure Kestrel, Polaris, Swift, Swan; metrics since Jan-26
Kick-off for Agile Initiative Jan-4; applied to Ruby, Gemstone, Jerry
n/a
n/a
Task Responsible Due date
see next slide

## Slide 5: PLM Excellence Project Status Overview: 25-Jan-06
Project, P-Leader | Status | Achievements | Critical Issues | Next Steps
Uniform Communi-cation; Bocionek |  | Concept „Quo Vadis R&D“ defined; accepted by mgmt team | n/a | All hands R&D meeting on 27-Jan-06
High-performing culture; Bocionek |  | KPI‘s defined, baselining underway, targets to be set end of months | n/a | KPI targets ready 31-Jan Mgmt objectives 14-Feb
Model-V implem. Bocionek, Fillers |  | n/a | n/a | Needs more discussions with BenQ QM; SB drives
Agile; U. Schmitz, Faessler, Rudolph |  | Kick-off for Swan and Koala on Jan 4/5; Consulting supp. by ObjectMentor(OM) | Koala stopped; now Ruby & Gemstone; High consultancy cost | Scrum start Ruby 14-Feb OM offer agreed 14-Feb
Best-in-Test: Wacker |  | Systemtest managers informed, goals partly defined | n/a | alignment with SW and Q, kick off in cw 4
Best-in-IT tools; J. Schmitz |  | Kick-off done; Benchmarking started | Ressource & budget in ES dept. depends on concept tp be realized | Concept proposal ready in cw07
Platform & Portfolio; SB + JE |  | Good alignment meetings with CM in Dec. 05; needs continuation | Too little exchange of ideas so far (but there was Christmas) | QA‘able Portfolio doc by Uwe Sydon due 31-Jan
Invent the future; Bauregger, Hartm. |  | Kick off meeting cw03 | n/a | Status eval. start cw04 Target clarif. start cw04
cleanApoxi platform; Faessler |  | Major goals identified | n/a | Team members to be named (Jan 06)
U2 projects; Faessler, Rudolph |  | Ongoing for Polaris, Swift, Swan, Kestrel; wallchart reviews started | n/a | Wallchart reviews & SW TTM call with JE weekly
Quality Up of MD; Thonauser |  | PLM MD excellence program and KPI‘s defined | n/a | Track monthly KPI‘s

## Slide 6: Template 3: Detailed project plan
Including:
Milestones
Tasks
Responsibilities
Timelines & due dates
see next slide

## Slide 7: PLM Excellence Project Plans: Overview
Project, P-Leader | Status | Project Plans | Next Steps
Uniform Communi-cation; Bocionek |  | Establish regular all hands communication Engange in breakfast meetings and other activities | 2nd all hands R&D meeting on March 06
High-performing culture; Bocionek |  | Establish commitment-driven behavior, KPI metrics, Balanced Score cards | BSC in Feb 06 Employee survey Jul 06
Model-V; Bocionek, Fillers |  | Introduce process culture and discipline, incl. Internal customer satisfaction metrics (Mar 06), CIP targets (Apr. 06), CMM baseline (Dec 06) | Define program, Feb. 06
Agile; U. Schmitz, Faessler, Rudolph |  | Prototype Agile in 2 – 3 projects (Jan – Sep 06) Prepare organization for full Agile transition (Dec 06) | Scrum start Ruby 14-Feb OM offer agreed 14-Feb
Best-in-Test: Wacker |  | Start defect injection analysis (Feb 06), define bug fix cycle time impro-vement plan (Feb 06), improve NCCPI at delivery dates to < 50K (Jul 06) | alignment with SW and Q, kick off in cw 4
Best-in-IT tools; J. Schmitz |  | Consolidate all tools for PLM (Mar 06), centralize support infrastructure (Mar 06), increase interaction and automation of tool chain (Jul 06) | Concept proposal ready in cw07
Platform & Portfolio; SB + JE |  | Define Roadmap alignment & change mgmt process (Feb 06), clarify plat-form responsibilities and activities (Feb 06), define re-use strategy (Mar 06) | QA‘able Portfolio doc by Uwe Sydon due 31-Jan
Invent the future; Bauregger, Hartm. |  | Agree on invention disclosure targets (Jan 06), start invention initiative (Feb 06), strengthen IP portfolio of BMG (Dec 06) | Launch initiative (Feb 06)
cleanApoxi platform; Faessler |  | Define formal platform concept, incl. technical specification (Mar 06), usage model (Apr 06); start skills enhancement program (May 06) | Start workgroup, cw5
U2 projects; Faessler, Rudolph |  | Set up U2 methodology for Polaris, Swift, Swan, Kestrel (done, Jan 06); report metrics on weekly basis (ongoing); secure TTM for the projects | Wallchart reviews started 26-Jan; weekly practice
Quality Up of MD; Thonauser |  | PLM MD excellence program and KPI‘s defined (done, Jan06; < 2% RR), improvement project starts Feb 06), visible results (Jul 06) | Track monthly KPI‘s