## Slide 1: How to use Timesheets
Planning Office
06 January 2006
Guideline for entering hours spent (Actuals) and progress of work packages in Timesheets

## Slide 2: Start Timesheets and Login
Open Microsoft Internet-Explorer
Enter the URL below to access Timesheets
Click „Run Timesheets“
(Remember to turn-off Popup blockers)
2
3
Timesheets URL: http://primavera.aaldk1.aal.siemens.dk/GroupserverP3e/en/index.html
Enter your login name (e.g. „klf987“) and your password
2
4
Note:
If you need a Login Name and Password for Timesheets or you do not remember your password please contact Primavera Support
Login Name and Password for Primavera Timesheets and Project Management are the same
Contents:
Start and Login
Open Timesheet
Enter Hours Spent and Remaining
Enter Progress Feedback

## Slide 3: Open Timesheet
Open the timesheet: Select: File > Open Timesheet
5
Mark timesheet of last week and click „OK“
When you open a timesheet the first time you may choose whether all your work packages are added automatically to the timesheet (recommended),
or added manually,
or copied from the previous timesheet.
You may select not to include your completed assignments (recommended)
6
7
8
9
10
Contents:
Start and Login
Open Timesheet
Enter Hours Spent and Remaining
Enter Progress Feedback

## Slide 4: Enter Hours Spent and Remaining (by all resources)
To be entered by all resources:
Enter hours spent on your work packages
11
To enter your remaining hours select the tab “Resources”
Enter your remaining hours for the work package selected in the cell “New Remaining Units”
13
12
Notes:
Do not open timesheets for periods consisting of e.g. holidays only (contact your timesheet approval manager in case of a timesheet opened by mistake)
Hours are entered as hours and hundreds of hours separated by a dot
Do not submit timesheet before entries done for all days relevant
Blue rows indicates the period between planned start and finish date
Note:
Enter new remaining units only when major change compared to ”Remaining Units”
Note:
Work packages missing in your timesheet are added manually by use of: Edit > Add Activity. Select the work package missing and click Add.
Contents:
Start and Login
Open Timesheet
Enter Hours Spent and Remaining
Enter Progress Feedback

## Slide 5: Enter Progress Feedback (by primary resources)
16
17
17
To be entered by primary resources only:
Select tab „General“
Mark work package started and select date of start
► Enter „Expected Finish Date“ for every work package in progress ◄
Mark work package finished when completed and select date of completion
Notes:
The cells „Started“, „Finished“, and „Expected Finish Date“ are available for the primary resource only
The primary resource (tab „Resources“) is marked with a specific icon
Do not enter „Expected Finish Date“ on a Level of Effort work package
When a work package is marked finished assigned resources cannot enter actuals anymore
14
15
16
Contents:
Start and Login
Open Timesheet
Enter Hours Spent and Remaining
Enter Progress Feedback