## Slide 1: How to initiate Tracking View for analysing resources.
Planning Office
15 December 2005
This guide describes how to set up Tracking View in Primavera Project Manager for analysing Resources.

## Slide 2: Initiate Tracking View
As Tracking View will include a heavy data-transfer, it is absolutely necessary to set up Tracking View as mentioned in the slides of step A:
(This should only be done once).
    A. Initiate Tracking View (when never used before) – Page 3.
The slides in step B show the planned effort for projects for a global line, a department or skill group, or a single resource.
    B. Tracking View – Page 15
NB! Tracking View is based on summaries data which are calculated every night. If recent changes to a project should be included - the project must be open. Then online values will be included

## Slide 3: Initiate Tracking View (Start Up Filters)
Go to User Preferences under EDIT in Primavera Project Manager and change the settings of Start Up Filters.

## Slide 4: Initiate Tracking View (Start Up Filters)
Set Start Up Filters shown here.
After the changes are made - log out and in to Primavera again.

## Slide 5: Initiate Tracking View (Start Tracking View)
Start the Tracking View by using one of the shown buttons.
After pushing the button it can take some time before the Tracking view is shown. Just be patient. 

## Slide 6: Initiate Tracking View (Select layout)
When the view is opened - select the Layout: BenQ Department Resource Analysis.
Select this Layout
Press to view
all layouts

## Slide 7: Initiate Tracking View (Select View)
Click here
Select
Check the view in the lower left corner. It has to be Resources.

## Slide 8: Initiate Tracking View (Filter)
Click here
Select
Set up a Filter for the resources before the rights figures are shown. The filter is “build” in the lower left corner.

## Slide 9: Initiate Tracking View (Filter)
“Build” a filter like shown below. In the resource tree - select the department in question.
Then only labor resources are viewed

## Slide 10: Initiate Tracking View (Group and Sort)
Select
Click here
The Group and Sort settings for the lower left corner has to be changed.

## Slide 11: Initiate Tracking View (Group and Sort)
Select Department
Group and sort for the resource view has to be set as shown below.

## Slide 12: Initiate Tracking View (Units)
Right click here
Select the type of units needed to be shown. If choosing Customize more than one type can be in the view
Different units can be shown in this View.

## Slide 13: Initiate Tracking View (Tracking View)
A Tracking View Layout is now build up and analyses of resources can start.

## Slide 14: Initiate Tracking View (Start Up Filters)
After “building” the Tracking View the Start Up Filter have to be set back - in the User Preferences.
After the changes are made - log out and in to Primavera again.

## Slide 15: Projects and Load in a Global Line
List of all Projects where selected Global Line are involved.
The following slides show the planned efforts for projects for a global line, a department or skill group, or a single resource.
It is e.g. possible to see which projects the resources have booked their effort on and/or to see which project they are assigned.....

## Slide 16: Projects and Load in a Department
List of all Projects where selected Department are involved.

## Slide 17: Load and Projects in a Department by Resource
Remove checkmark to show resources
List of projects & efforts by resource for selected Department

## Slide 18: Projects and Load of a Resource
List of all projects of selected resource