## Slide 1: Capacity and load in Primavera
Planning Office
21 January 2006

## Slide 2: Resource load on running projects in PV
Load in Primavera for running projects
time
hours
Capacity

## Slide 3: Resource load in PMC
Load from coming projects
only in PMC
Load from Running Projects
hours
time

## Slide 4: Resource load – overall picture
Primavera load
Trial ongoing: Focus only on
transfer of planned hours
Primavera
PMC
Load from coming projects only in PMC

## Slide 5: Working time for a resource
h/d
contract working time
Holiday
average productive
working time
Administration/Training & Absence (excl. holiday)

## Slide 6: Limit shown in Primavera for a resource
Administration/Training & Absence (excl. holiday)
Contract working time
Limit shown in Primavera
The limit shown in Primavera is individual for each resource.
The daily working time from the contract is reduced by 0,5 hours to take in account that a resource cannot be 100% productive.
The granularity in Primavera for the limit should be not lower than 0,5 hour.
This means that the limit in Primavera has to be set according to the following table:
hours

## Slide 7: Conclusion
The Primavera planning tool cover approved running projects. Valid from M0, C0, I0, …. (the pre-work to be booked in a Pre M0, Pre C0, Pre I0,.. project)
The future projects are planned only in PMC. Therefore only in PMC we have the complete picture regarding planned load.
The limit for working time in Primavera show the contract working time reduced by 0,5 hour to leave space for the non productive work.