## Slide 1: Primavera – Training Concept
2 March 2006
Presentation

## Slide 2: Current Training Status
Planning and Tracking with Primavera
Participants | Contents | Method | Duration | Trainer
Project Leaders | Introduction to the Time To Market Methodology at BenQ Mobile Phones Planning and tracking projects by use of Primavera | Lectures Practice | 2 days | Planning Office
Collection of Actuals
Participants | Contents | Method | Duration | Trainer
Resources | Give feedback to project planning regarding progress Participants are able to use Primavera Timesheets for collection of hours spent on project activities | Lectures | 1 hour | Local Supporter

## Slide 3: Improved Training Concept - Overview
Subjects
  Primavera Project Management
  Primavera Timesheets
Target groups
  Project managers
  Line managers
  Timesheet Approval Managers
  Resources
  Supporters
Suggested trainings to be be offered:
  PL Basic Primavera Training
  PL Primavera Workshop
  PLT Master Plan Workshop
  Timesheet
  Timesheet Approval Manager work
  Line manager work
  Primavera Supporter

## Slide 4: Improved Training Concept (1)
PL Basic Primavera Training
Participants | Purpose / Contents | Method | Duration | Trainer
Project Leaders - no Primavera knowledge - will be PL in near future - have read the project management concept | Overview of the concept at BenQ Basic understanding of the Methods and the tool Planning and tracking projects by use of Primavera Need to know in Primavera to plan and track a project Project management methodology Project planning – time and resource related Project execution and tracking Analysis and reporting Primavera user interface customization Training case | Lectures Practice | 1 day (regularly e.g. once a quarter at each location) | Local Supporter Planning Office

## Slide 5: Improved Training Concept (2)
PL Primavera Workshop
Participants | Purpose / Contents | Method | Duration | Trainer
Project Leaders - have participated in PL Basic Primavera Training - leading ongoing project - have read the project management concept | Give PL knowledge about their responsibility, rules and what to do Improve daily use of Primavera Weekly update Resource assignment and tracking Timeline Critical Path and how to stay on track Baseline Reporting Q-gate Workshop with questions about daily use of Primavera from participants | Lectures Practice Workshop | 1 day (regularly e.g. once a quarter at each location) | Local Supporter Planning Office

## Slide 6: Improved Training Concept (3)
PLT Workshop
Participants | Purpose / Contents | Method | Duration | Trainer
PLTs - leading ongoing project - have read the project management concept | Basic use of Primavera Give PLT knowledge about their responsibility, rules and what to do. Use of Master Plan Improve daily use of Primavera Use of PLT Master Plan Critical path and how to stay on track Timeline Schedule Control milestones Reporting Q-gate Baseline | Lectures Workshop | ½ day (when needed) | Local Supporter Planning Office

## Slide 7: Improved Training Concept (4)
Primavera Timesheets
Participants | Purpose / Contents | Method | Duration | Trainer
Resources | Introduction to Primavera Timesheets for collection of hours spent on project activities, progress feedback, and processing of collected hours Project Management at BenQ mobile Collection of actuals (hours spent) with Timesheets Progress feedback (dates) Weekly cycle | Lecture | 1 hour (regularly e.g. once a month at each location) | Local Supporter

## Slide 8: Improved Training Concept (5)
Timesheet Approval Management
Participants | Purpose / Contents | Method | Duration | Trainer
Timesheet Approval Managers | Give Timesheet Approval Manager knowledge about their responsibility, rules and what to do in Primavera Weekly update cycle Collection of actuals in general Responsibilities Timesheet approval Maintain resource calendars How to be substitutet | Lectures Practice | 1 hour (when needed) | Local Supporter

## Slide 9: Improved Training Concept (6)
Line Manager Training
Participants | Purpose / Contents | Method | Duration | Trainer
Line Managers - have read the project management concept | Overview of line manager responsibility, rules and what to do and find in Primavera. Basic overview of the project management concept Relation with PMC News and relevant subjects What to do in Primavera Resource tree maintenance. Timesheet approval procedure Tracking Resource load e.g. with Tracking view Agreement with PL’s about resources | Lectures | 1 hour (when needed/ requested) | Local Supporter Planning Office

## Slide 10: Improved Training Concept (7)
Primavera Supporter
Participants | Purpose / Contents | Method | Duration | Trainer
Primavera Supporters | Training supporters in relevant subjects Secure that supporters can continue supporting the users of Primavera e.g.: Reporting New features and more detailed knowledge about Primavera Supporter role training Project management Exchange of experience | Lectures Workshop | 1 hour -> ? (when needed/ requested) | Planning Office (and/or external)