## Matrix
Function | ID Name (see detailed description in comments) | Report | Layout | Content |  |  |  | Project | [9 empty] | Activity | [17 empty] | User | [6 empty] | Resource | [13 empty] | Units | [7 empty] | Dates | [12 empty] | Duration |  |  |  |  | Group by
|  |  |  | Needs Open Project(s) | Baseline Required | Time Distributed | Detailed description | Project ID | Name | Responsible Manager | Project status | ICM Project Code | Global Line Code | Project type Code | Generation Code | Platform Code | Project Planner Code | Activity ID | Activity Name | Activity type | Activity Status | Duration Type | Activity calendar | Predesessor | Successor | Steps | Constraints | Total Float | Project Phase code | Connector Code | MS-type Code | MS-Behavior Code | Board Type Code | Layout Cycle Code | SW integration Point Code | Login ID | Name | E-Mail | Global Security Profile | OBS assignment | Resource | Licens | Resource ID | Name | E-mail | Calender | Labor | Role | Department Code | Location Code | Employee type Code | SAP account Code | Default units/time | User Login | Uses timesheet | Timesheet Approval Manager | Budget | Actual | Remaining Early | Overallocated | Available | Limit | Variance Labor Units | BL Budget | Start | Finish | Early start | Early Finish | Actual start | Actual Finish | Expected Finish Date | Primary Constraint Date | Data Date | Variance Start date | Variance Finish Date | BL Start | BL Finish | Original | Actual | Remaining | At complete | Variance Duration | Project | Project Status | WBS | Activity | Project Phase | Global Line | Department | Location | Employee Type | Resource | Timesheet Approval Manager
All | Siemens Default Layout |  | A | X |  | X | [11 empty] | + | + |  |  |  | + |  |  |  |  | + | [29 empty] | + | + | [5 empty] | + | + | [11 empty] | + | [6 empty] | +
All | Template PG75_default |  | A | X
All |  |  |  | X
Project Manager | A08 Projects checklist Planning Phase (mod) | X |  | X |  |  |  | + | + | [8 empty] | + | + | [53 empty] | +
Project Manager | A09 Weekly Part-Project Check (mod) | X |  | X |  |  |  | + | + | [8 empty] | + | + | [53 empty] | +
Project Manager | A10 Activities and Milestones Without Successor and Finish Constraint (mod) | X |  | X |  |  |  | + | + | [8 empty] | + | + | [53 empty] | +
Project Manager | A11 Activities and Milestones Without Predecessor and Start Constraint (mod) | X |  | X |  |  |  | + | + | [8 empty] | + | + | [53 empty] | +
Project Manager | A12 No Activities as Successor on Control Milestones (mod) | X |  | X |  |  |  | + | + | [8 empty] | + | + | [53 empty] | +
Project Manager | A13 Activities with no Role or Resource assignment (mod) | X |  | X |  |  |  | + | + | [8 empty] | + | + | [53 empty] | +
Project Manager | A14 Activities with Role and no Resource assignment (mod) | X |  | X |  |  |  | + | + | [8 empty] | + | + | [53 empty] | +
Project Manager | A15 Activities or Milestones without Primary resource. No LOE. (mod) | X |  | X |  |  |  | + | + | [8 empty] | + | + | [53 empty] | +
Project Manager | A16 Activities (Task dependant and LOE) with Duration equal to 0 (mod) | X |  | X |  |  |  | + | + | [8 empty] | + | + | [53 empty] | +
Project Manager | A17 Activities with Non Labor Resources Assigned (mod) | X |  | X |  |  |  | + | + | [8 empty] | + | + | [53 empty] | +
Project Manager | A18 Activities and Milestones with Constraint (mod) | X |  | X |  |  |  | + | + | [8 empty] | + | + | [53 empty] | +
Project Manager | A19 Overallocated Resources for open Project (mod) | X |  | X |  | X | [36 empty] | + | + |  |  |  |  | + | [10 empty] | + | + | + | [26 empty] | +
Project Manager | A20 Resource assignment over 6 h/d per Activity | X |  | X |  |  |  | + | + | [8 empty] | + | + | [53 empty] | +
Project Manager | A22-01 Resource assignment per Proj and Act. from DD-1W to DD + 3W (mod) | X |  | X | [13 empty] | + | + | [39 empty] | + | [5 empty] | + | + | [11 empty] | + |  |  |  |  | + | [9 empty] | +
Project Manager | A22-02 Resource assignment per Proj. and Act. from DD to PF (mod) | X |  | X | [13 empty] | + | + | [39 empty] | + | [5 empty] | + | + | [11 empty] | + |  |  |  |  | + | [9 empty] | +
Project Manager | A23 Activities in Progress with no Expected Finish (mod) | X |  | X |  |  |  | + | + | [8 empty] | + | + | [51 empty] | + |  | +
Project Manager | A24 Activities with Expected finish <= Data Date (mod) | X |  | X |  |  |  | + | + | [8 empty] | + | + | [51 empty] | + |  | +
Project Manager | A26 Activities in Progress with no Remaining Units (mod) | X |  | X |  |  |  | + | + | [8 empty] | + | + | [53 empty] | +
Project Manager | A27 Actual and Rem. Units per month Grouped by Dep., Employee Type and Res. (mod) | X |  | X |  | X | [36 empty] | + | + |  |  |  |  | + |  | + | [6 empty] | + | + | [29 empty] | + |  | + | +
Project Manager | A28 Actual and Remaining hours, Monthly Sort by Phase and Project (mod) | X |  | X |  | X |  | + | + | [19 empty] | + | [28 empty] | + | + | [23 empty] | +
Project Manager | A30 Activities - 1 week forecast | X |  | X |  |  |  | + | + | [8 empty] | + | + | + | + | [6 empty] | + | [36 empty] | + | + | [5 empty] | + | [8 empty] | + |  | +
Project Manager | A31 Activities - Overdue and critical | X |  | X |  |  |  | + | + | [8 empty] | + | + | + | + | [6 empty] | + | [36 empty] | + | + |  |  |  |  | + | + | [10 empty] | +
Project Manager | A35 Project comparison with Primary Baseline (mod) | X |  | X | X |  |  | + | + | [8 empty] | + | + | [43 empty] | + | [10 empty] | + | + | [6 empty] | +
Project Manager | A36 Activities and their steps by Project (mod) | X |  | X |  |  |  |  | + | [8 empty] | + | + |  | + |  |  |  |  | + |  | + | [36 empty] | + | + | [16 empty] | +
Project Manager | A37 Activities and their steps by WBS (mod) | X |  | X |  |  |  |  | + | [8 empty] | + | + |  | + |  |  |  |  | + |  | + | [36 empty] | + | + | [18 empty] | +
Project Manager | A38 Actual, Remaining and BL budget hours Monthly group by Project (mod) | X |  | X | X | X |  |  | + | [48 empty] | + | + |  |  |  |  | + | [18 empty] | +
Project Manager | A39 Actual, Remaining and BL budget hours Week group by Project (mod) | X |  | X | X | X |  |  | + | [48 empty] | + | + |  |  |  |  | + | [18 empty] | +
Project Manager | A40 Data Date for active Opened Projects (mod) | X |  | X |  |  |  | + | + | [63 empty] | +
Project Manager | A41 Actual and Rem. units for opened project(s), monthly, group Dep & Res.(mod | X |  | X |  | X |  | + | [34 empty] | + | + |  |  |  |  | + | [8 empty] | + | + | [29 empty] | + |  |  | +
Project Manager | A42 Primary ressource on LOE activity (mod) | X |  | X |  |  |  | + | + | [8 empty] | + | + | [53 empty] | +
Project Manager | 1.I.a: Resource Planning missing | X |  | X |  |  |  | + | [9 empty] | + | + | + | [8 empty] | + | [35 empty] | + | + | [14 empty] | + |  |  |  | +
Project Manager | 1.I.b: Resource Planning with > 8h/d | X |  | X |  |  |  |  | + | [8 empty] | + | + | [24 empty] | + | [12 empty] | + |  | + | [5 empty] | + | + | [16 empty] | +
Project Manager | 1.II.a: Expected Finish missing | X |  | X |  |  |  | + | [9 empty] | + | + | [8 empty] | + | [36 empty] | + | + | [18 empty] | +
Project Manager | 1.II.b: Predecessor or Successor missing (no MSs) | X |  | X | [13 empty] | + | + | + | + |  |  | + | + | [39 empty] | + | + | [18 empty] | +
Project Manager | 1.II.c: Primary Constraint (and Predecessor, w/o Main Level, no MSs) | X |  | X | [13 empty] | + | + | + | + | [5 empty] | + | [37 empty] | + | + | [5 empty] | + | [8 empty] | + |  |  |  | +
Project Manager | 1.II.d: Overdue and critical | X |  | X |  |  |  | + | + | [8 empty] | + | + | + | + | [6 empty] | + | [36 empty] | + | + |  |  |  |  | + | + | [10 empty] | +
Project Manager | 1.II.e: Actual Dates > Current Date | X |  | X |  |  |  | + | + | [8 empty] | + | + | + | + | [6 empty] | + | [36 empty] | + | + |  |  |  |  | + | + | [10 empty] | +
Project Manager | 2.b: Actual Units (last 8 weeks) | X |  | X |  | X |  |  | + | [47 empty] | + |  | +
Project Manager
Line Manager | [90 empty] | +
Line Manager | L10 Actual and remaining units monthly grouped by Project, Dep. and Res. (mod) | X |  |  |  | X |  | + | + |  |  |  | + | [29 empty] | + | + |  |  |  |  | + | [29 empty] | + | + |  |  | + | [5 empty] | + |  |  | +
Line Manager | L14 Overallocated Resources grouped by Department (mod) | X |  |  |  | X | [36 empty] | + | + |  |  |  |  | + | [10 empty] | + | + | + | [26 empty] | +
Line Manager | L15 Actual, Remaining and Available units grouped by Department and Resources (mod) | X |  |  |  | X | [36 empty] | + | + |  |  |  |  | + | [8 empty] | + | + | + | + | + | [26 empty] | +
Line Manager | L20 Actual and remaining unit per month grouped by "Factory" (mod) | X |  |  |  | X | [42 empty] | + | [8 empty] | + | + | [29 empty] | + |  | +
Line Manager | L21 Actual and remaining unit per month grouped by GL (mod) | X |  |  |  | X | [42 empty] | + | [8 empty] | + | + | [29 empty] | + |  | +
Line Manager | L22 Actual and remaining unit per month grouped by GL and Department (mod) | X |  |  |  | X | [42 empty] | + | [8 empty] | + | + | [29 empty] | + |  | +
Line Manager | L23 Remaining Units per month grouped by department | X |  |  |  | X
Line Manager | L24 Remaining units per month grouped by Resources (mod) | X |  |  |  | X
Line Manager
Management
Management
Management
Timesheet App.
Timesheet App.
Timesheet App.
BA
BA
BA
Resources
Resources
Resources
Support Functions | S20 Security Profile Privileges (mod) | X
Support Functions | S21 Check Project Code Assignment (mod) | X | [5 empty] | + | + |  |  | + | + | + | + | + | +
Support Functions | S22 Check Resource Code Assignment | X | [40 empty] | + | + |  |  |  |  | + | + | + | +
Support Functions | S24 Resources with no resource calendar | X | [40 empty] | + | + |  | +
Support Functions | S25 Resource Calendars not used | X | [40 empty] | + | + |  | +
Support Functions
Note on B6: This report has the same content as in report A10, A11, A12, A13, A14, A15, A16, A17, A18 and A42.
Note on B7: This report has the same content as in report A23, A24, A26 and A42.
Note on B8: This report shows activities and milestones where there is no Successor or Finish Constraint.
Note on B9: This report shows activities and milestones where there is no Predeceessor or Start Constraint.
Note on B10: This report shows activities which are Successors to Control Milestones
Note on B11: This report shows activities where there is no roles or resources assigned.
Note on B12: This report shows activities where there is a role assigned but no resources.
Note on B13: This report shows activities and milestones where there is no Primary Ressource assigned. Level of effort are not included.
Note on B14: This report shows Task dependant and Level of Effort (LOE) activities which have duration = 0 days.
Note on B15: This report shows activities with nonlabor resources assigned.
Note on B16: This report shows activities and milestones with a Constraint assigned.
Note on B17: This report shows how the resources who are assigned to the opened project are allocated. Overallocation is shown in red and available are shown in green. The limit for the ressource are shown i black.
Note on B18: This report shows activities where resources are assigned with more than 6 hours/day.
Note on B19: This report shows all activities for each ressource within a timeframe from Data Date - 1 week to Data Date + 3 weeks. The report is grouped by Project and Ressource.
Note on B20: This report shows all activities for each ressource The report is grouped by Project and Ressource.
Note on B21: This report shows activities in Progress, where the Expected Finish date is not set.
Note on B22: This report shows activities where Expected finish date is earlier than Data Date.
Note on B23: This report shows activities in progress where remaining units is 0.
Note on B24: This report is showing Actual and Remaining units for all projects per month for resources assigned to the opened Project. The Report is grouped by Department, Employee Type and Ressource.
Note on B26: This report shows all Activities placed in following week. The Report is grouped by Project.
Note on B27: This report shows all critical and overdue Activities grouped by Project.
Note on B28: This report compare activities with Primary Baseline and shows activities where there is variance in Duration, Labor Units, start Date and Finish Date.
Note on B29: This report show all activities and their steps with Status. The activities are grouped by Project.
Note on B30: This report show all activities and their steps with Status. The activities are grouped by WBS.
Note on B31: This report shows actual, remaining and Baseline Budget hours per month from project start to finish. The data ar also shown cumulative. The report is grouped by project.
Note on B32: This report shows actual, remaining and Baseline Budget hours per week from project start to finish. The data ar also shown cumulative. The report is grouped by project.
Note on B33: This reports shows Data date and number of activities in opened Projects. Projects with Data Date older than 2 weeks is marked in red and Projts with Data Date newer is marked in green.
Note on B35: This report shows Level of Effort activities where a Primary ressource is assigned. It is recomended to remove this because the level of effort activity is driven by the relationships and therefore we do not need input from the resources.
Note on B46: This report shows actual and remaining units for fisical Year grouped by Project - Department and ressource.
Note on B47: This report shows resources allocation. Overallocation is shown in red and available are shown in green. The limit for the ressource are shown i black. The Timeframe for the data is Current Date and 6 months ahead.
Note on B48: This report shows Actual, remaining, available and overallocated units for each resource. Overallocation is shown in red and available are shown in green. The limit for the ressource are shown i black. The Timeframe for the data is Current Date and 6 months ahead.
Note on B49: This report shows actual and remaining Hours grouped by "Factory" (e.g. HW and MD) and Employee Type (e.g. SAG and INTCON). The Report is time distributed and shows figures for FY 2005.
Note on B50: This report shows actual and remaining Hours grouped by "Global LIne" (e.g. HW.1 and MD.3) and Employee Type (e.g. SAG and INTCON). The Report is time distributed and shows figures for FY 2005.
Note on B51: This report shows actual and remaining Hours grouped by "Department" (e.g. HW.1.AAL and MD.3.KLF) and Employee Type (e.g. SAG and INTCON). The Report is time distributed and shows figures for FY 2005.
Note on B52: This report shows remaining units per department for the next 12 month from Current Month.
Note on B53: This report shows remaining units per Resource for the next 12 month from Current Month.
Note on B68: This report shows Active Projects where coding is missing.
Note on B69: This report shows Resources where coding is missing.
Note on E2: The project(s) has to be opened before data is shown in the report or layout.
Note on F2: A baseline has to be selected before data for a baseline can be shown in the report or layout.
Note on G2: The report is time distributed per e.g. week or month.
Note on H2: By clicking in this a detailed information will be shown (e.g. screen dump of first page in the report or detailed technical information for the report developer)