## Slide 1: How to Request a new or another Project Manager for a Project in Primavera.
Planning Office
20 December 2005
This document describes the procedure.

## Slide 2: List of Content
Introduction
How
How to look up the name of the Project Manager Responsible (1-2)

## Slide 3: Project Manager request - Introduction
Each project in Primavera do have a Project Managers Responsible assigned.
At a later time the Project Manager who shall join the management of the project, may be assigned.
Requesters may be Line Managers, PLT, PPL, PLC, Local Supporters, and Planning Coordinators.
Primavera Support assigns Project Managers to projects in Primavera.
To ensure that Primavera write and linking rights are assigned to Project Managers in agreement with the Project Manager Responsible this guide has to be followed.

## Slide 4: Project Manager request - How
Before the request (by e-mail) is send to Primavera Support the requester ensures the acceptance by the Project Manager Responsible (for details look at page 5).
The request must include:
  Primavera project ID name.
  Name of the new Project Manager i.e. Primavera login name or e-mail address.
  Documentation for the Project Managers acceptance e.g. e-mail confirmation of the acceptance.
  The responsibility: either Project Manager or Project Manager Responsible must be stated (only one Project Manager Responsible per project allowed).
In case of the withdrawal of a Project Manager, then inform who to be withdrawn as Primavera login name or e-mail address.
Primavera Support assigns or withdraws the writing and linking rights for the Project Manager in question and informs via e-mail the involved parties, that the change has been done.

## Slide 5: How to look up the name of the Project Manager Responsible (1/2)
Open Project Manager
In the EPS select the project in question.
Select “Enterprise” and “OBS…”
2
1
3

## Slide 6: How to look up the name of the Project Manager Responsible (2/2)
In the OBS the project in question is marked.
Select “Users” and find the Login Name of the Project Manager Responsible or Project Manager
Select ”Admin” and “Users…”
In the Login Name columns find the person Login Name e.g. klf178
Name and e-mail address of the Project Manager Responsible.
(If the shown columns are not shown please include those.)
1
2
3
4
5