Planning Coordinator Guide

- Table of Contents

1	Introduction	1

1.1	Purpose	1

1.2	Scope	1

2	Roles and responsibility	1

2.1	Main tasks	1

3	Detailed tasks	2

3.1	Starting Phase	2

3.2	M0 activities	2

3.3	Weekly update 	2

3.4	M1 activities	2

3.5	S4 activities	3

# Introduction

## Purpose

The purpose of this document is to describe the roles and tasks for a Primavera Planning coordinator for product and platform projects.

## Scope

To be used at BenQ Mobile organisation during product and platform development.

# Roles and responsibility

The planning coordinator is the Primavera planning process expert for platform and product projects and shall enable and coach the dedicated team regarding all Primavera planning issues.

## Main tasks

The planning coordinator is responsible for:

- Supporting the projects PL’s in doing their Primavera planning; starting before M0 and ends with “After S4” planning.

- Organize/Coordinate opening and closing of the project(s).

- When necessary assist the PPL’s and PLT’s to secure a consistent and updated project plan in Primavera.

- Assists in evaluations of the project plan and support with relevant reports when requested by the project team.

- Making the Q-Gate rating of the project.

The planning coordinator is not responsible for:

- Quality of the planning data e.g.

  - The content of the activities and estimated effort

  - The links between the activities in the detailed planning

  - The update of the activities in the detailed planning

- Department related issues as overload of resources by all projects.

# Detailed tasks

The detailed planning support starting before M0 and ending with “After S4” planning can be divided up into 5 main phases as follow.

## Starting Phase

- Support PLT in planning issues e.g.

  - Fix Date for start of Project Planning

  - Define timeline for planning and communicate within project team

- Check if all Project Leaders have the necessary PV know-how and 
trigger appropriate training (if needed)

- Support all (Part) Project Leaders for any question related to PV (Planning Coach)

- Schedule complete Project Plan on regular base, analyse Critical Path and trigger responsible Project Planners for planning update

- Check progress of planning

## M0 activities

  - Support M0 Planning

  - Make Q-Gate for WPP part

    - Prepare Q-Gate Reports for WPP

    - Address open topics

    - Run official Q-Gate Reports and deliver results

  - Baselines

    - Make a M0 Master Baseline

  - Close Pre M0 Project after M0

  - Collect feedback for M0 Planning Phase and forward to Template Responsibles & User Group for Lessons Learned

## Weekly update

  - Support in weekly check of planning maintenance

  - Prepare & distribute agreed reports

  - Support the PLT in analysing Critical Path

  - Assist project leaders if irregularities or inconsistencies are found

  - Address open topics and issues in PD-Meeting

## M1 activities

  - Support M1 Planning

  - Make Q-Gate for WPP part

    - Prepare Q-Gate Reports for WPP

    - Address open topics

    - Run official Q-Gate Reports and deliver results

  - Align PLT target plan and PLT bottom up plan

  - Baselines

    - Make a M1 Master Baseline

  - Collect feedback for M1 Planning Phase and forward to Template Responsible for Lessons Learned

## S4 activities

  - Trigger & control Resource Planning of PPLs in “After-S4” project plan

  - Check closing of Part Projects after S4 reached

Note. The planning office will close the “After-S4” project plan when the BA unit informs about the finish date of the project in question.

For more details on Q-Gate refer to Guideline on Primavera IMS Pages

Mainly for project phase starting before M0 until after S4

For more details on weekly update refer to Guideline “Weekly Update” on Primavera IMS Pages

For more details on PLT Master plan refer to Guideline on Primavera IMS Pages