## Slide 1: From Template to Project
Planning Office
17 March 2006
Guideline for setting up a project based on a template

## Slide 2: Purpose
This guideline explains how to set up a project plan in Primavera based on a template, and how to adjust the project plan to the conditions for the project in question.
The guideline addresses project managers e.g. PLT for product projects and project managers responsible for other project types.
Contents:
Purpose
Setting up a new project
Activity settings
Setting up the project plan
Schedule project
Assigning resources
Checking resource availability
Setting the project active

## Slide 3: Setting up a new Project
Request new project
A set up of a new project plan in Primavera is requested by the PLT for product projects, or by the project manager responsible for another type of project. The new project is requested by use of the “Project Request Forms”, which is forwarded to Primavera Support.
The request sent to Primavera Support includes e.g.:
Contents:
Purpose
Setting up a new project
Activity settings
Setting up the project plan
Schedule project
Assigning resources
Checking resource availability
Setting the project active
the template the new projct has to be based on
the project name according to the PMC project database
the person(s) to have write access to the project
the SAP Cost Account
Adjust template to actual conditions
Adjust the Work Breakdown Structure - if needed
Add activities (tasks, milestones) – if needed
Delete activities not needed
Check settings for existing and new activities
Check relationships
Revise dates, durations, and effort (remaining units)
Schedule your project
Optimize the project plan

## Slide 4: Activity Settings (1)
Default Settings for new Activities
Select Projects
Select your project, e.g. in the structure shown
Select tab “Defaults” and check/ensure default settings are as shown
Select the Calendar valid for the site in question
2
3
1
Contents:
Purpose
Setting up a new project
Activity settings
Setting up the project plan
Schedule project
Assigning resources
Checking resource availability
Setting the project active
Notes:
The ”Activity ID Prefix” is dependent on the project in question but typically predefined by the template
The ”Cost Account” is not used (the cost account is specified by use of a project code)
Note a)
Note b)
4

## Slide 5: Activity Settings (2)
Check Activity Settings
Select tab ”General” of Activity Details to view and adjust activity’s properties
Compare settings with table below. These settings should normally be in place from the templates, but check them and remember to set them for new activities
1
2
3
4
5
Settings | 1. Activity Type | 2. Duration Type | 3. Activity Codes | 4. Activity ID | 5. Activity Calendar
Milestone | Start Milestone or Finish Milestone | - | MS-Behaviour; MS-Type; Project Phase | Prefix according to the global function the activity belongs to, e.g. BB12345 | Select according to location
Ongoing activity | Level of Effort | Fixed Duration and Units/Time | Project Phase |  | 
Detailed activity | Task Dependant | Fixed Duration and Units | Project Phase; Connector |  | 
Contents:
Purpose
Setting up a new project
Activity settings
Setting up the project plan
Schedule project
Assigning resources
Checking resource availability
Setting the project active
Note a)
Notes:
a) For Control Milestones with constraint dates (MS-Behaviour = Fixed) the Constraint Type is ”Finish On or Before”

## Slide 6: Setting up the Project Plan (1)
Adjusting the Work Breakdown Structure (WBS)
Adjusting Activities and Milestones
Select “Activities”
Use buttons on right hand side to add, copy, or delete activities.
Select “WBS”
Use buttons on right hand side to add, delete or rearrange WBS elements.
3
Adjusting Activity Duration and Effort (hours)
The example shows details for an activity of type ”Task Dependent”
Select the tab ”Status”
Adjust values for ”Duration – Remaining” and ”Labor Units – Remaining” according to actual estimations
Contents:
Purpose
Setting up a new project
Activity settings
Setting up the project plan
Schedule project
Assigning resources
Checking resource availability
Setting the project active
6
6
5
1
2
4

## Slide 7: Setting up the Project Plan (2)
1
Adjusting the Relationships
add relationships to new activities
remove relationships not relevant for the project in question
check that new and existing activities have predecessors and successors
check Codes for activities with relationships to other projects
agree with counterpart when adding/changing a relationship (link)
Contents:
Purpose
Setting up a new project
Activity settings
Setting up the project plan
Schedule project
Assigning resources
Checking resource availability
Setting the project active
How to Assign Predecessors or Successors
Select tab Predecessors to assign predecessors and tab Successors to assign successors (shown)
click the button ”Assign” to select the successor
enter ”Relationship Type” (Finish-Start, Finish-Finish, etc.)
enter Lag (planned offset in days from an activity to it’s successor)
1
2
2
3
4
Notes:
Control milestones must have no successors except when the successor is of the activity type Level of Effort (Ongoing Activities)
Refer to the guideline “Development Flow Chart” for standard connectors between part projects in a product project
Refer to the guideline ”Linking Concept” for details about how to link between projects

## Slide 8: Setting up the Project Plan (3)
Contents:
Purpose
Setting up a new project
Activity settings
Setting up the project plan
Schedule project
Assigning resources
Checking resource availability
Setting the project active
How to Check/Assign the Activity Code ”Connector”
Activities with a relationship to an activity in another project must have an Activity Code ”Connector” assigned.
The activity code ”Connector” may take one of the following values:
IN – i.e. the activity receives a deliverable from a predecessor in another project
OUT – i.e. the activity delivers a deliverable to an successor in another project
IN+OUT – i.e. the activity receives and delivers a deliverable from/to a predecessor/successor in another project
Select tab ”Codes”
Check whether the activity code ”Connector” is assigned and takes one of the values described above
Else assign the activity code ”Connector” by clicking ”Assign”
Select the appropriate code value and click
1
2
4
3
4

## Slide 9: Schedule Project
After adjusting the project. i.e.:
Contents:
Purpose
Setting up a new project
Activity settings
Setting up the project plan
Schedule project
Assigning resources
Checking resource availability
Setting the project active
the Work Breakdown Structure (WBS)
adding/removing activities
adjusting the relationships
entering the estimations for remaining duration and labor units
schedule the project to validate the resulting project plan and to determine whether the plan fulfills the agreed dates
Notes:
A schedule must be done to see the effect of the changes made to the activities
Before scheduling remember to mark activities started or finished respectively as appropriate.
How to Schedule a Project
Press F9 or select Tools -> Schedule to start scheduling
Click „Advanced Schedule Options“ to check whether settings are as shown below
Click „Schedule“
Optionally mark “Log to file” and enter path to produce a schedule log
1
8
3
2

## Slide 10: Assigning Resources (1)
Contents:
Purpose
Setting up a new project
Activity settings
Setting up the project plan
Schedule project
Assigning resources
Checking resource availability
Setting the project active
Selecting Resources
Agree with the responsible Line Manager number and names of resources assigned to the project
Agree with the responsible Line Manager the amount of effort (labor units) a resource may spend in the project
Assign resources according to the agreements and inform the resources in question.
Assigning Resources to Milestones
Go to tab ”General”
Enter responsible in the cell ”Primary Resource” for reporting the Start, Finish and Expected Finish dates
2
1
Assigning Resources to Ongoing Activities
Ongoing activities may be Phase Activities or activities lasting throughout the whole project duration
Go to tab ”Resources”
Click ”Add Resource” and select resource in the pop-up window
Enter Units/Time (hours/day) the resource is planned to work on this activity in the cell ”Remaining Units/Time”
Note:
Ensure an ongoing activity has no primary resource assigned
3
4
4
5
Note:
A resource is assigned to a milestone only when the resource in question has to update the milestone’s dates via Timesheets

## Slide 11: Assigning Resources (2)
Contents:
Purpose
Setting up a new project
Activity settings
Setting up the project plan
Schedule project
Assigning resources
Checking resource availability
Setting the project active
Assigning Rough Planning/Named Resources
To assign a Rough Planning Resource select the corresponding group of resources at the lowest level
To assign a Named Resource select an individual resource by name
Assigning 2nd, 3rd, ... Resource
If a 2nd, 3rd … resource is assigned, Primavera will take his/her default units/time, e.g. 7h/day, and based on duration calculate the “Remaining Units” for this resource. These hours are added to the total amount of remaining units for the activity
Subsequently adjust the “Remaining Units” (or “Remaining Units/Time”) of all assigned resources to meet the original total remaining units for the work package.
Optionally select primary resource when Timesheets is used for progress feedback (Start, Finish, and Expected Finish dates)
Assigning Resources to Detailed Activities
Go to tab ”Resources”
Click ”Add Resource” and select resource in the pop-up window
1
4
2
3
4
5

## Slide 12: Assigning Resources (3)
Contents:
Purpose
Setting up a new project
Activity settings
Setting up the project plan
Schedule project
Assigning resources
Checking resource availability
Setting the project active
Assigning Resources to Several Activities
In the view ”Activities” select relevant activities with the Shift or Ctrl button
Click the button ”Resources” on the right hand side of the Primavera window
Select resources and click to assign the resources selected
2
2
3
Replacing Resource(s)
Select resource(s) to be replaced in the ”Assign Resource” window and click
Select the new resource in ”Replace selected resource(s) with” window and click
Answer ”No” when you are asked to use Units per Time of the new resource. Primavera will then leave the ”Remaining Units” unchanged
4
4
5
6
1

## Slide 13: Checking Resource Availability
Contents:
Purpose
Setting up a new project
Activity settings
Setting up the project plan
Schedule project
Assigning resources
Checking resource availability
Setting the project active
Checking whether Resources are Overloaded
Select Resource Usage Profile in the toolbar at the top of the view “Activities”
Click “Display”, select “Filter By”, and “Current Project’s Resources”
Select one or more resources. In the lower right-hand window you will see the resulting load for the resources selected
Select “Resource” to display the resource’s work packages in upper right part of the window
Click ”Display” and toggle between / compare ”Show all Projects” and ”Open Projects Only”
2
2
1
3
4
Notes:
In case of resource overload clarify the situation with the line manager and/or the resource.
The black line (“limit”) shows the available working time of an employee (e.g. 7h/day). During e.g. vacation the limit is zero (if the resource calendar is updated).

## Slide 14: Setting the Project to Status ”Active”
Contents:
Purpose
Setting up a new project
Activity settings
Setting up the project plan
Schedule project
Assigning resources
Checking resource availability
Setting the project active
Notes:
When activity planning and resource assignments have been finished the project status has to be changed from “What-if” to “Active”
Resources may book their efforts in Timesheets only for projects with the status “Active”
When a project is “Active” resource’s load is included in the total resource load
When a project is “Active”, tracking of effort is done via resources’ Timesheets, i.e. actual units and new remaining units. Tracking of progress (actual start, actual finish, and Expected Finish Date) may optionally be done via Timesheets for “Active” projects..
Select the view “Projects”
Select and open the project in question
Select the tab “General”
Select “Active” in the drop-down list “Status”
1
3
4
2