## Slide 1: “What if” scenario planning in Primavera
Planning Office
15 December 2005
This guide describes a possible way for the Project Manager Responsible to do “what if” scenario planning for running projects.

## Slide 2: How to do – 1
The first step is to inform all relevant parties that a “what if” scenario planning is starting for the project, to avoid that nobody with writing rights will make changes in the project.
After this a backup must be created for the project for which the “What if” scenario planning will be done. This is done by exporting the project to a XER file. This file contains all relevant information for restoring the complete project. The export is done in the following way:
  Open the project and go to export. Be aware that everybody with writing rights can make changes in the project. This can be avoided by opening the project in exclusive mode.

## Slide 3: How to do - 2
Select Primavera PM/MM – (XER)
Select Project
Mark this for all projects which has to be included in the export.

## Slide 4: How to do - 3
Write in a path (a local drive with Back-up) and a file name for the export file. For easy identification is it recommended to include the project ID or name in the filename.
Be aware that the XER file must be stored on your local drive and not on the Citrix server!!

## Slide 5: How to do - 4
After the export is done and the XER file is stored on a local drive, the “what if” scenario planning can start. The first thing to do is to change the project status to “what if”, then the changes will not be shown in e.g. overall resource loads and resources are not able to book hours in timesheet. Be aware that it is not recommended to do “what if” scenario planning on Fridays because the resources are not able to book hours in the project then.
The scenario planning can then start, e.g. activities can be inserted or deleted, duration changed, resources assigned etc. Basically any scenario work that needs to be done can be done on the project plan. Once this is complete the Project Manager has to decide if the “What if” scenario plan is ok or not:
  If the “What if” scenario planning is ok, the project status is set back from what-if to active and no further changes is needed.
  If the what if scenario planning is not satisfying, the Planning office (+45 72195888 or Primavera_support@benq.com) has to be contacted to set the project plan back to original and reset all the changes in the scenario plan. The XER file will be imported and everything is set back to the status the project had when it was exported.