## Slide 1
Presentation Mα process COM MD Process Training
COM MD PBM PM, Arnold Spitaler
– For internal use only –
Copyright © Siemens AG 2004: Copying of this document and giving it to others and the use or communication of the contents thereof, are forbidden without express authority. Offenders are liable to the payment of damages. All rights reserved in the event of the grant of a patent or the registration of a utility model or design.

## Slide 2: Overview
PLM Process @ COM MD
Process in detail
Milestone description in detail
Project organisation
Additional information

## Slide 3: Milestone meaning
  M = Quarterly portfolio has been defined (Product Roadmap release)
  M0 = Product(s) within platforms have been defined
  S0 = Design freeze / Release of requirements list
  M1 = Release for realization
  S15 = A1 Board basically operable
  S2 = B1 Board basically operable - basic SW- functionality implemented
  S25 = Prototype B1+ tested
  M2 = Sales release
  PS = Production start (optional)
  S3 = Final prototype B2 tested
  DS = Delivery start (optional)
  S4 = Development finished - Product type approved
  M3 = Unlimited series release
  M4 = Ramp down strategy fixed
  M5 F/V = Production stop, Sales activities finalized
  M5 S = Service period terminated

## Slide 4: PLM Process @ COM MD
Basic Platform Framework
2 months
Timegrid: (ongoing)
10 months
12 months
I4
New HW predevelopment process
C4
M5
Portfolio
Creation
Initialisation quarterly
Initialisation per product
Product
Phase-Out
Series
Production
Product
Definition
M4
M3
M0
M
DS
M Kickoff
Product
Realization
M1
S25
M
2 months
I3
Corporate Projects Process
Pre-Development HW + "Hand over“
I0
I1
I3
HW component process, known technology
SW Component Development (product)
Features
C0
C0
C1
C1
CS0
C3
C3
C3
SW Component Development (platform)
Feature/ Technology
Roadmap
P Kickoff
Platform
Realization
P1
P2
P25
P15
P3
Platform
maintenance
P4
Platform
Definition
2 months
C0
P0
Feasibility
Study
BPF
Creation
I0
I1
Innovation
Roadmap
Requirements
P

## Slide 5: Portfolio will be defined using the "Rolling M" concept – aiming at definition "as early as necessary and as late as meaningful possible"
  Focus on one quarter (Q1 → Q4) of the FY portfolio and product definition
Quarterly Focus
Optimized Decision Taking
Matured Market Information
Reduced Lead-time
  Draw decision as early as necessary and as late as meaningful possible increases flexibility to better integrate or react to changed requirements during the FY into product definition process
  Helps to leverage more mature market / competitor information
  Increase TTM level of commitment for every product integrating G-Gates
  Reduced Lead-time of M-alpha to M1 due to concurrent platform & innovation process TTM2/3 in 85G (Target TTM ½ in 95G)
The improved M-alpha process is targeted towards significantly improving the quality and the output provided for all roadmap development and product definition activities introducing Q-Gates concept

## Slide 6: Milestone description in detail
M = Quarterly portfolio has been defined (Product Roadmap release)
  Definition of a quarterly product portfolio and outlook for FY (today + 18 months)
  Review of current portfolio and check for new market opportunities
  Final product profiles
  Project schedule and project organization till M0
  Roadmap changes (additional/cancelled products,
  changes on key features, changes on M3 dates) must be done
  via Change Requests procedure

## Slide 7: Portfolio Management Process Landscape
Innovations
Market- / Competitor Intelligence
Requirement Engineering
Integration of Customer & Consumer Intelligence incl. regional requirements
P1
P2
Portfolio Creation & Product Definition
P15
Portfolio Strategy
SGI
Mid-term implementation
Short-term implementation
Strategic framework
Frontloading
Basis Platform Framework
Platform Creation
Pα
Market Segmentation (Price, Volume)
Consumer Segmentation
Themes Roadmap
Concept Pool
Platform Pool
Time horizon: long-term (min. 5 years)
Brand Strategy (SM MC)
Time horizon: up to 3-5 years
Business Strategy (SM BD)
Technology Strategy (CTO)
Time horizon: next generation & up to 3 years
Portfolio Strategy (PBM PM)
Time horizon: mainly next generation
Functional strategies e.g. Design, UE, Accessories, Applications
M Kickoff
M Kickoff
Q
on- going
Product profiling
Roadmap creation
M
1st check feasibility
Shaping & detailing requirements
Final alignment of prod. def.
Mα
Feasibility check
Q
M0
Roadmap shaping
Roadmap alignment & approval
Roadmap Team
Quart. Portfolio Def Team
Product Def/Rea Team
Notes: <number>
<footer>
<date/time>

## Slide 8: Deliverables of Portfolio Creation & Product Definition Process
TARGET Roadmap:
Number & priority of products for FY
Make or buy defined
Product description
1st alignment with PD budget
Enthusiasm model
Platform concept
Window of opportunity
Target Market (Consumer & Operator)
Consumer Segment
Regional Market Focus
Sales Channel Split
Key operators addressed
Main reference/competitor product
Target Positioning in Portfolio
Story & Technical successor to …
Price point/line
TTM & Lifecycle indication
Addressable Market, planned volumes
Product Idea
Key Theme / related use cases / special characteristics
Dedicated innovation
Input to M-alpha Kick-off:
M-beta deliverables:
M-alpha deliverables:
M0 deliverables:
Quarterly Roadmap PROPOSAL:
Draft Product Profile (Steckbrief)
Design: 1st line drawings based on draft stack-up concepts
Business Case incl. product target splitting
Final Enthusiasm model
Generation and evaluation of alternative product concepts (scenarios)
1st feasibility check incl. resources, TTM
Approval by Sounding Board and staffing Product Def/Rea Teams
FINAL quarterly Roadmap and outlook fiscal year:
Final product profile (Steckbrief)
Detailed product specification (HW, Mech., SW aligned with MCL)
Final feasibility check incl. resources, TTM
Alternative designs ready for mock-up build
Generation and evaluation of alternative modules or components
Reverse calculation for final product concepts
Business Case incl. volumes and prices
Q-Gate approval for products
MD Board confirmation for Product Roadmap
Product Definition
Final product definition done (ref. to MEP) incl. Accessories and Applications
Feasibility check according to MEP done
Detailed planning (Primavera) until M1incl. resources & work packages. Rough planning until M3
Design acceptance & usability test results available
Final design decision (ID 90% defined)
Business Case incl. financial performance during lifecycle, regional split of volumes, risk & opportunities incl. defined measurements.
Q-Gate approval
2 months
2 months
2 months
Shaping & Detailing
Requirements
1st check
feasibility
Product
Profiling
M Kickoff
M Kickoff
M
Q
M0
Roadmap creation
Feasibility Check
Mα
Q
Final Alignment of
Product Definition
Notes: <number>
<footer>
<date/time>

## Slide 9: Product characteristic and product focus will be described by Enthusiasm Model
Support/ provide …
Data storage
Usage/ standby time
Consumer personalization/ Operator customization
Quality of basic functions (I/O-keypad & voice / UI / RF)
Interaction with other devices
Business/ PIM/ Sync
Messaging/Presence/ PoC
Outdoor (robustness/location)
Gaming
Music/Audio
Imaging/Video
Visualization (display/ lighting)
Design/ Material/ Form factor
Basic (As predecessor)
Standby/Talk-time above segment average
Basic SW personalization
Target values (value range)
Basic (As predecessor)
IRDA
Sync.
MMS receive and forward
Robustness; IP54
Basic (As predecessor)
Basic (As predecessor)
Ext.camera(As predecessor)
64K CSTN,130*130
Robust appearance, easy to use keypad
not req.
MNO requirements
Consumer requirements
Enth. (exceed)
Perf.
(meet)
Basic (under fulfilled)
Enth.
Perf.
Basic
not req.
Required air interface: GSM GPRS EDGE UMTS WLAN VoIP (WLAN) other: “…”
Preferred form factor: Bar Slider Clam New/ others: “… e.g. swivel-clam”
X
X
X
Example
Notes: <number>
<footer>
<date/time>

## Slide 10: Integration of M0 tasks into M-alpha process require very close collaboration between Product Def. and Portfolio Def. Team
Product 3
Product cancelled
2 months
2 months
2 months
“Maintain”
Product n
Product 1
Product 2
Quarterly Portfolio Creation
One Portfolio Definition Team
Several dedicated Product Def/Rea Teams
Product cancelled
Roadmapping Process
Product cancelled
Roadmap Team
Product Def/Rea Team
Portfolio Definition Team
Drive product definition projects to ensure TTM and profitability of products.
Mission
Roadmap Team
Create a competitive and feasible product roadmap fulfilling the MD business targets.
Define a competitive and feasible
quarterly portfolio according to
window of opportunity.
Responsibility
- M-Beta, M-alpha approval.
- Overall Responsibility for Global Roadmap Management (from strategy development and identification of new product ideas to handling roadmap CR's)
Define product window of opportunity (based on Gap analysis) and ensure execution by portfolio definition team.
- Preparation of content for M-beta and M-alpha milestones according Q-Gates.
Create detailed products profiles (based on two Pager Window of opportunity template from Target Costing) incl. design renderings at M-Beta and design ready for mock-up at M-alpha
Planning M-Beta, M-alpha and M0 milestones allowing M3 according roadmap plan
- M0 declaration.
- Shaping and detailing requirements according to product profiles and customer enthusiasm model.
- Confirmation of product feasibility at M-alpha milestone (Product content for M-alpha declaration).
Mα
M Kickoff
M
M1
M0
DRAFT
Notes: <number>
<footer>
<date/time>

## Slide 11: Set-up for Portfolio Definition Team and Product Def/Rea Team
PDM
PPM
BA
SPM
PLP
Product Def/Rea Team
(S)PM
MM
PLT
BA
AD (PM)
AS
UE
MarCom
SCM
AD RD
MD
SW
HW
NPI 2/3
ST
CC
QM
GPM tbc
GS APE
Quarterly Portfolio Definition Team “Q1”
SPM UMTS
SPM
Smart
PDM Beijing
PDM: Portfolio Definition Manager (from PBM PM)
MM: Marketing Manager (from PBM PM)
(S)PM: (Senior) Product Manager (from PBM PG or PBM PPM PM)
PLT: Project Leader Technology
PLP: Project Leader Platform (from PD or PBM PPM PE)
= PD Team
= Core Team members (>80%)
CRP: Customer & Regional Portfolio
Market Requirement Spec. MRS +)
Themes
Strategic Portfolio Marketing
CDO Design Strategy
UE User Interface Strategy
MR - Segmentation - Addressable market - Competitor information - PPA Price performance analyses
“Q2”
“Q3”
“Q4”
Product 2
Product n
MD
SW
HW
Product 1
Contribution
till M-Beta
+) Consolidation of market requirements from Regions/Operator (CRP), Marketing and Technology Experts
Platform (PD/PPM)
= if experts for new technologies are required: Core Team members till M-Beta (>80%)
= support functions till M-Beta
= Process owner with decision right
Technology Strategy Features
Innovations / Pre-development
Portfolio Strategy
Pricing & Volume
Consumer Trends & Concepts
Target Costing Office
AS Applications
Sales represented within teams by CRP, but “F” right at Sales for M0/M1 Milestones
CTO
PBM
SM
SCM
GS APE
AD (PM)
Support Functions / Expert Pool (on-going)
= timeframe for responsibility
= timeframe for support
Portfolio Definition Team
Product Def/Rea Team
DRAFT
close
collaboration required
M Kickoff
M Kickoff
M
M0
Mα
M1
Notes: <number>
<footer>
<date/time>

## Slide 12: Approval until M-Alpha will be taken by a Sounding Board, after M-Alpha approval will be taken by Q-Gate procedure
Sounding
Board
PM
PPM
CTO
BA
SM
PD
W. Matuschek
Sounding Board:
Members:
Q-Gate
Product Quality
Sales Fit
Product Profitability
Project Quality
Strategy Fit
Time-to-market
Deficiencies:
prohibitive
major
none to minor
CEO of MD
Head of PBM
PGM
Decision right:
W. Bea
J. Cron / J. Tiepermann
W. Klebsch
R. Dingle
R. Ernst
PBM
CDO
PGM
K. Braun
Q-Gate process responsible: PBM PSO
K. Freeguard
Example 85G
Q-Gate
Q-Gate
Q-Gate
Approval committees
Sounding
Board
Sounding
Board
Quarterly Roadmap PROPOSAL
FINAL Quarterly Roadmap & Outlook
Sounding
Board
Roadmap approval
MD Board confirmation
Product Q-Gate, 2 weeks prior to M-alpha
M Kickoff
M Kickoff
M
M0
Mα
M1
“TARGET” Roadmap Window of Opportunity
Notes: <number>
<footer>
<date/time>

## Slide 13: Milestone description in detail
M0 = Product(s) within platforms have been defined
  Product concept (approved by MD DB) available
  Start of project released by MD DB
  Verified Design proposals issued
  Platform concept provided by Definition Team
  Resource planning available Resources till M1 allocated / Resources M1-M3 planned
  BOM / Budget / Volume / Lifecycle targets defined
  Verified Design proposals issued
  Changes on product must be done via Change Request
  1st business case calculated

## Slide 14: 3 core phases and 4 key items are driving the project from M0 Kick-off, to succeed M0 declaration
= Milestones
MRS = Market Requirement Specification
Marketing
Design, HW & Mechanic
Featuring
M0 Kick-off
Product
Profitability
= Key actions (Kick-off, decisions, results)
Shaping & Detailing
Requirements
Final Alignment of
Product Definition
Evaluation & Feasibility Check
M
Product EBIT
target (M)
Feature
classification &
prioritization
Cost evaluation
&
benchmarking
Risks,
Opportunities
& Measures
Evaluation of solution
(costs vs. commercial or market potential incl. T2M etc.)
M0
Business Case
Continuing Target Gap Analysis
(Verification of Volume, Price, Costs)
Financials
PD & Rea Team in place
“Round Table”
I2
I3
Design Test (mock-up)
Production
of mock-up
Design Briefing
Decision on
Principal Design
Final Design Decision
(ID defined to 90% )
ID study available
Relevant predevelopment finished
Design Review
“Mock-up start”
Alignment Design and
assembly concept (HW)
Design concepts &
initial assembly concepts
Finalizing
Product Story
Shape of M-alpha
product positioning
Securing of consistency of product position and story with related interfaces
M0
M0 Document
PPM: RFQ-Start
PPM: RFI-Start
Alignment &
Resource planning
MRS freeze
Declaration of critical components
Requirements Doc.
per Topic
Detailing Requirements
T-Manager
Kick-off
MRS
Framework
CS0
PPM only: Ready for RfQ
Development of specification and feasibility check
C0
Requirements
integrated in MRS
Components requirements specified

## Slide 15: Standard project will require 4 months from M to reach M0 milestone (10 weeks for PPM products)
Shaping & Detailing
Requirements
Final Alignment of
Product Definition
Evaluation & Feasibility Check
PD & Rea Team in place
“Round Table”
M0 Document
PPM: RFQ-Start
PPM: RFI-Start
Kick off M0
-17
Weeks
0
-9
+8
+4
M0
PBM products: 4 months
PPM products: 10 weeks
= Milestones
-2
S0
= Key actions (Kick-off, decisions, results)
Predevelopment and SW-Components:
C milestones and lead times vary depending on complexity of SW component.
At least I3 of important HW components need to be achieved by the time of M0
M Kickoff
M
Q
M0
Mα
Q
M1

## Slide 16: To secure product profitability, M0 project will be supported by Target Costing Method
Product
Profitability
Feature
classification &
prioritization
Cost evaluation
&
benchmarking
Risks,
Opportunities
& Measures
Evaluation of solution
(costs vs. commercial or market potential incl. T2M etc.)
Product EBIT
target (M)
M0
Business Case
Target Gap Analysis
(Verification of Volume, Price, Costs)
Financials
Classification of features in Basic, Performance and Enthusiasm according to customer requirements and consumer preference
Price point check according to operator requests
Challenging of feature requirements evaluating cost and market potential based on positioning.
Evaluation of feasible scenarios considering estimated resources, T2M, features, costs and positioning/market potential
ACTIVITIES
RESULTS
Feature list (MRS level) prioritisation according to product positioning
Prioritisation by:
- Customer requirements
- Consumer
- Competition
Identification of risks & opportunities along profit drivers and definition of measures
Cost structures
Target costs per
top components
Identification of cost drivers (top components)
incl. SW licences &
IPR costs
Reverse calculation
Risk and Opportunities analysis
Evaluated alternative solutions and decision on final product concept
ACTIVITIES
Market-Potential / Topdown estimate
Gathering of key data
RESULTS
Continuos target gap analysis & verification of key data
M0 Business Case
Volume &
Priceline, regional split
HK overview (BOM, CC, licences, IPR) & overhead costs

## Slide 17: Marketing sub-process shapes product story and keeps market conformity of product
Marketing
Finalizing
Product Story
Shape of M-alpha
product positioning
Securing of consistency of product position and story with related interfaces
Securing of consistency of product position and story
Management of iterative alignment process of market requirements and current MP feasibility
Conception of Lifecycle management
Update and alignment of price position and sales volume
Detailing of product story and alignment with communication story
Alignment of M product position with identified core brand values to be supported by respective product
Detailing product marketing strategy and positioning through
- shape of product story
- clarification of target group
- definition of key product arguments
- performance profile
- product design
Analysis of competition and preparation of SWOT
Definition of necessary accessories (AD)
Final alignment of product story
Key selling arguments:
- Consumer value
- Customer value
- Performance value
- Competitor SWOT
ACTIVITIES
RESULTS
Detailed product story including target group,USP and/or highlights of core features according to product positioning
Reviewed and confirmed product story

## Slide 18: Lead time of SW sub-process is mainly determined by the status of development and complexity of required SW components
Featuring
CS0
Alignment &
Resource planning
MRS freeze
PPM: Ready for RfQ
Declaration of critical components
Requirements Doc.
per Topic
Detailing Requirements
T-Manager
Kick-off
MRS
Framework
Detailed analysis of requirements per component team
Development of missing, or adaptation of existing SW component concepts
Proof of component feasibility
Start of high level SW design specification
Handover of UI concept and general UI principles
Trade mark check new feature names
Final alignment on feasibility of requirements
Planning of work packages and resources to meet T2M/launch date target
Feasibility check and resource planning
Clarification of requirements and communication of M product data to T-Managers and T-Experts in T-Manager Kick-off
T-Managers to hand in detailed feature requirements per topic
Clarification and specification of requirements
Identification and interaction of components
Specified Requirements per Topic (resp.: T-Manager)
MRS (Market Requirement Specification) Framework
ACTIVITIES
RESULTS
C0 reached: SW component requirements specified
MRS completed (all market relevant requirements included)
Declaration of CS0 for all pivotal components
MRS detailed feature list freezed
RfQ feature list
Development of specification and feasibility check
C0
Requirements
integrated in MRS
Components requirements specified

## Slide 19: Process quality of design check is already less critical even if only pivotal HW components achieve I3 milestone on time
Design, HW & Mechanic
I2
I3
Design Test (mock-up)
Production
of mock-up
Design Briefing
Principal Design Decision
Final Design Decision
(ID defined to 90% )
ID studies available
Relevant predevelopment finished
Design Review
“Mock-up start”
Alignment Design and
assembly concept (HW)
Design concepts &
initial assembly concepts
DESIGN
Product design briefings based on identified product position
Creation of product design concepts based on design briefing
ID rough adjustment with assembly concept
Verification (testing) of schematics and PCB layouts
Rework of platform (components, assembly, architecture, etc.)
Alignment with accessories and devices
Customisation concept impact on SCM (SCM PL)
Production of up to 3 mock-up designs (incl. AD examples)
Final preparation regarding Design tests (time schedule to secure necessary input for M0, set up operational team)
Continuation of HW and Mechanic specifications and development (incl. risk management plan)
Conduction of Design and usability tests (incl. AD; for important products)
Evaluation and aggregation of acceptance test outcome, communication to involved parties
Detailed planning of work packages and resources (project plan)
HW/MECHANIC
Briefing of functional block and dimension targets laid (incl. prioritisation of height, depth and width)
Development of initial assembly concept incl. all size determining components
Coordination/manage- ment of HW predeve- lopments
ID studies available
Assembly concepts available
Decision on principle design direction
ACTIVITIES
RESULTS
Freeze of HW and Mechanic requirements
3D IDs
Platform components defined / PCB outline confirmed/agreed (90%)
Relevant predevelopments reached I3
Mock-ups for acceptance test
Models for usability test
Design Acceptance Test results (PPM: first results only)
Usability Test results
Final design decision, including UI (ID defined to 90%)
PPM only: Ready for RfQ

## Slide 20: M0 Declaration Documentation (PM products)
1. Product Profile
2. Strategy & Positioning:
2.1 Target Group & Product Story
2.2 Argumentation
2.3 Performance Profile
2.4 Competition & SWOT
2.5 Lifecycle Management
2.6 Differentiation within Roadmap
2.7 Accessories
2.8 Applications
2.9 Sales Strategy (op/retail, bundles etc.)
3. Specification:
3.1 Design & Mechanics
3.2 Featuring
3.3 Platform Concept
3.4 HW & SW components
3.5 User Interface
3.6 Customization Concept
3.7 UM/Pack
3.8 Variants
3.9 Production
3.10 Quality
3.11 Service
3.12 Patents
4. Financials:
4.1 Market Potential/Top-Down Estimate
4.2 Volume and Priceline at M0 (incl. reg. split)
4.3 HK overview: BOM, CC and Licence Cost
4.4 Financial Performance during Lifecycle
4.5 Business Case at M0 comp. Malpha
4.6 Contingency Plan: risk & opp. incl. AI list
5. ODM Supplier n.a.
5.1 Make or Buy / PPM Strategy
5.2 Supplier Evaluation
5.3 LoI
6. Timeline and Project Organisation:
6.1 Project Schedules
6.2 Ressources
6.3 Rea Team and PD Team
6.4 Signatures
Design Documents
Design Renderings and Mockups
Design Decision Matrix
Design Acceptance Test Results
PSR before M0
Product Profile
Product Status Sheet
Corrective actions
MRS + “Steckbrief M0”
Market Requirement Specification
HW architecture
Platform Overview and Site Strategy
Business Case
See M0 4.1 to 4.6
Decision Right Matrix
Foundation for signature sheet
M0 deliverables
Checklist part I
Checklist part II
SW feature list
Detailed PD SW feature list
User Interface
UI principles: UI styleguide
UI concepts: basic description for new concepts
UI usability test results
Milestones & Ressources
Milestones and ressources until M1 namely
in PMC database („LinderDB“)
PSR M0 Declaration
Design
Product Profile
Product Status Sheet
Business Case at M0 and Malpha
Risk & opportunities incl. AI-list
Open Activities at M0
Signatures
M0 Declaration
Backup: Differentiation within Roadmap
Backup: Volume and Priceline at M0, regions
M0 Document
Project controlling
Accompanying documentation
PD internal documents

## Slide 21: M0 Declaration Documentation (PPM products)
1. Product Profile
2. Strategy & Positioning:
2.1 Target Group & Product Story
2.2 Argumentation
2.3 Performance Profile
2.4 Competition & SWOT
2.5 Lifecycle Management
2.6 Differentiation within Roadmap
2.7 Accessories
2.8 Applications
2.9 Sales Strategy (op/retail, bundles etc.)
3. Specification:
3.1 Design & Mechanics
3.2 Featuring
3.3 Platform Concept
3.4 HW & SW components
3.5 User Interface
3.6 Customization Concept
3.7 UM/Pack
3.8 Variants
3.9 n.a.
3.10 Quality
3.11 Service
3.12 Patents
3.13 Type Approval
3.14 SCM
4. Financials:
4.1 Market Potential/Top-Down Estimate
4.2 Volume and Priceline at M0 (incl. reg. split)
4.3 HK overview: BOM, CC and Licence Cost
4.4 Financial Performance during Lifecycle
4.5 Business Case at M0 comp. Malpha
4.6 Contingency Plan: risk & opp. incl. AI-list
5. PPM Supplier
5.1 Make or Buy / PPM Strategy
5.2 Selection Criteria
5.3 Potential Suppliers / Rfl
5.4 Supplier Evaluation / Audit
5.5 RfQ
6. Timeline and Project Organisation:
6.1 Project Schedule
6.2 Associated Schedules
6.3 Product Rea. Team & Resources
6.4 Risk Assessment
6.5 Program Rea. Team
6.6 Signatures
Design Documents
Design Renderings (ID Study 3D)
Design Decision Matrix
PSR before M0
Product Profile
Product Status Sheet
Corrective actions
RfQ feature list + “Steckbrief
M0”
Market Requirement Specification
Product Marketing
Requirements
Business Case
See M0 4.1 to 4.6
Decision Right Matrix
Foundation for signature sheet
M0 deliverables
Checklist part I
Checklist part II
User Interface
UI principles: UI styleguide
Additional info to achieve Siemens look & feel
Action Planning
from M0 till M1
PSR M0 Declaration
Design
Product Profile
Product Status Sheet
Business Case at M0 and Malpha
Contingency Plan
Open Activities at M0
Signatures
M0 Declaration
Backup: Differentiation within Roadmap
Backup: Volume and Priceline at M0, regions
M0 Document
Project controlling
Accompanying documentation
PD internal documents
Resource Planning