## Slide 1
Product Realization : M0 – M3 COM MD Process Training
COM MD BL PSO PP, Dr. Thomas Masselink
– For internal use only –
Copyright © Siemens AG 2004: Copying of this document and giving it to others and the use or communication of the contents thereof, are forbidden without express authority. Offenders are liable to the payment of damages. All rights reserved in the event of the grant of a patent or the registration of a utility model or design.

## Slide 2: 1. Overview
Overview
PLM Process @ COM MD
Process Phase: Product Realization
Milestone description in detail
Process plan electronics
Project organisation

## Slide 3: 2. PLM Process @ COM MD
Basic Platform Framework
2 months
Timegrid: (ongoing)
10 months
12 months
I4
New HW predevelopment process
C4
M5
Portfolio
Creation
Instantiation quarterly
Instantiation per product
Product
Phase-Out
Series
Production
Product
Definition
M4
M3
M0
M
DS
M Kickoff
Product
Realization
M1
S25
M
2 months
I3
Corporate Projects Process
Pre-Development HW + "Hand over“
I0
I1
I3
HW component process, known technology
SW Component Development (product)
Features
C0
C0
C1
C1
CS0
C3
C3
C3
SW Component Development (platform)
Feature/ Technology
Roadmap
P Kickoff
Platform
Realization
P1
P2
P25
P15
P3
Platform
maintenance
P4
Platform
Definition
2 months
C0
P0
Feasibility
Study
BPF
Creation
I0
I1
Innovation
Roadmap
Requirements
P

## Slide 4: 3. Process Phase: Product Realization
Product(s)
within platform
have been defined
Release for realization
Design Freeze –Release of requirement list
Prototype B1+ tested
Final prototype B2 tested
A1 Board basically operable
Development finished - Product type approved
B1 Board basically operable
Unlimited series Release
Sales Release
Product Realization
M3
M0
DS
M1
S0
S15
S2
S25
S3
M2
S4
PS
Delivery
Start
(Optional)
Production
Start
(Optional)

## Slide 5: 4. Milestone description in detail
M0 = Product(s) within platforms have been defined
  Product concept (approved by MD DB) available
  Start of project released by MD DB
  Verified Design proposals issued
  Platform concept provided by Definition Team
  Resource planning available Resources till M1 allocated / Resources M1-M3 planned
  BOM / Budget / Volume / Lifecycle targets defined
  Verified Design proposals issued
  Change Requests on product must be done via Change Request
  1st business case calculated

## Slide 6: 4. Milestone description in detail
  Market/customer requirements completed
  Design agreed and aligned with mechanical concept
  all external interfaces have been defined
  general MMI-concept defined
  Volume and price line estimation aligned with sales
  BOM and conversion costs updated
  Production site determined
  Offers for external SW- and HW-services/products
S0 = Design freeze / Release of requirements list

## Slide 7: 4. Milestone description in detail
M1 = Release for realization
  Project released by MD Decision Board based on aligned Product Contract and Performance Description
  Time schedule, resource planning, Volumes at M3 and Quality plans committed by team
  Development costs checked and committed by Project Manager
  Volumes and price line committed by sales
  Project organization confirmed
  All used components are qualifiable and available (ideally) as samples
  Primavera operational approval

## Slide 8: 4. Milestone description in detail
  Main board B1 & 1st plastic parts  first devices available
  Prototype operable at room temperature
  Working shielding verified on B1-board
  Prototypes electrically measured and verified
  Mechanical concept verified by simulation and tolerance calculation as well as plan/actual comparison
  All HW-related SW-Functions are implemented and operable
  QM Review has been carried out
S2 = B1 Board basically operable - basic SW-Functionality implemented

## Slide 9: 4. Milestone description in detail
  Product / System (e.g. Accessories) completely available
  Hardware verified and compliant to specification
  Software completely implemented - Final bug fixing started
  Product / System has full functionality partly incorrect behavior
S25 = Prototype B1+ tested

## Slide 10: 4. Milestone description in detail
  Product/System released for sales by Market Introduction Team (milestone not relevant for product development)
  Communication of launch prices including accessories
  Acquisition samples available
  First shipment of dummies to customers done
  Marketing concept completed and internally agreed
M2 = Sales release

## Slide 11: 4. Milestone description in detail
HW has reached S3 maturity. Pilot series finished
Final prototype B2 tested
Risk analysis based on executed tests (fixed to M1)
SW for production and testing has to be implemeted and tested
Rebooting option has to be secured
It is possible to start production of limited volumes even SW hasn‘t
reached final quality status and implementation level
Important:
Secure HW quality to PS (avoid scrap and rework risk, …)
PS = Production start (optional)

## Slide 12: 4. Milestone description in detail
S3 = Final prototype B2 tested
  Internal testing Product / System successfully finished
  All features are completely implemented and tested
  S3 for all subprojects reached
  Start of Type Approval, Field Trial
  Product/System completed, compliant to specifications,
  operable in production (test and assembly)
  All components have been released
  Requirements performance description has been fulfilled

## Slide 13: 4. Milestone description in detail
In case of positive financial impact:
=> Start of delivery makes sense before SW debugging phase is finished.
(Final expected return rate defined by CCQ not reached)
Customer approvals and certifications reached
Decision to be taken by entrepreneur:
(informed about risks by RMEA and NCCPI methods)
Important:
Risks regarding SW have to be under control of entrepeneur. Financial calculation has to be serious.
DS = Delivery start (optional)

## Slide 14: 4. Milestone description in detail
  (Final Milestone for Product Development)
  End of Product Development - Start Sustain Engineering
  Product/System officially approved
  Product/System fulfills all requirements of Product Contract and Performance Description.
  Process capability proven (Quality in production etc.)
  Results of Field Trial available and incorporated
  Release of shipments out of pilot run and ramp up given
S4 = Development finished - Product type approved

## Slide 15: 4. Milestone description in detail
  Shipment volumes agreed at M1 are available on stock
  Service established (swap components / parts available)
  Unlimited shipment releases given
  Hand over to sustain engineering team completed
  Business case calculated and analyzed in comparison with M1
  Discharge of realization team and sub teams
M3 = Unlimited series release

## Slide 16: 5. Process plan electronics
Nov.
Dec.
Jan.
Feb.
Mar.
Apr.
Mai
June
July
Aug.
Sep.
Oct.
Nov.
Dec.
Jan.
M0
S0
M1
S2
S3
S4
M3
B1
B2
B3
M/E6
E9
B11
E12
Rapid- Proto.-parts
PCBs (Main + MMI)
Prototype steps mobiles:
Software
Implementation
Layer1 SW compl.
Type-approval- SW ready
MMI-SW complete
Pilot-
run
A1/A1+
B1
B1+
Ramp-up
A1-SW
B1+-SW
Debugging
Field trial
Type approval
Construction
Mechanical
design
1. Hardtool
Softtool
1st
adjustment
2nd
adjustm.
Acoustic
Display
Design- Fine-tuning
Design
Design
Mechanical Fine-tuning
Softtool
A1-Tests
Hardtool
B1-Tests
B1+
Tool-adj.
B2-Tests
Softtool
B1-
Tests
Hardtool
B2-
Tests
B1+
Data
Sample-p.
Eval.
B2
Data
Sample-prod.
Eval.
Rough-
Specification
Detailed
B2-SW
S15
E7
B5
Concept-evaluations
B1-SW
Data
sample prod.
B1
Eval.
Evaluation
RFT-SW
sample production
A1
Data-
generation
Layout
Schematic/
1. Floor-plan
Data
Eval.
A1+
S25
B2
1. Q.-Tests

## Slide 17: 5. Process plan electronics with milestones PS and DS
M0
S0
M1
S2
S3 - HW
S3
M3
B1
B2
B3
M/E6
E9
B11
E12
Rapid- Proto.-parts
PCBs (Main + MMI)
Prototype steps mobiles:
Software
Implementation
Layer1 SW compl.
Type-approval- SW ready
MMI-SW complete
Pilot-
run
A1/A1+
B1
B1+
Ramp-up
A1-SW
B1+-SW
Debugging
Field trial
Type approval
Construction
Mechanical
design
1. Hardtool
Softtool
1st
adjustment
2nd
adjustm.
Acoustic
Display
Design- Fine-tuning
Design
Design
Mechanical Fine-tuning
Softtool
A1-Tests
Hardtool
B1-Tests
B1+
Tool-adj.
B2-Tests
Softtool
B1-
Tests
Hardtool
B2-
Tests
B1+
Data
Sample-p.
Eval.
B2
Data
Sample-prod.
Eval.
Rough-
Specification
Detailed
B2-SW
S15
E7
B5
Concept-evaluations
B1-SW
Data
sample prod.
B1
Eval.
Evaluation
RFT-SW
sample production
A1
Data-
generation
Layout
Schematic/
1. Floor-plan
Data
Eval.
A1+
S25
B2
1. Q.-Tests
PS
DS
S4

## Slide 18: 6. Project organisation
SProdM: Senior Product Manager
BA: Business Administration
PL-T: Project Leader Technique
ProdM: Product Manager
PL: Project Leader
ST: Systemtest
MD: Mechanical Design
QPM: Quality Project Manager
PE: Procurement Engineer
PTM: Production Technology Manager
AD: Accessory Devices
QM SQA: QM Supplier Quality Assurance
BO: Business Operations
VM: Variant Management
GPM: Global Product Manager
SCM: Supply Chain Management
CC: Customer Care
MM: Marketing Manager
AS: Application & Solution
Product Development Team
SProdM + BA
PL-T
ProdM
PL
HW
PL
SW
PL
ST
PL
MD
QPM
PE
PTM
Operations Team
VM
BO
PL
Start
From
M
Start
From
M
PL-T
AD
PPL
BB
PPL
RF
PPL
EA
PPL
LPD
GPM
SCM
PL
CC
MM
Area
ProdM
PM
AD
PM
AS
Overall functions
Market Team
QM
SQA