## Slide 1: SGL Products Phoenix/Sirius
Phoenix/
Sirius
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
PV-Milestones Phoenix/Sirius:
M0 10.06.04 / 10.06.04
S0 10.09.04 / 03.09.04
M1 25.10.04 / 05.11.04
S15 18.11.04 / 12.11.04
S2 26.01.05 / 08.02.05
S25 06.04.05 / 14.04.05
Pilot Start 12.05.05 / 20.05.05
DS SW Freeze 13.05.05
S3 20.05.05 / 25.05.05
PS 30.05.05 / 02.06.05
DS 10.06.05 / 28.06.05
Major threats:
Temp.-Control-Bug in Intel Memory (Flash/SRAM) may lead to decreased standby time.
=> Countermeasures under evaluation.
Some Key Function of the Project Team stuffed with not so experienced Colleagues.
SW-Maturity at Operator Approval / DS.
=> Help from experienced Experts & Commitment form Mario Topel to reach DS.
Delay of Phoenix-Mechanics due to belated Samples in Shanghai may delay DS.
=> Countermeasures under Evaluation.
Misalignment of Phoenix-Joystick => Countermeasures under Evaluation.
Lead Free Soldering Process seems not to be stable yet (Mozart and I/O-Connector).
Some Accessories of 75 Generation will not be supported by Phoenix and Sirius.
Prototyping:
B1+ Phoenix finished, Sirius ongoing, no change form B1+ to B2 Layout planned.
Highlights
DS still feasible.
SW S25 declared by SW in time
SW stability one week after S25 SW Freeze already remarkable good – though many bugs (up to 30 per day) reported
Info:
Increase of Development Cost in clarification.