## Slide 1: SGL Platform
Schedule/PV/Milestones:
M0: 01.03.05 ( 10.06.04)  S2: N/A  DS: N/A
S0: N/A  S25: 18.03.05 ( 18.03.04)  S4: 01.04.2006
M1: 01.03.05 ( 22.10.04)  S3: 15.12.05  M3: 01.06.2006
SGL Platform planning has been finished and account application is in progress
Resource planning in PV will be done by linking Platform tasks in projects to platform account
Major threats
Introduction of lead-free soldering – new problems appeared in Phoenix/Sirius B1+ boards with Mozart ASIC
Stabilization period between SW S25 and first DS only 9 weeks
HW
First risk release of SGL with G15 mask done.
B6E RF-solution implemented in Adonis – high power consumption in talk mode under investigation.
Use of SGL G15 and Mozart+/Twigo+ not possible for all products due to huge stocks from R65 generation. Careful material management between products required.
SW
Z-IDB4 will be set up on 18.04.05 and will be used for X75 products Phoenix, Sirius, Adonis & Aries
S25 SW has been declared with few exceptions (SWUOTA, BT car kit support, new POC side-key mapping)
Must CR “Background audio playing” can not be integrated in Phoenix DS release