## Slide 1: SGL products Siskin
Schedule/PV/Milestones:
M0: 04.03.05 -> 23.03.05  S2: 22.07.05  DS: 08.12.05
S0: 24.03.05 -> 30.03.05  S25: 26.09.05  S4: 05.01.06
M1: 21.04.05  S3: 01.11.05  M3: 02.02.06
M0 and S0 shifted due to change to 1.3MPix camera / TFT-display and additional necessary surface design modifications.
Roadmap delivery start in 11/05 not feasible due to camera and display changes
Official request to change timeline to 12/05 together with the feature set change on the RM
Major threats
TFT display schedule is very risky. B1 samples only available in time for B1+ devices
HW
Same main PCB as Adonis to be used
Changes wrt Adonis: Liftpart PCB (Epson 732), display, camera, hinge flex, antenna, housing, keypad
SW
Support of MPix-Camera, driver for TFT-display and Epson 732 has been confirmed