## Slide 1: SGL Platform
Schedule/PV/Milestones:
M0: 01.03.05 ( 10.06.04)  S2: N/A  DS: N/A
S0: N/A  S25: 18.03.05 ( 18.03.04)  S4: 01.04.2006
M1: 01.03.05 ( 22.10.04)  S3: 15.12.05  M3: 01.06.2006
X75/85 SGL Platform planning has been finished and account has been opened
Milestones are only SW related. S25 has been declared
Major threats
Introduction of lead-free soldering – new problems appeared in Phoenix/Sirius B1+ boards with Mozart ASIC
Lack of SW resources to assign and fix bugs and to implement CRs (including operator CRs) in time for the DS SW-freeze
Potential delay of the PoC and I-mode implementation in CX70 and early X75 products
HW
New AAC/MP3-chip with integrated MMC-interface for SGL platform under development
Due to high unused stock of key components from R65 generation (SGL, Mozart), careful material management and component allocation to the new SGL products is required
All tests on SGL lead-free showed positive results, no problems expected in mass production.
SW
S25 SW has been declared with few exceptions (SWUOTA, BT car kit support, new POC side-key mapping)
Must CR “Background audio playing” can not be integrated in Phoenix DS release
Estimated number of critical bugs can only be fixed if bug fixing rate is increased – resources needed.

## Slide 2: SGL products SP65
Schedule/PV/Milestones:
M1: 10.12.04 ( 10.12.04) DS: 23.03.05 ( 23.03.05)
S25: 20.01.05 ( 25.01.05 ) S4: 22.04.05 (-)
S3: 25.02.05 ( 28.02.05) M3: 20.05.05 (-)
Major threats
No major threats
HW
No open issues.
SW
SVN47 available for production.
S4 aligned with Phase II product declaration.
Mechanics
No open issues.
Production
Ramp up started
No open technical issues
Claus Dalmose COM MD PD PGG AAL / 11. March 2005

## Slide 3: SGL Products Phoenix/Sirius
Phoenix/
Sirius
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
Milestones Phoenix / Sirius:
M0 10.06.04 / 10.06.04
S0 10.09.04 / 03.09.04
M1 25.10.04 / 05.11.04
S15 18.11.04 / 12.11.04
S2 26.01.05 / 08.02.05
S25 06.04.05 / 14.04.05
Pilot Start 09.05.05 / 23.05.05
DS SW Freeze 19.05.05
S3 20.05.05 / 25.05.05
PS 30.05.05 / 02.06.05
DS 10.06.05 / 28.06.05
Major threats:
Temp.-Control-Bug in Intel Memory (Flash/SRAM) may lead to decreased standby time.
=> Closed: Second source qualified and improvement of first source ongoing.
SW-Maturity at Operator Approval / DS.
SW bug-fixing rate not high enough to reach S3-maturity in time. Resources for approval not ensured.
=> SW resource situation escalated in PSR.
Delay of Phoenix-Mechanics due to belated Samples in Shanghai may delay DS.
=> Closed: Due to overtime on weekends is the project is back on track.
Misalignment of Phoenix-Joystick => Countermeasures under Evaluation, looks promising.
Lead Free Soldering Process seems not to be stable yet
=> SGold and Mozart improved in drop test significant. Results need to be check in B2 run.
Prototyping:
B2 Phoenix started, no change form B1+ to B2 Layout done.
Highlights
DS still feasible, but volumes in June endangered due to missing SW resources.
SW S25 declared by SW in time
SW stability one week after S25 SW Freeze already remarkable good – though many bugs (up to 30 per day) reported
Info:
Increase of Development Cost in clarification.

## Slide 4: SGL products Adonis
Schedule/PV/Milestones:
M0: 22.10.04 ( 25.10.05)  S2: 16.03.05 ( 30.03.05)  DS: 11.07.05
S0: 29.10.04 ( 01.11.05)  S25: 27.04.05  S4: 11.07.05
M1: 10.12.04 ( 23.12.05)  S3: 30.05.05  M3: 08.08.05
Major threats
ESD failure when camera is in view finder mode
BYD is the single supplier for major components LCD and FPC – quality risk in mass production
HW
ESD failure of display (only during active viewfinder mode) - the complete solution still not not available
SW
Defect and bug tracking has started
APAC variant available
Mechanics
Static-load test failed, the improvement is on going
3rd OT will be on time.
Prototyping:
First batch of B1+.1 boards available and some devices will be available in the beginning of next week. Due to “start call fail”, the run might not be finished on time.
The fixture for CT is unstable.

## Slide 5: SGL products Siskin
Schedule/PV/Milestones:
M0: 04.03.05 -> ( 23.03.05)  S2: 22.07.05  DS: 08.12.05
S0: 24.03.05 -> 08.04.05  S25: 26.09.05  S4: 05.01.06
M1: 21.04.05 -> 29.04.05  S3: 01.11.05  M3: 02.02.06
M0 and S0 shifted due to change to 1.3MPix camera / TFT-display and additional necessary surface design modifications. M0 Declaration is also blocked by SAR value risk – red Q-Gate rating
S0 Declaration is blocked by MD Design data, which is needed by LPD for S0 declaration. S0 declaration will be on 08.04.05
M1 Declaration may be delayed. M1 declaration will be on 29.04.05
Roadmap delivery start in 11/05 not feasible due to camera and display changes
Official request to change timeline to 12/05 together with the feature set change on the RM
Major threats
TFT display schedule is very risky. B1 samples only available in time for B1+ devices
BYD is the single supplier
HW
Same main PCB as Adonis to be used
Changes wrt Adonis: Liftpart PCB (Epson 732), display, camera, hinge flex, antenna, housing, keypad
SW
Support of MPix-Camera, driver for TFT-display and Epson 732 has been confirmed

## Slide 6: SGL products Plover
Schedule/PV/Milestones:
M0: 01.04.05 => 08.04.05  S2: 26.09.05  DS: 14.02.05
S0: 26.04.05  S25: 24.11.05  S4: 28.02.06
M1: 03.06.05  S3: 10.01.06  M3: 28.03.06
Major Issues
Deviation from target BOM still appr. 5 Euro
HW
Updated AAC-Chip (SACC-X) required with included SD-Interface and 26MHz SPI. Schedule risky but feasible.
SW
High one-time effort for support of Nano-I/O, AAC chip with SD interface, display interface not via video chip.
Only support of 130x130 display resolution possible as no SGL-based MMI available for 128x128 resolution
Design/Mechanics
Final adjustment to reach 90% surface ongoing