## SG Lite Cockpit
TTM
Cockpit SG Lite | Product | update from date | All |  | Next Milestone | [5 empty] | DS / S4 | [5 empty] | Technical Risk Status
|  |  | Input Status | Status | MS |  | MS date | Input Status | Status | History |  |  | date | Input Status | Status | History | TOP Risks |  | Input Status | Status | History
| SG Lite Platform | F. Zabel | red |  | Plan | S3 | 2005-12-15 | green |  |  | Plan M1 | S4 | 2006-04-01 | green |  |  | I-mode and improved POC UI CRs; Bug fixing rate too slow |  | red
|  | 2005-04-08 |  |  | Current |  | 2005-12-15 |  |  |  | Current |  | 2006-04-01 |  |  |  | VF CR for background audio playing not possible for release 1
| Phönix | G. Flüge | red |  | Plan | S3 | 2005-05-17 | green |  |  | Plan M1 | DS | 2005-06-10 | green |  |  | Increase of requirements after M1, missing SW resources. Late changes of B2 mech.; tight SW schedule; Pb-free |  | yellow
|  | 2005-04-01 |  |  | Current |  | 2005-05-17 |  |  |  | Current |  | 2005-06-10
| Sirius | G. Flüge | red |  | Plan | S25 | 2005-04-14 | green |  |  | Plan M1 | DS | 2005-06-28 | green |  |  | Increase of requirements after M1, missing SW resources. tight SW & mech. schedule; Pb-free; side key not testable. |  | yellow
|  | 2005-04-01 |  |  | Current |  | 2005-04-14 |  |  |  | Current |  | 2005-06-28
| Adonis | Wei Jun Hui | yellow |  | Plan | S25 | 2005-04-27 | green |  |  | Plan M1 | DS | 2005-07-11 | green |  |  | ESD failure when display is in viewfinder mode |  | yellow
|  | 2005-04-08 |  |  | Current |  | 2005-04-27 |  |  |  | Current |  | 2006-07-11 |  |  |  | BYD single supplier for key components
| Plover | F. Zabel | red |  | Plan | M0 | 2005-04-01 | yellow |  |  | Plan M-alpha | DS | 2006-02-14 | yellow |  |  | Tight schedule of new AAC chip |  | yellow
|  | 2005-04-08 |  |  | Current |  | 2005-04-12 |  |  |  | Current |  | 2006-02-20 |  |  |  | High SW effort for last SGL project
| Siskin | Paul Xu | red |  | Plan | M0 | 2004-04-03 | red |  |  | Plan M-alpha | DS | 2005-11-22 | yellow |  |  | Design adaptation for SAR-compliance; Replacement of Epson 732 |  | yellow
|  | 2005-04-08 |  |  | Current |  | 2004-04-01 |  |  |  | Current |  | 2005-12-06 |  |  |  | by Epson 758; Late availability of Epson 758, B1 LCD & camera
| M65 Rescue | O. Byrdal | green |  | Plan | DS | 2005-03-11 | green |  |  | Plan M1 | S4 | 2005-02-28 | green |  |  | Deliveries planned for CeBit done |  | green
|  | 2005-03-11 |  |  | Current |  | 2005-03-04 |  |  |  | Current |  | 2005-02-28 |  |  |  | No further activities
| SP65 | C. Dalmose | green |  | Plan | S4 | 2005-04-22 | green |  |  | Plan M1 | S4 | 2005-04-22 | green |  |  |  |  | green
|  | 2005-04-08 |  |  | Current |  | 2005-04-22 |  |  |  | Current
| Aries | R. Kern | yellow |  | Plan | S25 | 2005-05-20 | green |  |  | Plan M1 | DS | 2005-08-19 | green |  |  | Tight mechanical schedule (B1 does not pass all env. tests) >> counter measures to be tested in B1+ |  | yellow
|  | 2005-04-08 |  |  | Current |  | 2005-05-20 |  |  |  | Current |  | 2005-08-19 |  |  |  | SW bug fixing rate will become NOT sufficient; New bugs are not assigned to pecific components due to lack of expierence & ressources
|  |  | green |  | Plan |  |  | green |  |  | Plan |  |  | green |  |  |  |  | green
[5 empty] | Current | [5 empty] | Current
| Product | update from date | Resource Situation | [7 empty] | Project-Budget | [5 empty] | BOM / HK (incl.Challenge)
|  |  | TOP Problems |  |  |  |  | Input Status | Status | History |  | Budget |  | Input Status | Status | History |  | BOM / HK (incl.Challenge) | Input Status | Status | History
| SG Lite Platform | F. Zabel | Resources for bug assignment and fixing missing |  |  |  |  | red |  |  | target M0 | 3800000 |  | green |  |  | target M1 | N/A | blank
|  | 2005-04-08 | Experience of team (partly), first platform | [7 empty] | 2005-02-28 | 3800000 |  |  |  |  | 2005-02-28
| Phönix | G. Flüge | Experience of Team (partly), |  |  |  |  | red |  |  | target M1 | 7800000 |  | red |  |  | target M1 | 88.75 € LC BOM | green
|  | 2005-04-01 | SW- & EMC-ressources | [7 empty] | 2005-01-31 | 10200000 |  |  |  |  | 2005-01-26 | 87.18 € LC BOM
| Sirius | G. Flüge | Experience of Team (partly), |  |  |  |  | red |  |  | target M1 | 8300000 |  | red |  |  | target M1 | 98.76 € LC BOM | green
|  | 2005-04-01 | SW-ressources | [7 empty] | 2005-02-28 | 9000000 |  |  |  |  | 2005-01-26 | 93.6 € LC BOM
| Adonis | Wei Jun Hui | Share of resources with Adonis LAM and Siskin |  |  |  |  | green |  |  | target M1 | 6300000 |  | green |  |  | target M1 | 64.27 € LC BOM | green
|  | 2005-04-08 | [8 empty] | 2005-02-28 | 4900000 |  |  |  |  | 2005-02-28 | 62.97 € LC BOM
| Plover | F. Zabel | SW-resources for Plover adaptations required |  |  |  |  | yellow |  |  | target M1 |  |  | blank |  |  | target M-alpha | 50.00 € LC BOM | red
|  | 2005-04-08 | [15 empty] | 55.49 € LC BOM
| Siskin | Paul Xu | HW-resources for 1.3MPix and TFT display not |  |  |  |  | yellow |  |  | target M0 | 2600000 |  | green |  |  | target M-alpha | 50.27 € LC BOM | red
|  | 2005-04-08 | confirmed. EA SAR value, and Epson 13758 new chip will affect siskin schedule | [7 empty] | 2005-02-28 | 2600000 |  |  |  |  | 2005-03-18 | 70.72 € LC BOM
| M65 Rescue | O. Byrdal | n/a |  |  |  |  | green |  |  | target | 180000 |  | green |  |  | target M-alpha |  | green
|  | 2005-03-11 | [8 empty] | 2004-12-01 | Booked on M65 X-Cite
| SP65 | C. Dalmose | [5 empty] | green |  |  | target Mar 05 | 765500 |  | green |  |  | target M1 |  | green
|  | 2005-04-08 | [8 empty] | Up to Feb 05 | 303580
| Aries | R. Kern | SW team BEJ: not enough resources & experience to handle incoming bugs |  |  |  |  | yellow |  |  | target M1 | 6300000 |  | green |  |  | target M1 | 64,83€ (HK-over-LC) | green
|  | 2005-04-08 | (see Phönix/Sirius) | [7 empty] | 2005-02-28 | 5800000 | [5 empty] | 64,83€ (HK-over-LC)
[8 empty] | blank |  |  | target M1 |  |  | blank |  |  | target M-alpha |  | blank
Hidden infomation. |  | Legend: History | [8 empty] | Icons: |  | Hints on data entry:
ü
List for traffic light: |  | traffic light has improved compared to last status report | [10 empty] | 1 |  | Traffic lights are driven by input in column named "Input Status"
green | [12 empty] | 2 |  | Trend icons have to be copied from Legend (see left side)
yellow |  | no change of traffic compared to last status report | [10 empty] | 3 |  | Please hide columns D, I, O, T, Y, AD, AI by pressing button
red | [14 empty] | butten for level 1 in the very top left corner of this sheet
blank |  | traffic light worser compared to last status report
[13 empty] | x |  | Please see also comments behind cells
Table for use of history symbols:
|  | last |  | actual |  | Symbol
|  | green |  | green
|  | green |  | yellow or red
|  | yellow |  | yellow
|  | yellow |  | green
|  | yellow |  | red
|  | red |  | red
|  | red |  | yellow or green
Note on D4: green: all lights are green yellow: no red, but one or more yellow lights red: 1 or more red lights
Note on H16: Declared by PD-Team, but Q-Gate is red.
Note on I4: green: max. +1 week yellow: max. +2 weeks red: more than +2 weeks
Note on I28: green: for information. yellow: critical, but only for infomation, team can handle. red: very critical, management support needed.
Note on K4: here please state the trend of traffic light in the past - examples see below
Note on K28: here please state the trend of traffic light in the past - examples see below
Note on L30: date last update
Note on M5: DS when next Milestone is before DS, S4 when next Milestone is DS or later.
Note on M7: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M9: DS when "Next Milestone" is before DS, S4 when "Next Milestone" is DS or later
Note on M11: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M13: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M15: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M17: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M19: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M21: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M23: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on O4: green: max. +1 week yellow: max. +2 weeks red: more than +2 weeks
Note on O28: green: less than +/- 3% deviation *) yellow: between +/- 3% and +6% deviation *) red: more than +/- 6% deviation *) *) shall cover both actual status and M3 prognosis
Note on Q4: here please state the trend of traffic light in the past - examples see below
Note on Q28: here please state the trend of traffic light in the past - examples see below
Note on R30: date last update
Note on T4: green: for information. yellow: critical, but only for infomation, team can handle. red: very critical, management support needed.
Note on T28: green: better or equal yellow: max. +3 Euro red: more than +3 Euro (compared to target)
Note on V4: here please state the trend of traffic light in the past - examples see below
Note on V28: here please state the trend of traffic light in the past - examples see below