## Slide 1: SGL Platform
Schedule/PV/Milestones:
M0: 01.03.05 ( 10.06.04)  S2: N/A  DS: N/A
S0: N/A  S25: 18.03.05 ( 18.03.04)  S4: 01.04.2006
M1: 01.03.05 ( 22.10.04)  S3: 15.12.05  M3: 01.06.2006
X75/85 SGL Platform planning has been finished and account has been opened
Milestones are only SW related. S25 has been declared
Major threats
Introduction of lead-free soldering – new problems appeared in Phoenix/Sirius B1+ boards with Mozart ASIC
Lack of SW resources to assign and fix bugs and to implement CRs (including operator CRs) in time for the DS SW-freeze
Potential delay of the PoC and I-mode implementation in CX70 and early X75 products
HW
New AAC/MP3-chip with integrated MMC-interface for SGL platform under development
Due to high unused stock of key components from R65 generation (SGL, Mozart), careful material management and component allocation to the new SGL products is required
Unlimited release for SGL with new lead-free package has been done
SW
Must CR “Background audio playing” can not be integrated in Phoenix DS release
Estimated number of critical bugs can only be fixed if bug fixing rate is increased – resources needed.

## Slide 2: SGL products SP65
Schedule/PV/Milestones:
M1: 10.12.04 ( 10.12.04) DS: 23.03.05 ( 23.03.05)
S25: 20.01.05 ( 25.01.05 ) S4: 22.04.05 (-)
S3: 25.02.05 ( 28.02.05) M3: 20.05.05 (-)
Major threats
No major threats
HW
No open issues.
SW
SVN47 available for production.
S4 aligned with Phase II product declaration.
Mechanics
No open issues.
Production
Ramp up started
No open technical issues
Claus Dalmose COM MD PD PGG AAL / 11. March 2005

## Slide 3: SGL Products Phoenix/Sirius
Phoenix/
Sirius
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
Milestones Phoenix / Sirius:
M0 10.06.04 / 10.06.04
S0 10.09.04 / 03.09.04
M1 25.10.04 / 05.11.04
S15 18.11.04 / 12.11.04
S2 26.01.05 / 08.02.05
S25 06.04.05 / 14.04.05
Pilot Start 09.05.05 / 23.05.05
DS SW Freeze 19.05.05
S3 20.05.05 / 25.05.05
PS 30.05.05 / 02.06.05
DS 10.06.05 / 28.06.05
Major threats:
SW-Maturity at Operator Approval / DS.
SW bug-fixing rate not high enough to reach S3-maturity in time. Resources for approval not ensured.
=> SW resource situation escalated in PSR. – Resource enhancement still under discussion – fix needed urgently.
B2-SW does not fulfill LCM/Production requirements, - this could block S3.
Sirius side keys currently not testable, - could block S25 for Sirius
Misalignment of Phoenix-Joystick => Countermeasures under Evaluation, looks promising.
Lead Free Soldering Process seems not to be stable yet
=> SGold and Mozart improved in drop test significant. Results need to be check in B2 run.
Prototyping:
B2 Phoenix started, no change form B1+ to B2 Layout done.
Highlights
DS still feasible, but volumes in June endangered due to missing SW resources.
Phoenix declared S25 as planned.
Info:
Increase of Development Cost in clarification.

## Slide 4: SGL products Adonis
Schedule/PV/Milestones:
M0: 22.10.04 ( 25.10.05)  S2: 16.03.05 ( 31.03.05)  DS: 11.07.05
S0: 29.10.04 ( 01.11.05)  S25: 27.04.05  S4: 11.07.05
M1: 10.12.04 ( 23.12.05)  S3: 30.05.05  M3: 08.08.05
Major threats
ESD failure when camera is in view finder mode
BYD is the single supplier for major components LCD and FPC – quality risk in mass production
The test cycle time is quite high (because Adonis is the first clamshell supporting camera)
HW
ESD failure of display (during viewfinder mode) – potential solution found, feasibility under investigation
SW
S25 SW frozen according to plan and delivered to ST
“Start Call” production test failure has been solved
Mechanics
Static-load test failed, the improvement is on going
3rd OT will be on time.
Prototyping:
B1+.1 boards available, B1+.2 will start next week
The test cycle time is quite high (because Adonis is the first clamshell supporting camera)
The fixture for CT is unstable.

## Slide 5: SGL2005 products ARIES status
ARIES
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
High/Lowlight
LF-icons implemented in BL196 (incl. new bootcore for SCOUT tool)
1st VF-SW for ARIES available
All ARIES variants based on 100% CAD data available
Only a few numbers of 1st B1+ devices delivered because customer test & production SW not 100% ok
Flextronics VGA camera supplier announced delay for B2 samples >> BB & SP involved; new timeline negotiated but at high risk
Major threats
none
HW
Flextronics VGA camera supplier announced delay for B2 samples >> BB & SP involved; new timeline negotiated but at high risk
SW
SGL2005 defect priorization & tracking finally started >> bug fixing rate may become not sufficient (to few resources, not enough experience in SW BEJ)
Handling of ClearQuest is not properly (no resource/experience to assign new bugs to components)
Mechanics
Quality of vacuum metallization currently not sufficient >> Switch to silver-copper EMI painting decided; spec conformity of JIGs/metallization area to be confirmed
ALPS display broken during droptests; counter measures does not fix the problems (although Minos, Phoenix, Sirius are ok now)
Uppercase breaks during drop test >> mould flow analysis checked, countermeasures initiated

## Slide 6: SGL products Siskin
Schedule/PV/Milestones:
M0: 04.03.05 -> ( 23.03.05)  S2: 22.07.05  DS: 08.12.05
S0: 24.03.05 -> 14.04.05  S25: 26.09.05  S4: 05.01.06
M1: 21.04.05 -> 29.04.05  S3: 01.11.05  M3: 02.02.06
M0 and S0 shifted due to change to 1.3MPix camera / TFT-display and additional necessary surface design modifications. M0 Declaration is also blocked by SAR value risk – red Q-Gate rating
S0 Declaration is currently blocked by introduction of new Epson 758 and SAR value risk
DS may be affected due to introduction of new Epson 758, new planning ongoing
Major threats
TFT display and camera schedule are very risky. B1 samples only available in time for B1+ devices
Replacement of Epson 732 by 758 chip requires additional qualification time and effort; if first samples of Epson 758 are delayed, complete project will be delayed
HW
Due to cost reasons it is necessary to replace the Epson 732 video chip by the Epson 758
Changes w.r.t. Adonis: Liftpart PCB (Epson 758), display, camera, hinge flex, antenna, housing, keypad
New FPC technology might be required to avoid ESD risk (as currently observed in Adonis)
SW
Support of Epson 758 based drivers for MPix-Camera and the TFT-display under clarification

## Slide 7: SGL products Plover
Schedule/PV/Milestones:
M0: 01.04.05 => 12.04.05  S2: 26.09.05  DS: 14.02.05
S0: 26.04.05  S25: 24.11.05  S4: 28.02.06
M1: 03.06.05  S3: 10.01.06  M3: 28.03.06
Slight shift of DS in official M0 planning by 4 working days.
M0 not reached in plan, only one blocking point which is expected to be solved a few days later.
Major Issues
Business case is still negative (-1.5 Euro per device)
B1 TO dependent on SACC-X sample availability => if delayed, complete project is delayed
HW
Updated AAC-Chip (SACC-X) with included SD-Interface and 26MHz SPI. Schedule risky but feasible.
New BB shielding to be developed as planned G85 vibra will not be developed
SW
High one-time effort for support of Nano-I/O, AAC chip with SD interface, display IF not via video chip.
Design/Mechanics
90% surface ID reached
Drawing of new BB shielding required for M0 declaration

## Slide 8: SGL2005 products ARIES schedule
TODAY
33
32
31
30
29
28
27
26
25
24
23
22
21
20
19
18
17
16
15
14
13
12
11
10
09
08
07
06
05
04
Milestones
Type Approval R&TTE, GCF
(CETECOM)
Mechanics
Software
Vodafone
Operator
Approval
Hardware
M1 11.02.
FEB05
MAR05
APR05
MAY05
JUN05
JUL05
AUG05
S15 04.03.
S2 01.04.
S25 20.05.
AS 03.06.
S3 08.07.
PS 15.07.
DS 19.08.
R&TTE, GCF, FCC
Acoustic / SAR&EMC&RF
Golden Devices
Internal Pretests
Silver Devices
B2-Run
Pilot Run
Ramp Up
3k
B1+ Run
B1 Run
B1+ Tape Out
17.03.
B2 Tape Out
04.05.
Fast Tool Parts (80%)
Fast Tool Parts (100%)
1.Hard Tool Parts (100%)
2.Hard Tool Parts (100%)
3.Hard Tool Parts (100%) „cosmetic only“
B1-SW
B1+-SW
Start z-IDB4
S25-SW
S25 stab.
S3-SW
S3 prep.
S3 stab.
DS prep.
DS-SW
B1+ Samples
1st VF-SW
max. 15 devices
B2 Samples
3rd VF-SW
Note: Weekly SW from z-IDB4
Operator
Approval
Test Prep.
1st Test
Delta Test
Final
2nd VF-SW
VF-DS-SW
S4/M3 30.09.









