## Slide 1
M0 Status Siskin and Plover
Date: 2005-04-18
PPL: Farouk Zabel

## Slide 2: M0 Status Siskin – All declarations signed
SAR-value of Siskin too high => Red Q-Gate Rating
A value below 1.3 Wkg can be committed (which is less than Leopard and less than Adonis) but as this is still above the Siemens internal requirements, an approval from the MD-board is required
The project team (PD- and Rea) will propose to accept this value and declare M0
Epson 732 vs Epson 758 Video Chip
The M0-planning is based on use of the Epson 732 (reuse from Penelope/Phoenix/Sirius)
Epson 758 is pin/SW-compatible to Epson 716 but supports a 1.3MPix cam and fits Siskin feature set
Epson 758 has a cost saving potential of appr. 1.6 Euro
Availability of Epson 758 does not fit to the project schedule and would lead to a delay of 5 weeks, leading to a delivery start mid of January 2006
Epson 758 leads to a high risk due to potential bugs in new chip and additional SW effort.
The project team (PD- and Rea) will propose to change to Epson 758
1.3 MPix-Camera
Time schedule for new 1.3 MPix Camera from BYD (One-stop-shopping) highly risky
Fallback solution to use modified X75 Platform camera (Premier) would require a slight design change (height increase of 0.4mm) => still under investigation
Business Case
BOM/HK ~12 € off M-Alpha target, but ASP increased by ~ 12.50 € due to upgrade to 1.3MPix camera
Overall Business Case is negative => -2.1% EBIT, -5.5 Mio Euro (appr. -2 Euro/phone)

## Slide 3: M0 Status Plover
Declarations: Only LCM1 signature is missing due to missing confirmation from Global Line Manager
Epson SACC-X Music Chip:
Epson SACC-X is pin-compatible to Epson SACC-1 but additionally includes an MMC-Interface
Late availability of Epson 758 does fits to the project schedule but leads to a high risk due to potential bugs in new chip and additional SW effort.
Potential risk associated with high SW-effort for new implementation of:
FM-Radio
Nano I/O connector
USB-Mass Storage
New display and MMC Interface concept
HW
Due to reuse of platform vibra and desing limitations, vibration force most likely does not fulfil TC requirements (worse than Leopard, better than Adonis)
Single source display due to SW limitations (SGL SW only fits to 130x130 and not to 128x128 resolution)
Business Case
BOM/HK ~5 € off M-Alpha target
Overall Business Case is negative => -2.1% EBIT, -5.5 Mio Euro (appr. -2 Euro/phone)