## Slide 1: SGL Platform
Schedule/PV/Milestones:
M0: 01.03.05 ( 10.06.04)  S2: N/A  DS: N/A
S0: N/A  S25: 18.03.05 ( 18.03.04)  S4: 01.04.2006
M1: 01.03.05 ( 22.10.04)  S3: 15.12.05  M3: 01.06.2006
Milestones are only SW related. S25 has been declared
Major threats
Lack of SW resources to assign and fix bugs and to implement CRs (including operator CRs) in time for the DS SW-freeze
Potential delay of the PoC and I-mode implementation in CX70 and early X75 products
HW
New AAC/MP3-chip with integrated MMC-interface for SGL platform under development
Due to high unused stock of key components from R65 generation (SGL, Mozart), careful material management and component allocation to the new SGL products is required
Unlimited release for SGL with new lead-free package has been done
New video chip from Epson 758 in discussion to replace Epson 732
SW
Must CR “Background audio playing” can not be integrated in Phoenix DS release
Estimated number of critical bugs can only be fixed if bug fixing rate is increased – resources needed.

## Slide 2: SGL products SP65
Schedule/PV/Milestones:
M1: 10.12.04 ( 10.12.04) DS: 23.03.05 ( 23.03.05)
S25: 20.01.05 ( 25.01.05 ) S4: 22.04.05 (-)
S3: 25.02.05 ( 28.02.05) M3: 20.05.05 (-)
Major threats
No major threats
HW
No open issues.
SW
S4 aligned with Phase II product declaration.
Mechanics
No open issues.
Production
No open technical issues
Claus Dalmose COM MD PD PGG AAL / 11. March 2005

## Slide 3: SGL Products Phoenix/Sirius
Phoenix/
Sirius
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
Milestones Phoenix / Sirius:
M0 10.06.04 / 10.06.04
S0 10.09.04 / 03.09.04
M1 25.10.04 / 05.11.04
S15 18.11.04 / 12.11.04
S2 26.01.05 / 08.02.05
S25 06.04.05 / 14.04.05
Pilot Start 09.05.05 / 23.05.05
DS SW Freeze 19.05.05
S3 20.05.05 / 25.05.05
PS 30.05.05 / 02.06.05
DS 10.06.05 / 28.06.05
Major threats:
SW-Maturity at Operator Approval / DS.
SW bug-fixing rate not high enough to reach S3-maturity in time. Resources for approval not ensured.
=> SW resource situation escalated in PSR. – Resource enhancement still under discussion – fix needed urgently.
B2-SW does not fulfill LCM/Production requirements, - without change this will block S3.
Sirius side keys currently not testable, - solution for S25 available, improvement for S3 needed
Misalignment of Phoenix-Joystick => Countermeasures under Evaluation, looks promising.
Lead Free Soldering Process seems not to be stable yet
=> SGold and Mozart improved in drop test significant. Results need to be check in B2 run.
Phoenix rear cover: conflict between requirements of mechanical quality and assembly in production, must be solved before ramp up start => Task force set up in Shanghai
Highlights
DS still feasible and volumes in June endangered due to delayed assignment of missing SW resources.
Phoenix and Sirius declared S25 as planned.
Info:
Increase of Development Cost in clarification.

## Slide 4: SGL products Adonis
Schedule/PV/Milestones:
M0: 22.10.04 ( 25.10.05)  S2: 16.03.05 ( 31.03.05)  DS: 11.07.05
S0: 29.10.04 ( 01.11.05)  S25: 27.04.05  S4: 11.07.05
M1: 10.12.04 ( 23.12.05)  S3: 30.05.05  M3: 08.08.05
Major threats
The test cycle time is quite high (The rough estimation from prototype run is 5to 7 seconds more than target)
ESD failure when camera is in view finder mode (local SW available and need verify with latest HW)
BYD is the single supplier for major components LCD and FPC – quality risk in mass production
HW
Due to secrete and the other reason we need one additional PCB TO
ESD failure of display (during viewfinder mode) – temporary SW available need to verify with the latest HW
SW
B2 SW will be delay somehow.
“Start Call” failure not completely solved
Mechanics
Static-load test failed, the improvement is on going
3rd OT will be on time.
Prototyping:
B1+.2 is ongoing and B2 will be delayed some days( This will very likely result in some delay of DS)
The test cycle time is quite high (5to 7 seconds more than target based on the rough estimation)
The fixture for CT is unstable.

## Slide 5: SGL2005 products ARIES status
ARIES
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
High/Lowlight
B1+ Test & Assembly running with reduced customer test coverage; 2-3 days delay of "high volume" device delivery due to technical & logistic problems in prototype shop
Major threats
none
HW
Flextronics VGA camera supplier announced delay for B2 samples >> B2 timeline confirmed, but NO buffer available anymore (weekly update by Flextronics)
SW
SGL2005 defect priorization & tracking finally started >> bug fixing rate may become not sufficient (to few resources, not enough experience in SW BEJ) >> additional budget & resources released
Handling of ClearQuest is not properly (no resource/experience to assign new bugs to components) >> additional resources transferred to BEJ; improvements available
Mechanics
Quality of vacuum metallization currently not sufficient >> Switch to silver-copper EMI painting decided; spec conformity of JIGs/metallization area to be confirmed >> samples in CW16
ALPS display broken during droptests; counter measures does not fix the problems (although Minos, Phönis, Sirius are ok now) >> samples on 26.04.
Uppercase breaks during drop test >> mould flow analysis checked, counter measures initiated >> samples in CW16

## Slide 6: SGL products Siskin
Schedule/PV/Milestones:
M0: 04.03.05 -> ( 23.03.05)  S2: 22.07.05  DS: 08.12.05
S0: 24.03.05 -> 14.04.05  S25: 26.09.05  S4: 05.01.06
M1: 21.04.05 -> 29.04.05  S3: 01.11.05  M3: 02.02.06
M0 and S0 shifted due to change to 1.3MPix camera / TFT-display and additional necessary surface design modifications. M0 Declaration is also blocked by SAR value risk – red Q-Gate rating
S0 Declaration is currently blocked by introduction of new Epson 758 and SAR value risk
DS will be delayed by 5 weeks if Epson 758 is introduced
Major threats
TFT display and camera schedule are very risky. B1 samples only available in time for B1+ devices
Replacement of Epson 732 by 758 chip requires additional qualification time and effort; if first samples of Epson 758 are delayed, complete project will be delayed
HW
Due to cost reasons it is necessary to replace the Epson 732 video chip by the Epson 758
Changes w.r.t. Adonis: Liftpart PCB (Epson 758), display, camera, hinge flex, antenna, housing, keypad
SW
Support of Epson 758 based drivers for MPix-Camera and the TFT-display under clarification

## Slide 7: SGL products Plover
Schedule/PV/Milestones:
M0: 01.04.05 => 12.04.05  S2: 26.09.05 => 10.10.05  DS: 14.02.06 => 16.02.06
S0: 26.04.05  S25: 24.11.05 => 05.12.05  S4: 28.02.06 => 01.03.06 M1: 03.06.05  S3: 10.01.06 => 11.01.06  M3: 28.03.06 => 29.03.06
Slight shift of DS in official M0 planning by 2 working days.
M0 not reached in plan, only one confirmation of LCM1 Global Line Manager missing
Major Issues
Business case is still negative (-2.3 €E per device)
B1 TO dependent on SACC-X sample availability => if delayed, complete project is delayed
HW
Updated AAC-Chip (SACC-X) with included SD-Interface and 26MHz SPI. Schedule risky but feasible.
New BB shielding to be developed as planned
=> therefore, G85 vibra need not be developed
SW
High one-time effort for support of Nano-I/O, AAC chip with SD interface, display IF not via video chip.
Design/Mechanics
90% surface ID reached
Drawing of new BB shielding required for M0 declaration

## Slide 8: SGL2005 products ARIES schedule
TODAY
33
32
31
30
29
28
27
26
25
24
23
22
21
20
19
18
17
16
15
14
13
12
11
10
09
08
07
06
05
04
Milestones
Type Approval R&TTE, GCF
(CETECOM)
Mechanics
Software
Vodafone
Operator
Approval
Hardware
M1 11.02.
FEB05
MAR05
APR05
MAY05
JUN05
JUL05
AUG05
S15 04.03.
S2 01.04.
S25 20.05.
AS 03.06.
S3 08.07.
PS 15.07.
DS 19.08.
R&TTE, GCF, FCC
Acoustic / SAR&EMC&RF
Golden Devices
Internal Pretests
Silver Devices
B2-Run
Pilot Run
Ramp Up
3k
B1+ Run
B1 Run
B1+ Tape Out
17.03.
B2 Tape Out
04.05.
Fast Tool Parts (80%)
Fast Tool Parts (100%)
1.Hard Tool Parts (100%)
2.Hard Tool Parts (100%)
3.Hard Tool Parts (100%) „cosmetic only“
B1-SW
B1+-SW
Start z-IDB4
S25-SW
S25 stab.
S3-SW
S3 prep.
S3 stab.
DS prep.
DS-SW
B1+ Samples
1st VF-SW
max. 15 devices
B2 Samples
3rd VF-SW
Note: Weekly SW from z-IDB4
Operator
Approval
Test Prep.
1st Test
Delta Test
Final
2nd VF-SW
VF-DS-SW
S4/M3 30.09.









