## Sheet1
| SG2 | SGL
pro | Improved BOM (appr. 0.60 Euro) | avoid scrap risk of SGL G12 mask
| Overall reduced budget (resources) | customization for 130x130 resolution available from Hera
All features for Plover included in required SG2 release 2 feature set
con | Market availability in 02/06 not feasible from today's point of view. *M0-date can only be committed mid of April 2005 and is most likely end of May 2005 * SG2 release 1 schedule is highly endangered. Big risk that measures to secure the release 1 schedule endanger " release 2 timeline | One-time development of additional features on SGL such as: * Nano-I/O * support of MMC interface on AAC chip * LCD directly connected to SGL (not via Epson 716/732) * Background audio playing implementation * FM Radio support
| SG2 release 2 "Not committed featueres" include (i) FM Radio support and (ii) Music Player UI incl. playlist (feature level music phone) | Extended support, set up and maintenance period of SGL IDBs by three to six months
| Beijing currently not started SG2 development | Development of new HW (AAC-chip)
* 130x130 display MMI customization not available yet on SG2 SW
Action Items => due 18/03/05
AI-1 | Concept for SWC & SWP-set up for SG2 in Beijing in 02/06 timeframe to be provided | Topel/Kretz/Rudolph
AI-2 | Clarify, if 130x130 MMI from SGL can be reused in SG2 (info from A. Graeupel) | Kretz
AI-3 | Effort and risk estimation for SGL development for Plover expecially with respect to timeline | Topel/Kretz/Rudolph
AI-4 | Clarify if SGL development packages for Plover can be externally handled, also with regard to CM scenario | Kretz