## Slide 1: Minos Status: DS shifted by 2 weeks
Project Status, Timeline, Milestones:
- B2-Tape Out (B2-TO) is further shifted by two weeks
=> Impact: DS shifted by two weeks – new date is (29.09.05)
Reason and consequences of shifting B2-TapeOut:
- B1+ evaluation as input for B2-TO couldn’t be finished due to missing B1+ SW content
- Availability of B2 reference devices 2 weeks too late for starting Type Approval on time
- 2 weeks delay of TA causes also 2 weeks delay of DS
Preconditions to prevent additional delay of DS
- SW delivery (Ver. 36.3) from today 22.04.05 includes all missing B1+ features
- B2 SW for prototype run available latest on 20.05.05
- SW maturity for start of TA pre-tests not later than CW21 (S25-SW-TA freeze)
Minos
Status last week:
Current status:

## Slide 2: Minos: Status of SW deliveries
Project Status, M1 SW planning compared with current SW status:
- SW maturity for B1+ run (some major topics) delayed by 10 weeks (according to HW-to-SW- requirement-list of M1)
- B1+ evaluation as input for B2-TO couldn’t be finished due to missing B1+ SW content
- SW maturity for B2 (SIP8) according to HW-to-SW-requ.-list of M1 delayed by 4 weeks
Preconditions to prevent additional delay of DS
- SW delivery (Ver. 36.3) from 22.04.05 includes all missing B1+ features
Minos
Status M1:
Current
Status
22.04.05:
Status
08.03.05: