## Slide 1: SGL Platform
Schedule/PV/Milestones:
M0: 01.03.05 ( 10.06.04)  S2: N/A  DS: N/A
S0: N/A  S25: 18.03.05 ( 18.03.04)  S4: 01.04.2006
M1: 01.03.05 ( 22.10.04)  S3: 15.12.05  M3: 01.06.2006
Milestones are only SW related. S25 has been declared
Due to shift of Plover to SG2, milestones and budget planning need to be adapted.
Major threats
Assignment and fixing of bugs gained speed, but still critical
Potential delay of the PoC and I-mode implementation in CX70 and early X75 products
HW
Due to the realization of Plover on SG2 the new Epson AAC chip will not be continued
New video chip from Epson 758 in discussion to replace Epson 732
SW
Must CR “Background audio playing” can not be integrated in Phoenix DS release
Additionaol resources for fixing estimated number of critical bugs have been assigned

## Slide 2: SGL products SP65
Schedule/PV/Milestones:
M1: 10.12.04 ( 10.12.04) DS: 23.03.05 ( 23.03.05)
S25: 20.01.05 ( 25.01.05 ) S4: 22.04.05 ( 19.04.05)
S3: 25.02.05 ( 28.02.05) M3: 20.05.05 (-)
Major threats
No major threats.
HW
No open issues.
SW
S4 aligned with Phase II product declaration
Mechanics
No open issues.
Production
No open technical issues.
Claus Dalmose COM MD PD PGG AAL

## Slide 3: SGL Products Phoenix/Sirius
Phoenix/
Sirius
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
Milestones Phoenix / Sirius:
M0 10.06.04 / 10.06.04
S0 10.09.04 / 03.09.04
M1 25.10.04 / 05.11.04
S15 18.11.04 / 12.11.04
S2 26.01.05 / 08.02.05
S25 06.04.05 / 14.04.05
Pilot Start 09.05.05 / 23.05.05
DS SW Freeze 19.05.05
S3 20.05.05 / 25.05.05
PS 30.05.05 / 02.06.05
DS 10.06.05 / 28.06.05
Major threats:
SW-Maturity at Operator Approval / DS.
SW bug-fixing rate not high enough to reach S3-maturity in time. Resources for approval not ensured.
=> SW resource situation escalated in PSR. – Resources have been made available, but dedicated nomination still open.
B2-SW does not fulfill LCM/Production requirements, - without change this will block S3.
Sirius side keys now currently not testable, - solution for S25 available, improvement for S3 needed
Misalignment of Phoenix-Joystick => Countermeasures under Evaluation, looks promising.
Lead Free Soldering Process seems not to be stable yet
=> SGold and Mozart improved in drop test significant. Results need to be check in B2 run.
Phoenix rear cover: conflict between requirements of mechanical quality and assembly in production, must be solved before ramp up start => Task force set up in Shanghai
3C-Exemption certificate for device import to China
Highlights
Assignment of missing SW resources for bug fixing help keep DS and volumes in June feasible, situation relaxed, but still critical.
Phoenix and Sirius declared S25 as planned.
Info:
Increase of Development Cost in clarification.

## Slide 4: SGL products Adonis
Schedule/PV/Milestones:
M0: 22.10.04 ( 25.10.05)  S2: 16.03.05 ( 31.03.05)  DS: 11.07.05
S0: 29.10.04 ( 01.11.05)  S25: 27.04.05  S4: 11.07.05
M1: 10.12.04 ( 23.12.05)  S3: 30.05.05  M3: 08.08.05
Major threats
The test cycle time is too high (a rough estimation is 5to 7 seconds above target), this requires implementation of an additional camera test tower and will have some impact on the BC
Several problems popped up one day before B2 start (Vibrator and Lift part) the impact is under evaluation
BYD is the single supplier for major components LCD and FPC – quality risk in mass production
HW
Several unexpected issue happened last Thu. & Fri. (Vibrator and Lift part) the impact is under evulation
B2+ tape out (originally not planned) in next week.
Final EMC solution available and will be implemented in B2+ devices (B2+ PCB with B2 housing).
SW
B2 SW released on Apr.23.
APAC variant is too late for S25.
Mechanics
Static-load test failed, the improvement is on going
3rd OT will be on time.
Prototyping:
The test cycle time is quite high (see “Major threats”)
B2 SMT will start on 25.04.2005; assembly could start on 26.04.05.

## Slide 5: SGL2005 products ARIES status
ARIES
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
High/Lowlight
B2 MMI-PCB not necessary, B1+ status can be reused !!!
B1+ devices passed LEADFREE drop test with good results (with TWIGO+ BB version)
z-IDB4 started with problems >> no S25-SW freeze on 22.04.
Major threats
none
HW
Flextronics VGA camera supplier announced delay for B2 samples >> B2 timeline confirmed, but NO buffer available anymore (weekly update by Flextronics)
SW
Bug fixing rate may become not sufficient (too few resources, not enough experience in SW BEJ) >> additional budget & resources released
Handling of ClearQuest is not properly (no resource/experience to assign new bugs to components) >> additional resources transferred to BEJ; improvements still not sufficient >> NO real status of open bugs and bug fixing statistics
Mechanics
Samples of upper cases with EMI painting STILL not within spec >> LUMBERG as integrated supplier installed QM directly at Greenpoint >> new samples in CW17
ALPS display broken during droptests; counter measures does not fix the problems (although Minos, Phoenix, Sirius are ok now) >> samples on 26.04.
Uppercase breaks during drop test >> mould flow analysis checked, counter measures initiated >> new samples showed improved performance but still not sufficient, further improvements will be implemented

## Slide 6: SGL products Siskin
Schedule/PV/Milestones:
M0: 04.03.05 -> ( 23.03.05)  S2: 15.09.05  DS: 16.01.06
S0: 24.03.05 -> 14.04.05  S25: 02.11.05  S4: 01.03.06
M1: 21.04.05 -> 19.05.05  S3: 06.12.05  M3: 01.04.06
M0 and S0 shifted due to change to 1.3MPix camera / TFT-display and additional necessary surface design modifications. M0 Declaration is also blocked by SAR value risk – red Q-Gate rating
DS will be delayed to Jan 16, 2006, if Epson 758 is introduced
S0 Declaration is currently blocked by introduction of new Epson 758
M1 Declaration date is shifted to May 19, 2005
Major threats
TFT display and camera schedule are very risky. B1 samples only available in time for B1+ devices
Replacement of Epson 732 by 758 chip requires additional qualification time and effort; if first samples of Epson 758 are delayed, complete project will be delayed
HW
Due to cost reasons it is necessary to replace the Epson 732 video chip by the Epson 758
Changes w.r.t. Adonis: Liftpart PCB (Epson 758), display, camera, hinge flex, antenna, housing, keypad
SW
Support of Epson 758 based drivers for MPix-Camera and the TFT-display under clarification
Some Resources will join in Siskin project for LCD and Camera development

## Slide 7: SGL products Plover
Schedule/PV/Milestones:
M0: 01.04.05 => tbd  S2: 26.09.05 => tbd  DS: 14.02.06 => tbd
S0: 26.04.05 => tbd  S25: 24.11.05 => tbd  S4: 28.02.06 => tbd M1: 03.06.05 => tbd  S3: 10.01.06 => tbd  M3: 28.03.06 => tbd
All milestones have to replanned due to shift of platform from SGL to SG2.
Major Issues
Business case is still negative (-2.3 € per device)
SG2 Rel 2 schedule unclear – M0 status expected for beginning of June. DS needs to be shifted to 04/06
HW
New stack-up concept needs to be done, keeping SGL based PCB size included SD-Interface and 26MHz SPI. Schedule risky but feasible.
SW
SG2 Rel. 2 schedule highly critical for currently planned DS.
Design/Mechanics
90% surface ID reached – Design shall remain unchanged

## Slide 8: SGL2005 products ARIES schedule
TODAY
33
32
31
30
29
28
27
26
25
24
23
22
21
20
19
18
17
16
15
14
13
12
11
10
09
08
07
06
05
04
Milestones
Type Approval R&TTE, GCF
(CETECOM)
Mechanics
Software
Vodafone
Operator
Approval
Hardware
M1 11.02.
FEB05
MAR05
APR05
MAY05
JUN05
JUL05
AUG05
S15 04.03.
S2 01.04.
S25 20.05.
AS 03.06.
S3 08.07.
PS 15.07.
DS 19.08.
R&TTE, GCF, FCC
Acoustic / SAR&EMC&RF
Golden Devices
Internal Pretests
Silver Devices
B2-Run
Pilot Run
Ramp Up
3k
B1+ Run
B1 Run
B1+ Tape Out
17.03.
B2 Tape Out
04.05.
Fast Tool Parts (80%)
Fast Tool Parts (100%)
1.Hard Tool Parts (100%)
2.Hard Tool Parts (100%)
3.Hard Tool Parts (100%) „cosmetic only“
B1-SW
B1+-SW
Start z-IDB4
S25-SW
S25 stab.
S3-SW
S3 prep.
S3 stab.
DS prep.
DS-SW
B1+ Samples
1st VF-SW
max. 15 devices
B2 Samples
3rd VF-SW
Note: Weekly SW from z-IDB4
Operator
Approval
Test Prep.
1st Test
Delta Test
Final
2nd VF-SW
VF-DS-SW
S4/M3 30.09.









