## Slide 1: SG2 platform – reporting – 85 generation
Platform Timeline
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
Status
milestones, timeline, primavera planning
target M0 31.03.2005 is not feasible from SW platform point of view
-> M0 platform date will be communicated at 2005-04-22 (M0 target A06/2005)
o follow up milestones are not verified yet
development aspects
+ Top level feature list of X85 SG2 PF SW Release 2 frozen.
+ CCB process established. Regular CCB meetings will start in M05/2005.
o CCB buffer of 7MY decided (PD & PBM management). Split into departments and SW components ongoing.
o Final alignment of ‘Requirements to SW’ list ongoing. DL feedback scheduled for E04/2005 and CA feedback until E05/2005.
o Decision: Plover should base on SG2 PF. Impact to platform development open.
major threats
SW is heavily booked by Rel1 activities (PLCs)
  estimation of component milestone not before cw16
o SW top level requirement assignment to component projects is ongoing. First version is scheduled for 2005-05-13. Finalization is planned until 2005-06-10.
  CTO TS have to assure detailed FL
M0 (Rel2) target A06/2005
DS (Rel2) target 02/2006 (to be verified)
Notes: <number>
<footer>
<header>
<date/time>

## Slide 2: SG2 platform – reporting – 85 generation
Software Platform
System Test
Platform
- No fixed M0 date yet; no rough project pan until DS yet
+ Detailing SW requirements ongoing
o Announcement of M0 date is scheduled for 22.04.05
+ SW for Polaris A1 run was provided in time and boards were produced as planned
o In a meeting of Klebsch and Lepold a CR Buffer of 7 PY (3,5 PY in FY04/05) was discussed, but not yet officially agreed by PD (budget clarification is still ongoing)
o First CCB Meeting was held and it was decided to immediately start the evaluation of some high prio CRs (the regular CCB work on all other CRs will start mid/end 05/05)
M0:Untill no Feature list will provide by PL-SW, ST can not set the neseccary Resources. Rough planning available.
S0: The Approval strategy according to the necessary Certification could not be seattled cause of missing timeline from SW.
M1: Neither budget planning could be succeeded nor Resourcen planning and Testplan setup could be executed by ST.
Blue marked text is new, black is old, red will serve as indicator for the red traffic light

## Slide 3: SG2 platform – reporting – 85 generation
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
Hardware Platform
+ HW feature list for X75 and X85 SG2 platform available. Update scheduled for Mcw17.
+ Prototype planning list for X75 and X85 products available.
+ First master schematic release for X85 SG2 platform available.
+ Malpha.4_1 tape out done. First boards are available. Because of restrictions in prototype shop main run delayed to cw16. Assembling ongoing. Board delivery planned until Ecw17.
o Primavera planning started for X85 SG2 HW platform. Expert planning team set up. Subprojects defined and establishment requested from PV support.
o X85 SG2 HW concept discussions in some parts are ongoing: + Status LED concept defined. Detailed measurements are ongoing. + Illumination concept defined. Alignment with product projects ongoing. o Flash LED interconnection @ SG2: X75 SG2 concept available. Second option under evaluation. o 2Mpix camera @ SG2: Feature not confirmed until now. Related CR available. Evaluations are ongoing.
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4: SG2 products – Polaris -> Status Update
Polaris
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
milestones, timeline, Prima Vera planning
M0 -> Q-Gate not passed:
Status reached (except SW relevant WP): MD; HW; LCM (NPI 2&3)
Status open: ST; SW; QA
S0:
Status reached (except SW relevant WP): MD
Status open: HW; LCM (NPI 2&3); ST; SW; QA
Prima-Vera Planning
Not completed due to missing links to platform
All HW relevant WP in time with “Target S15”: 29.06.05
technical aspects, next steps
IMD window will be employed
A1: PCBA Build: done on 15-Apr-05, first pass rate 95%, ‘normal mode’ possible. SLA Build: 06.06.05 ;WB TO: done on 18-Apr-05
major threats
TimeLine:
M0: 3.5 month delayed
S2: 1 month delayed (based on SW Platform DL C25 planning 09/05)
Time between M1 and AS app. 3month only (based on M1 08/05 PL-T assumption)
X85 portfolio review - invest on hold – decision on 25-Apr
BC:
Target cost gap of app. 7,-EUR due to reduced ASP and additional PD Budget (1/6 of X75 platform cost to be covered by Polaris)

## Slide 5: SG2 products – Polaris -> Decisions
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
Decisions Due:
Declaration of M0 Milestone
Release of Invest/ Budget till M0 (has been passed on to PBM Head as well)
  ->PD Budget till M0 (6/05) 1.7Mio EUR (including SCM Budget 135k EUR)
  ->Tooling due till M0 (6/05) 1.478Mio EUR
Proposal of Polaris Project Team:
Do not declare M0 Polaris due to missing input from platform, esp. missing timeline
Continue WP as planned with preliminary Time Schedule and release Budget/ Invest in order to minimize DS delay

## Slide 6: SG2 products - Swift
Swift
milestones, timeline, PrimaVera planning
Swift rough PV planning done, alignment of detailed plans ongoing
„Steckbrief“ is updated
SW M0 delayed to M June 2005
=> the current Swift DS date is extremely unrealistic from project point of view => T-PSR feedback: continue with the current DS target; a SW delay is not known today
technical aspects, next steps
remaining Swift S0-HW issues solved, S0-HW status will be reached by 22.04.2005
Swift A1 PCB tapeout on 04.05.2005
Swift might need a non platform display because of a different flex length
major threats
Swift has reached M0 status for all HW related topics!
Swift BOM target cannot be met (about 7€ delta); CRW showed only very minor saving potentials
Swift supplier selection was done and agreed between purchasing and mechanics
Platform SW timeline missing therefore an overall project planning is not possible => Swift and Ibis will not declare M1 or M1-HW
The needed investment until end of May was approved but must not be spent before cw17
Q-GATE conclusion:
  team proposes to continue until expected M0 in M June 05;
  bring SW issue to management attention
Blue marked text is new, black is old, red will serve as indicator for the red traffic light

## Slide 7: SG2 products - Ibis
Ibis
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
milestones, timeline, PrimaVera planning
Ibis rough PV planning done,
„Steckbrief“ is updated
SW M0 delayed to M June 2005
=> the current Swift DS date is extremely unrealistic from project point of view => T-PSR feedback: continue with the current DS target; a SW delay is not known today
technical aspects, next steps
Ibis M0-HW status is beginning of May – except for SW related issues no M0 stopper identified so far
major threats
Ibis BOM target cannot be met (about 7€ delta)
Platform SW timeline missing therefore an overall project planning is not possible

## Slide 8: SG2 products - Brambling
Brambling
milestones, timeline, Primavera planning
technical aspects, next steps
major threats
Blue marked text is new, black is old, red will serve as indicator for the red traffic light

## Slide 9: SG2 products - Hummingbird
Humming-
bird
milestones, timeline, Primavera planning
technical aspects, next steps
major threats
Blue marked text is new, black is old, red will serve as indicator for the red traffic light

## Slide 10: actions SG2 85 platform & products