## EG V3, EG Lite Cockpit
TTM
Cockpit EG Lite EG V3 | Product | update from date | All |  | Next Milestone | [5 empty] | DS / S4 | [5 empty] | Technical Risk Status
|  |  | Input Status | Status | MS |  | MS date | Input Status | Status | History |  |  | date | Input Status | Status | History | TOP Risks |  | Input Status | Status | History
| Libra | C. Ziegler | red |  | S25 | Plan | 2005-02-17 | red |  |  | Plan | DS | 2005-05-06 | yellow |  |  | high power consumption (platform) |  | yellow
|  | 2005-03-07 |  |  |  | Current | 2005-03-18 |  |  |  | Current |  | 2005-05-20 |  |  |  | Critical SW bugs (S25 relevant for ST)
| Dorado | C. Ziegler | red |  | S2 | Plan | 2005-01-19 | red |  |  | Plan | DS | 2005-05-19 | red |  |  | high power consumption (platform) |  | yellow
|  | 2005-03-07 |  |  |  | Current | 2005-03-18 |  |  |  | Current |  | 2005-06-16 |  |  |  | Critical SW bugs (S2 relevant for ST)
| Pegasus | C. Ziegler | red |  | S2 | Plan | 2005-02-28 | red |  |  | Plan | DS | 2005-05-30 | red |  |  | high power consumption (platform) |  | yellow
|  | 2005-03-07 |  |  |  | Current | 2005-03-18 |  |  |  | Current |  | 2005-06-17 |  |  |  | Critical SW bugs (S2 relevant for ST)
| Flamingo | C. Ziegler | green |  | S15 | Plan | 2005-03-17 | green |  |  | Plan | DS | 2005-10-24 | green |  |  | Color separation at BALDA not feasible |  | green
|  | 2005-03-07 |  |  |  | Current | 2005-03-17 |  |  |  | Current |  | 2005-10-24
| Quail | C. Ziegler | red |  | M0 | Plan | 2005-02-28 | red |  |  | Plan | DS | 2006-01-17 | green |  |  | tech. feasibility of antenna concept |  | yellow
|  | 2005-03-07 |  |  |  | Current | 2005-03-18 |  |  |  | Current |  | 2006-01-24
| Finch | C. Ziegler | green |  | M0 | Plan | 2005-03-25 | green |  |  | Plan | DS | 01.05 | green |  |  |  |  | green
|  | 2005-03-07 |  |  |  | Current | 2005-03-25 |  |  |  | Current |  | 01.05
| Pelicane | C. Ziegler | green |  | M0 | Plan | 2005-04-22 | green |  |  | Plan |  | 03.06 | green |  |  |  |  | green
|  | 2005-03-07 |  |  |  | Current | 2005-04-22 |  |  |  | Current |  | 03.06
| Lark | not started yet | blank |  |  | Plan |  | blank |  |  | Plan |  | 06.06 | blank |  |  |  |  | blank
[6 empty] | Current |  |  |  |  | Current
| Product | update from date | Resource Situation | [7 empty] | Project-Budget | [5 empty] | BOM / HK (incl.Challenge)
|  |  | TOP Problems |  |  |  |  | Input Status | Status | History |  | Budget |  | Input Status | Status | History |  | BoM over Life Cycle | Input Status | Status | History
| Libra | C. Ziegler | no problems yet |  |  |  |  | green |  |  | target M1 |  |  | blank |  |  | M1 value | 36.72 EUR | green
|  | 2005-03-07 | [14 empty] | S2 - 24.01.2005 | 34.51 EUR
| Dorado | C. Ziegler | EA resoures for 2nd housing supplier missing |  |  |  |  | red |  |  | target |  |  | blank |  |  | M1 value | 24.44 EUR | yellow
|  | 2005-03-07 | [14 empty] | S2 - 25.02.2005 | 25.39 EUR
| Pegasus | C. Ziegler | no problems yet |  |  |  |  | green |  |  | target |  |  | blank |  |  | M1 value | 41.67 EUR | green
|  | 2005-03-07 | [14 empty] | S2 - 03.02.2005 | 36.15 EUR
| Flamingo | C. Ziegler | no problems yet |  |  |  |  | green |  |  | target |  |  | blank |  |  | Malpha value | 48.52 EUR | green
|  | 2005-03-07 | [14 empty] | M1 - 27.01.2005 | 45.55 EUR
| Quail | C. Ziegler | [5 empty] | blank |  |  | target |  |  | blank |  |  | target M-alpha |  | blank
2005-03-07
| Finch | C. Ziegler | [5 empty] | blank |  |  | target |  |  | blank |  |  | target M-alpha |  | blank
2005-03-07
| Pelicane | C. Ziegler | [5 empty] | blank |  |  | target |  |  | blank |  |  | target M-alpha |  | blank
2005-03-07
| Lark | not started yet | [5 empty] | blank |  |  | target |  |  | blank |  |  | target M-alpha |  | blank
Hidden infomation. |  | Legend: History | [8 empty] | Icons: |  | Hints on data entry:
ü
List for traffic light: |  | traffic light has improved compared to last status report | [10 empty] | 1 |  | Traffic lights are driven by input in column named "Input Status"
green | [12 empty] | 2 |  | Trend icons have to be copied from Legend (see left side)
yellow |  | no change of traffic compared to last status report | [10 empty] | 3 |  | Please hide columns D, I, O, T, Y, AD, AI by pressing button
red | [14 empty] | butten for level 1 in the very top left corner of this sheet
blank |  | traffic light worser compared to last status report
[13 empty] | x |  | Please see also comments behind cells
Table for use of history symbols:
|  | last |  | actual |  | Symbol
|  | green |  | green
|  | green |  | yellow or red
|  | yellow |  | yellow
|  | yellow |  | green
|  | yellow |  | red
|  | red |  | red
|  | red |  | yellow or green
Note on D4: green: all lights are green yellow: no red, but one or more yellow lights red: 1 or more red lights
Note on I4: green: max. +1 week yellow: max. +2 weeks red: more than +2 weeks
Note on I24: green: for information. yellow: critical, but only for infomation, team can handle. red: very critical, management support needed.
Note on K4: here please state the trend of traffic light in the past - examples see below
Note on K24: here please state the trend of traffic light in the past - examples see below
Note on M5: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M7: DS when "Next Milestone" is before DS, S4 when "Next Milestone" is DS or later
Note on M9: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M11: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M13: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M15: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M17: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M19: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on O4: green: max. +1 week yellow: max. +2 weeks red: more than +2 weeks
Note on O24: green: less than +/- 3% deviation *) yellow: between +/- 3% and +6% deviation *) red: more than +/- 6% deviation *) *) shall cover both actual status and M3 prognosis
Note on Q4: here please state the trend of traffic light in the past - examples see below
Note on Q24: here please state the trend of traffic light in the past - examples see below
Note on T4: green: for information. yellow: critical, but only for infomation, team can handle. red: very critical, management support needed.
Note on T24: green: better or equal yellow: max. +3 Euro red: more than +3 Euro (compared to target)
Note on V4: here please state the trend of traffic light in the past - examples see below
Note on V24: here please state the trend of traffic light in the past - examples see below