## SG2 Cockpit
TTM
Cockpit SG2 | Product | update from date | All |  | Next Milestone | [5 empty] | DS / S4 | [5 empty] | Technical Risk Status
|  |  | Input Status | Status | MS |  | MS date | Input Status | Status | History |  |  | date | Input Status | Status | History | TOP Risks |  | Input Status | Status | History
| SG2 Platform Rel 1 | M. Weigang | yellow |  | S25 | Plan | 2005-06-24 | yellow |  |  | Plan | DS | 2005-09-15 | yellow |  |  | SW: 4 key components does reach C3 in B06/2005 |  | yellow
|  | 2005-03-07 |  |  |  | Current | 2005-06-24 |  |  |  | Current |  | 2005-09-15 |  |  |  | high amount of CRs, SW consultant POs were stopped in Jan
| X75 Minos | M. Feldfhoff | yellow |  | S25 | Plan | 2005-06-24 | yellow |  |  | Plan | DS | 2005-09-15 | yellow |  |  | mainly refer to platfomr rel1 SW situation |  | yellow
|  | 2005-03-07 |  |  |  | Current | 2005-06-24 |  |  |  | Current |  | 2005-09-15
| X75 Hydra | K.Soerensen | red |  | S25 | Plan | 2005-06-24 | yellow |  |  | Plan | DS | 2005-09-22 | yellow |  |  | mainly refer to platfomr rel1 SW situation |  | yellow
|  | 2005-03-07 |  |  |  | Current | 2005-06-24 |  |  |  | Current |  | 2005-09-22 |  |  |  | PI-engineering will be transfered
| SG2 Platform Rel 2 | M. Weigang | red |  | M0 | Plan | 2005-02-28 | red |  |  | Plan | DS | 2006-02-20 | yellow |  |  | Feature req. were settled late, no final agreement with PBM |  | yellow
|  | 2005-03-07 |  |  |  | Current | TBD |  |  |  | Current |  | TBD |  |  |  | critical situation in Rel1 leads to delay in Rel 2
| X85 Polaris | Th. Neumann | red |  | M0 | Plan | 2005-02-28 | red |  |  | Plan | DS | 2006-02-20 | yellow |  |  | refer to platform rel2, SW |  | yellow
|  | 2005-03-07 |  |  |  | Current | TBD |  |  |  | Current |  | TBD
| X85 Swift | J. Kockmann | red |  | M0 | Plan | 2005-03-30 | red |  |  | Plan | DS | 2006-03-31 | yellow |  |  | ATI decision, antenna decision -> stack up |  | red
|  | 2005-03-07 |  |  |  | Current | TBD |  |  |  | Current |  | TBD |  |  |  | refer to platform rel2, SW
| X85 Ibis | J. Kockmann | blank |  | M0 | Plan | 2005-04-29 | yellow |  |  | Plan | DS | 2006-05-31 | blank |  |  |  |  | blank
|  | 2005-03-07 |  |  |  | Current | 2005-04-29 |  |  |  | Current |  | TBD
| X85 Baya | N. Walkling | red |  | M0 | Plan | 2005-03-30 | red |  |  | Plan | DS | 2006-02-20 | yellow |  |  | missing design |  | yellow
|  | 2005-03-07 |  |  |  | Current | TBD |  |  |  | Current |  | TBD |  |  |  | refer to platform rel2, SW
| X85 Macaw | N. Walkling | blank |  | M0 | Plan | TBD | blank |  |  | Plan | DS | 2006-04-29 | blank |  |  |  |  | blank
|  | 2005-03-07 |  |  |  | Current | TBD |  |  |  | Current |  | TBD
|  |  | blank |  |  | Plan |  | blank |  |  | Plan |  |  | blank |  |  |  |  | blank
[6 empty] | Current |  |  |  |  | Current
| Product | update from date | Resource Situation | [7 empty] | Project-Budget | [5 empty] | BOM / HK (incl.Challenge)
|  |  | TOP Problems |  |  |  |  | Input Status | Status | History |  | Budget |  | Input Status | Status | History |  | BOM / HK (incl.Challenge) | Input Status | Status | History
| SG2 Platform Rel 1 | M. Weigang | consultant ordering need further monitoring |  |  |  |  | yellow |  |  | target |  |  | yellow |  |  | target M1 | NA | blank
|  | 2005-03-07 | Primavera planning will be consolidated | [7 empty] | Forecast Jan. 2005
| X75 Minos | M. Feldfhoff | product related res. stuffed |  |  |  |  | green |  |  | target |  |  | green |  |  | target M1 |  | green
|  | 2005-03-07 | [8 empty] | Forecast Jan. 2005
| X75 Hydra | K.Soerensen | Lumberg: critical financial situation |  |  |  |  | red |  |  | target |  |  | yellow |  |  | target M1 |  | green
|  | 2005-03-07 | PI engineering will be transfered | [7 empty] | Forecast Jan. 2005
| SG2 Platform Rel 2 | M. Weigang | critical SW situation in rel1 leads bottlenecks in Rel2 |  |  |  |  | red |  |  | target | budget planned |  | green |  |  | target M1 | NA | blank
|  | 2005-03-07 | -> SW PL, PV support, Architects, PLCs | [7 empty] | before M0 | account open
| X85 Polaris | Th. Neumann | product related res. stuffed |  |  |  |  | green |  |  | target | budget planned |  | green |  |  | target M-alpha | same BOM as Mbeta | yellow
|  | 2005-03-07 | [8 empty] | before M0 | account open | [5 empty] | ASP now reduced !!
| X85 Swift | J. Kockmann | product related res. stuffed |  |  |  |  | green |  |  | target | budget planned |  | green |  |  | target M-alpha | target is ways off | red
|  | 2005-03-07 | [8 empty] | before M0 | account open
| X85 Ibis | J. Kockmann | [5 empty] | blank |  |  | target | budget planned |  | green |  |  | target M-alpha |  | blank
|  | 2005-03-07 | [9 empty] | account open
| X85 Baya | N. Walkling | product related res. stuffed |  |  |  |  | green |  |  | target | budget planned |  | green |  |  | target M-alpha | target is ways off | red
|  | 2005-03-07 | [9 empty] | account open
| X85 Macaw | N. Walkling | [5 empty] | blank |  |  | target | budget planned |  | green |  |  | target M-alpha |  | blank
|  | 2005-03-07 | [9 empty] | account open
[8 empty] | blank |  |  | target |  |  | blank |  |  | target M-alpha |  | blank
Hidden infomation. |  | Legend: History | [8 empty] | Icons: |  | Hints on data entry:
ü
List for traffic light: |  | traffic light has improved compared to last status report | [10 empty] | 1 |  | Traffic lights are driven by input in column named "Input Status"
green | [12 empty] | 2 |  | Trend icons have to be copied from Legend (see left side)
yellow |  | no change of traffic compared to last status report | [10 empty] | 3 |  | Please hide columns D, I, O, T, Y, AD, AI by pressing button
red | [14 empty] | butten for level 1 in the very top left corner of this sheet
blank |  | traffic light worser compared to last status report
[13 empty] | x |  | Please see also comments behind cells
Table for use of history symbols:
|  | last |  | actual |  | Symbol
|  | green |  | green
|  | green |  | yellow or red
|  | yellow |  | yellow
|  | yellow |  | green
|  | yellow |  | red
|  | red |  | red
|  | red |  | yellow or green
Note on D4: green: all lights are green yellow: no red, but one or more yellow lights red: 1 or more red lights
Note on I4: green: max. +1 week yellow: max. +2 weeks red: more than +2 weeks
Note on I28: green: for information. yellow: critical, but only for infomation, team can handle. red: very critical, management support needed.
Note on K4: here please state the trend of traffic light in the past - examples see below
Note on K28: here please state the trend of traffic light in the past - examples see below
Note on L30: date last update
Note on L32: date last update
Note on L34: date last update
Note on M5: DS when next Milestone is before DS, S4 when next Milestone is DS or later.
Note on M7: DS when "Next Milestone" is before DS, S4 when "Next Milestone" is DS or later
Note on M9: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M11: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M13: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M15: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M17: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M19: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M21: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on M23: DS when next Milestone is before DS, S4 when next Milestone is DS or later
Note on O4: green: max. +1 week yellow: max. +2 weeks red: more than +2 weeks
Note on O28: green: less than +/- 3% deviation *) yellow: between +/- 3% and +6% deviation *) red: more than +/- 6% deviation *) *) shall cover both actual status and M3 prognosis
Note on Q4: here please state the trend of traffic light in the past - examples see below
Note on Q28: here please state the trend of traffic light in the past - examples see below
Note on R30: date last update
Note on T4: green: for information. yellow: critical, but only for infomation, team can handle. red: very critical, management support needed.
Note on T28: green: better or equal yellow: max. +3 Euro red: more than +3 Euro (compared to target)
Note on V4: here please state the trend of traffic light in the past - examples see below
Note on V28: here please state the trend of traffic light in the past - examples see below