## Slide 1: EGL products predevelopment
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
Timeline
I0 09.04.2004  I3 18.03.2005
I1 08.06.2004  I4 29.04.2005
I2 13.08.2004 
- I3 declaration is delayed due to several SW bugs found in Libra B6E B1+ devices
SW debugging with Libra B6E B1+ is ongoing.
Software platform
Hardware platform
EGOLDlite
All features of Libra were implemented except for AMR link adaptation.
AMR link adaptation implementation is ongoing on Comneon side.
S25 for Libra B6E int’l variant will be declared in cw11, 2005.
- For Libra, bugfixing is ongoing.
 X75 HW platform does not include HW which is explicitly used in EGOLDlite products. Such components (e.g. B/W display DORADO, slim 130 x 130 TFT display  FLAMINGO, …) are tracked in the related EGL product projects.
EGOLDlite baseband chipset qualification is almost done, including:
The TEAKlite DSP qualification is done and debugging is almost done.
GPRS qualification is ongoing and will be completed in cw14.
RRs of EGOLDlite in Libra and Dorado was signed
EGOLDlite is an cost optimized baseband processor and based on a shrinked EGOLD V3 and SGOLDlite DSP targeting low tier products.
The development of the EGOLDlite is carried out in a pre-development project which covers EGL HW, SW and FW. The purpose of the predevelopment is to verify and test EGL for the secure application in product products. Lead product projects are LIBRA/DORADO with M3 05/05.

## Slide 2: EGL products Libra (A75) – lead project of the EGL platform
Libra
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
Schedule/PV/Milestones:
M1 28.10.04 done S3 22.04.05 RU 09.05.05
S2 25.02.05 done Pilot 18.04.05 DS 20.05.05
M2 18.03.05 % PS 09.05.05 S4 03.06.05
S25 18.03.05 M3 30.06.05
Status next milestone:
S25 (18.03.): blocked by big power consumption and current existing SW bugs (ST & SW).
Major threats
big power consumption unclear if SW or HW, bugs such as 474E (S25 relevant for ST), etc.. SW and COMNEON are investigate in parallel.
HW
Device selection will started on March 15. TA planned for March 28.
The qualification of some DTC components (Wintek LCD 1USD, PCM lest battery (0.18 EUR), …) is ongoing.
SW
Last weeks blocker: AMR link adaptation will be implemented by COMNEON & SIEMENS! Ongoing,
Mechanics
Keypad (gap between function keys and housing bridge) need to be further improved in 3rd OT. Ongoing.
Prototyping:
B1+ run is done, B2 population and test will start on Mar. 22, 2005

## Slide 3: EGL products Dorado
Dorado
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
Schedule/PV/Milestones:
M0 07/14/04 √ S15 11/24/04 √ 11/25/04 S3 04/14/05 ->05/19/05
S0 07/30/04 √ S2 01/19/05 ->03/18/05 DS 05/19/05 ->06/16/05
M1 09/28/04 √ 10/25/04 S25 02/25/05 ->04/14/05 S4 05/26/05 ->06/30/05
Status next milestone:
S2 (03.18): blocked by power consumption (same as Libra)
Major threats
Big power consumption, critical bugs etc. (same as Libra)
SW booting problem must be solved before Approval Starts (Apr. 12)
HW
Base band, RF, LPD, EA: S2 status reached.
EMC problem (Self interference) found. Solution in Libra available. Has to be confirmed in Libra B2.
SW
Last weeks blocker: AMR link adaptation will be implemented by COMNEON & SIEMENS!
Mechanics
S2 status reached
Prototyping:
B1+ 1st run started on Mar. 10.

## Slide 4: EGL products Pegasus
Pegasus
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
Schedule/PV/Milestones:
M0 23.07.04  S15 15.11.04  S3 20.05.05
S0 17.08.04  S2 18.03.05 DS 17.06.05
M1 28.09.04  S25 31.03.05 S4 01.07.05
M3 22.07.05
Status next milestone:
S2 (18.03.): Blocked due to high power consumption (ST, SW, CCQ).
Major threats
big power consumption unclear if SW or HW. Some bugs such as 474E (S25 relevant for ST), etc.. SW and COMNEON are investigate in parallel.
Reference sensitivity endangers device selection and TA. HW & SW investigating. Most probably related to the SALZBURG ASIC.
EMC/Antenna
B1+ shows good improvement regarding spurious emission but still optimization necessary. New self interference found.
SW
Last weeks blocker: AMR link adaptation will be implemented by COMNEON & SIEMENS!
ST
High Power consumption ST S2 blocking point.
Ref. Sensitivity critical regarding start of TA.
Prototype run:
B1+ ongoing, IRDA testing is fully implemented in prototype run.

## Slide 5: EGL products Flamingo
Flamingo
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
Schedule/PV/Milestones:
M0 10.12.04 done S2 26.05.05 S4 24.10.05
S0 23.12.04 done S25 21.07.05 DS 24.10.05
M1 28.01.05 done S3 30.08.05 M3 25.11.05
Major threats
New components (display, Speaker box, …) critical regarding aggressive time line.
There is a problem with color separation on the slider part in BALDA, which is being under investigation and the solution needs to be found out by BALDA, MD, PM and the designer together ASAP.
Status next milestone:
S15 will be declared on March 17, no big issue at this moment.
HW
A1 prototype is under evaluation. No big issues have been found so far.
SW
B1 software development is under development and on the right track.
Mechanics
100% of MD data has bee sent to the supplier – Balda on 28/02/05 for soft tool and hard tool making. There is a problem with color separation on the slider part in Balda, which is being under investigation and the solution needs to be found out.
Prototyping:
A1 prototype shop is completed. B1 TO is 14/03/05.

## Slide 6: EGL products Flamingo Milestones Update
Flamingo
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
M1 milestones:
PD Team Official
schedule PSR
M0 12/10/04 S0 12/23/04
M1 01/21/05 S15 03/17/05 S2 05/26/05 S25 07/21/05
S3 08/30/05
PR 08/31/05 PS 09/21/05
DS 10/05/05 10/24/05 S4 10/19/05 11/07/05 M3 11/08/05 11/25/05

## Slide 7: EGL products Quail
Quail
Blue marked text is new, black is old, red will serve as indicator for the red traffic light
Schedule/PV/Milestones:
M0 28.02.05 declaration blocked due to new antenna concept ( March 18 expected)
S0 21.04.05 S3 19.12.05
M1 19.05.05 DS 24.01.06
S25 14.11.05 S4 24.01.06
According PV planning (M0-M1 detailed and M1 – M3 rough).
Major threats
New antenna concept (slim line, antenna in south) under development. Feasibility not finally proven in Quail. Actually looks quite promising. ( March 18).
Status next milestone:
M0 (18.03.): EA declaration blocked as antenna antenna concept is still under investigation. ( March 18)
HW
3 layers FPC will be executed and 2 layers FPC stand by
SW
Requested feature set exceeds available memory (RAM)->estimation show RAM will be enough after optimization, and other optimization will be performed to improve performance since long time for S0.
Mechanics
Mockups/SLA parts for antenna development available in EA.->2nd Mockup is available in EA
Prototyping:
A1 TO scheduled 06.05.05-> depending on EA input

## Slide 8
Backup
Blue marked text is new, black is old, red will serve as indicator for the red traffic light

## Slide 9: EGL products Pegasus & Dorado Sample Shop Schedule
Blue marked text is new, black is old, red will serve as indicator for the red traffic light