## Sheet1
Jerry effort estimation
Component / Task | First Effort Estimation (2006-01-16) | Effort estimation Beijing (2006-01-23) | Effort estimation PHE (2006-01-23) | Comments | Period from/to
C_apbas | 32 | 32 | 32 | UI flow, look&feel | start Feb. or March
C_apcnct | 4 | 4 | 1 | removing features | 1 month before S25
C_apidc | 50 | 150 | 50 | might be higher | start Feb. or March
C_apmm | 4 | 4 | 4 | removing features | 1 month before S25
C_apMMS | 16 | 16 | 16 |  | start Feb. or March
C_apmsg | 16 | 16 | 16 |  | start Feb. or March
C_appim | 25 | 25 | 25 |  | start Feb. or March
C_appImail | 0 | 0 | 0 |  | start Feb. or March
C_appIMPS | 0 | 0 | 0 |  | start Feb. or March
C_AppMenu | 2 | 2 | 2 | removing FlexMenu | start Feb. or March
C_ApPoC | 0 | 0 | 0 |  | start Feb. or March
C_apreui | 6 | 6 | 6 | 2 Man * 3 Month | start Feb. or March
C_Avatar | 0 | 0 | 0 |  | start Feb. or March
C_browser | 4 | 4 | 4 | remove browser | 1 month before S25
C_coapi | 4 | 4 | 4 |  | start Feb. or March
C_cojava | 4 | 4 | 4 | remove Java | start Feb. or March
C_couios | 8 | 8 | 8 |  | asap
C_DoJa | 0 | 0 | 0 |  | start Feb. or March
C_JavaApps | 0 | 0 | 0 |  | start Feb. or March
C_JavaAppsExtern | 0 | 0 | 0 |  | start Feb. or March
C_mobsim | 4 | 4 | 2 | add keys, adapt display size, feature set | asap (setup PCMMI)
C_mopi | 2 | 2 | 2 | support for developers
C_security | 1 | 1 | 1 | remove DRM feature
C_servims | 0 | 0 | 0
C_servPoC | 0 | 0 | 0
C_SipRtp | 0 | 0 | 0
Object Server | 2 | 2 | 2
Device Layer | 25 | 25 | 25 |  | PL complete time, 4-5 Dev until End April, 1 Dev complete time
CoreIntegrationTeam + IM | 36 | 36 | 36 | 20 (DL only) + 4*4 MMI | IM complete time, CIT from April
Customization | 2 | 2 | 2 | only one customer, no variants
DSP | 0 | 0 | 0 | no changes expected
PC-Tools | 2 | 2 | 2 | MPM not clarified
Protocol Stack | 4 | 4 | 4 | 1 TAM, support from IFX, 5-6 weeks for new features and bug fixing. | Complete time
CM | 10 | 10 | 10 | 1 person + 2 months consultant | Complete time
Smoke Test | 8 | 8 | 8 | 1 SM leader + interns | Complete time
BM | 20 | 20 | 20 | 2-3 BMs | Complete time
MMI Spec |  |  |  | Do we need internal MMI spec?
RM | 12 | 12 | 12 | 1 RM + 1 MMI clarifications | Complete time
ST
Component Test |  |  |  | assumption: only unit and system test
PL | 24 | 24 | 24 | 4 PLs (1 DL (see above), 2 MMI, 1 PL-SW) | Complete time
Architects | 16 | 16 | 16 | 1 DL (see above), 2 MMI | Complete time
Effort sum | 343 | 443 | 338