## Content
Table of contents | Jerry | 2026-07-28
Project Team | PD- and REA-Team Members
Project Profile | Device- And Feature-Description
Project Status | Reporting Template
MTA | Milestone-Trend-Analysis
PD-Team (Minutes of Meeting)
Participants And Informed Parties
Absence & Holidays
Important PD Decisions And Information
Important Feature Decisions
General Information / Issues
CPM (Category Product Management)
TPM (Technical Product Management)
Planning (Primavera)
| HW (Hardware) | RF | BB | EA | LPD
SW (Software)
MD (Mechanical Design)
ST SW (Software Systemtest)
ST MO (Modem and Approval)
TLM MD (Technology and Lifecycle Management Mobile Devices)
CCQ QM (Quality Management, PQA)
CCQ S (Service, Customer Care)
SP (Strategic Procurement)
AD (Accessory Devices)
Note on B29: now including NPI 2
Note on D24: Baseband = Digital Hardware
Note on E24: EMC / Antenna
Note on F24: Layout & Production Data former: - Electronic Design - Technische Koordination

## Project Team
Project Team Jerry |  |  |  | Status: 13.12.05
Names in italics are substitutes
Technical Projectmanager (TPM) |  |  |  |  | Category Prod. Manager (CPM)
Lars Bonde (AAL), Arjen Broeze (BEJ), XinJuan Song - Sara (BEJ) |  |  |  |  | Kheng-Wah Koh (Beijing)
R&D |  | SCM | QM | TPM BO | Marketing
HW | SW | LCM | QM HW | BO-PL
PL HW | SW DL/IM | LCM1 | Thomas Bartel
Poul Erik Rask | Allan Hansen (AAL) | Jens Riedel (KLF) | Poul Søndergaard | N.N. | N.N.
N.N.
|  |  | QM SW | VM
PPL RF |  | LCM3
Michael Brammer (AAL) |  | Katharina Hilker (KLF) | ?? | ??
N.N. |  | N.N. | N.N. | N.N. | N.N.
PPL BB |  | QM PRO | NPI (Service) | Manual / Packaging
Flemming Bach Kristensen (AAL)
N.N. |  |  | Henning Boll (AAL) | ??
| ST | N.N. | N.N. | N.N. | N.N.
PPL EA
Arne Bisgaard Kristensen (AAL) | ST SW |  |  | GPM
N.N. | Handled by BEJ | TPM BA | Planning |  | Sales
PPL LPD |  | Jie gao (Bej) | Bjarne Lund Thomsen (AAL) | N.N.
Randi Bak (AAL) | ST MO | N.N. | N.N. |  | N.N.
Erik Juul Petersen | Flemming Kokholm (AAL)
MD |  | Procurement | Accessories | AS | CM BA
Christian Primdahl Nielsen |  | Svendsen, Mariann (AAL) |  | ??
|  | N.N. |  | ?? | N.N.

## Part.&Inf.
BACK
PD-Meeting Hawk |  |  |  | Meeting-Organization | today | next time
|  |  |  | date: | 2006-02-03
minutes / moderation by: | Lars Bonde |  |  | time: | 13:00 - 14:30
|  |  |  | room Aal: | 2.1.13 | 6.2.09
|  |  |  | phone Aal: | +45 7219 xxxx | +45 7219 xxxx
|  |  |  | Dial-In Germany: | +49 (0) 69 - 40359803 | +49 (0) 69 - 40359803
[5 empty] | Code : 45438 # | Code : 45438 #
Team members
name | department | location |  | absence | representative
Allan Hansen | BenQ MD PD SWP 1 PM AAL | AAL
Arne Bisgaard Kristensen | BenQ MD PD HW 1 AAL 1 | AAL | AAL
Bjarne Lund Thomsen | BenQ MD PD OS AAL | AAL | AAL
Christian Primdahl Nielsen | BenQ MD PD MD AAL | AAL | AAL
Dorte Nielsen | BenQ MD PD HW4 AAL | AAL
Hans Henrik Skovgaard | BenQ MD PD SWP 1 PM AAL | AAL | AAL
Henning Boll | BenQ MD CC GRM R | AAL | AAL
Jens Riedel | BenQ MD SCM TLM LCM 1 | KLF
Katharina Hilker | BenQ MD SCM TLM LCM 4 | KLF
Lars Bonde | BenQ MD PBM PPM PM | AAL | AAL
Mariann Svendsen | BenQ SP D PE MD | AAL | AAL
Michael Brammer | BenQ MD PD HW 1 AAL 2 | AAL
Poul Erik Rask | ICM MP PBM PPM PM AAL | AAL | AAL
Randi Bak | BenQ MD PD HW4 AAL | AAL | AAL
|  | participants in total: | 9
|  | Aal: | 9
|  | KLf: | 0
|  | MchG: | 0
|  | UlmL: | 0
Note on E9: dila in code: 36383#

## Abs.-Holiday
BACK
PD-Meeting JERRY
Absence & Holiday List
|  |  |  | CW1 | CW2 | CW3 | CW4 | CW5 | CW6 | CW7 | CW8 | CW9 | CW10 | CW11 | CW12 | CW13 | CW14 | CW15 | CW16 | CW17 | CW18 | CW19 | CW20 | CW21 | CW22 | CW23 | CW24 | CW25 | CW26
Name | Department | Location | Substitute | 2006-01-02 | 2006-01-09 | 2006-01-16 | 2006-01-23 | 2006-01-30 | 2006-02-06 | 2006-02-13 | 2006-02-20 | 2006-02-27 | 2006-03-06 | 2006-03-13 | 2006-03-20 | 2006-03-27 | 2006-04-03 | 2006-04-10 | 2006-04-17 | 2006-04-24 | 2006-05-01 | 2006-05-08 | 2006-05-15 | 2006-05-22 | 2006-05-29 | 2006-06-05 | 2006-06-12 | 2006-06-19 | 2006-06-26
Allan Hansen | BenQ MD PD SWP 1 PM AAL | AAL |  | 2006-02-20: 20.21
Allan Steensgaard Jensen | BenQ MD PD ST1 AAL | AAL
Arne Bisgaard Kristensen | BenQ MD PD HW 1 AAL 1 | AAL
Bjarne Lund Thomsen | BenQ MD PD OS AAL | AAL |  | 2006-03-13: Holiday
Dorte Nielsen | BenQ MD PD HW4 AAL | AAL
Erik Kirstejn Jensen | BenQ MD PD MD AAL | AAL
Flemming Kokholm | BenQ MD PD ST 2 AAL | AAL |  | 2006-02-13: 15,16,17; 2006-02-27: 27.28
Hans Henrik Skovgaard | BenQ MD PD SWP 1 PM AAL | AAL |  | 2006-02-20: Holiday
Henning Boll | BenQ MD CC GRM R | AAL |  | 2006-02-20: Holiday
Jens Riedel | BenQ MD SCM TLM LCM 1 | KLF | Katharina | 2006-02-06: Holiday; 2006-02-13: Holiday; 2006-02-20: Holiday
Katharina Hilker | BenQ MD SCM TLM LCM 4 | KLF
Lars Bonde | BenQ MD PBM PPM PM | AAL |  | 2006-01-30: 30,31,1,2; 2006-03-20: Holiday
Mariann Svendsen | BenQ SP D PE MD | AAL
Michael Brammer | BenQ MD PD HW 1 AAL 2 | AAL
Poul Erik Rask | ICM MP PBM PPM PM AAL | AAL |  | 2006-04-10: Holiday; 2006-04-17: Holiday; 2006-04-24: Holiday
Randi Bak | BenQ MD PD HW4 AAL | AAL

## Project Status
BACK
Project Status Report Jerry |  |  | as of ? | Assessment
|  |  |  | there is a problem | L | x
|  |  |  | might become a problem | K
|  |  |  | no problem | J
| TPM: | Betting Andreas Com MD PD PGG
A. | Project Data
| Project Cost | K
| Schedule | K
| Risk | K
B. | Highlights / activities during reporting period
C. | Main project targets within the next 4 weeks
D. | Problems
| Problems / Risks | Actions | Responsible | Date | Status
E. | Milestone status according to MEP?.?? of ??.??.???? |  |  |  | MEP 6.01
| department | PPL | M0/S0 Target for PD-Team 16.12.2005 | comments
RF
EA
BB
SW
MD
LPD
SP
LCM4
PT1
PT4
SDQM
QM-HW
QM-SW
ST MO
ST SW
AD
Service
Planning
F. | Change Requests against Jerry (platform CRs will not be traced here)
| CR-Nr. | CR Short Description | Status
| 8627 | ME75 customized SW for Vodafone | cw48 summary: VF-SW has been first generated with R7, due to Java-Exit R7* is planned for VF-approval | Closed
| 8731 | ME75 create I_Mode variant - hardware |  | CANCELED
| 8732 | ME75 SWC create I_Mode variant - software |  | CANCELED
Draft

## General
BACK | General Information / Issues
date | issue | who | when
Project Account E???-0??? = Jerry
Milestones Jerry ( basis Draft V?,?)
M0 Milestone
S0 Milestone
M1 Milestone
S15 Milestone
S2 Milestone / S25-SW Milestone
TA-Milestone (Type Approval Start)
S25 Milestone / S3 SW-Milestone
S3 Milestone (Pilot Start)
DS Milestone (Delivery Start) (5k)
S4 SW Milestone (ST/SW, QM-SW)
S4 Milestone
M3 Milestone (tbc)
Product Info:
| Color Versions: ??? | Info
Ramp up: Start Pilot ? Color: ?
Project Drive
Link
Prototype Planning & Delivery
?
Time Scheudle
?
PM documentation (all PM info on IMS)
?
SW PD minutes & activities / SW Release Plan
?
MEP V.6.01
?
Risk Assessment
?
FMEA reviews
?
Service Requirements
?
HW Defect Tracking List
| ? | weekly update
Primavera - Homepage
?
Draft

## MTA
BACK
Draft

## MTA Data
| Reference Line | M3 - 01.12.06 | S4 - 01.11.06 | EDS - 15.09.06 | EPS - 01.09.06 | S3 - 14.08.06 | M2 - 22.06.06 | S25 - 22.06.06 | S2 - 17.05.06 | S15 - 18.04.06 | M1 - 14.03.06 | S0 - 28.02.06 | M0 - 03.02.06
2006-01-20 | 2006-01-20 | 2006-12-01 | 2006-11-01 | 2006-09-15 | 2006-09-01 | 2006-08-14 | 2206-06-22 | 2006-06-22 | 2006-05-17 | 2006-04-18 | 2006-03-14 | 2006-02-28 | 2006-02-03
2006-02-01
2006-03-01
2006-04-01
2006-05-01
2006-06-01
2006-07-01
2006-08-01
2006-09-01
2006-10-01
2006-11-01
2006-12-01
2006-12-28
2007-01-27
2007-02-26
2007-03-28
2007-04-27
2007-05-27
2007-06-26

## History-Decisions
BACK | History of important feature decisions
date | issue | decided by
2006-01-13 | Management decision: - Jerry is a PHA project - Change of platform: SGL native instead of EGR w. Apoxi - BEJ must fully control the SW development, outsourced to SISL and PSE Nanjing, DL/CM/IM support from AAL - HW and MD must be driven by AAL until May/June timeframe
2006-01-19 | Working decision to go for the Aries display | Kheng-Wah Koh

## CPM
CPM (Category Product Manager)
| Owner: | Kheng-Wah Koh |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 2006-01-20 | open | LCD display | Working decision is to use the Aries display. Reasons: - Big risk on timeline of Amber display - SW can immediately start development based on the Aries wingboards - SW should be able to save time compared to Amber display - Mail from Dirk Didascalou mentions that the display is supported on SGL platform | Kheng-Wah
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## MD
MD (Mechanical Design)
| Owner: | Christian Primdahl Nielsen |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 2006-10-20 | Info | LCD display | Aries 3D data sent to designer Pearl Chen | Erik
| 20-01-2006 03-02-2006 | Open | ID impact of Aries display | Pearl is currently working on the design. Feedback from this morning is: - Phone is expected to grow 1.6 mm in thickness in the display area - Phone is expected to grow 1.5 mm in length - 1st shot of data will be sent to Erik Friday afternoon - Renderings for VF will be available on Tuesday 24-01-06 Stack-up available. Length of antenna is currently a challenge. A change to B6E could be required in order to lower the sidekeys and increase the antena length. | Erik Pearl
| 2006-01-20 | Info | Mech. Development | It has been decided to shift from Pochtler to Perlos for the 3D work. Perlos also has a set-up in BEJ wich makes it easier to transfer the project during spring/summer, plus Pochtler has already worked on Hawk that is alive again. | Erik
| 20-01-2006 26-01-2006 03-02-2006 | Open | Key-lock switch | Implementation of sliding switch must be investigated for space and implementation issues: - Switch or hall sensor? - Size of either solution - Can the switch be moved to the other side of the phone? Hall sensor is most feasible for both parties. Two type are available. Decision not yet made It looks as if there is room for the Hall effect sensor solution | Erik | Flemming B. | 2006-02-10
| 2006-01-26 | closed | SP65 data | Should arrive today. Based on these data we will put in Aries display, Side switches and Hall sensor, as base for ID rework. | Christian |  | 2006-01-30
| 2006-02-03 | Open | Use of 600mAh battery | We have been asked if we can use the 600 mAh battery in order to decrease the phone thichness. Standby and talktime will be reduced by 26% | Christian | Flemming B. | 2006-02-08
| 2006-02-03 | Info | Meeting with industrial designer | Pearl Chen and Markus Borchert will be in Aalborg from 7-9 of Feb. | Christian
| 2006-02-03 | Info | Meeting with Perlos | 3 design engineers from Perlos will be in Aalborg from 6-9 of Feb. | Christian
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## BB
BB (Baseband)
| Owner: | Flemming Bach Kristensen |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 2006-01-26 | Open | Removal of components from SP 65 | Removal has been started, and addition of new connector and switches. Schematic update on-going. Waiting for board outlne for routing | Flemming
| 2006-01-26 | open | Backlight concept | Investigations on-going. Waiting for answer from Thomas Bartl regarding use case for LED that must be white and also blink Green. Working assumption is 8 white and 1 green LED | Flemming
| 26-01-2006 03-02-2006 | closed | Power management | Investigating if changing from the Mozart+ to the Mozart Boost+. SW effort could stop this. We will stay with Mozart+ | Flemming
| 2006-02-03 | Info | Vibra | We will change to the Hera vibra and move it to the top of the phone | Flemming
| 2006-02-03 | Open | USB cable suuport | If the components needed are removable, we will implement USB support initially on the B1 PCB | Flemming
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## LPD
LPD (Layout & Production Data)
| Owner: | Randi Bak |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 2006-01-26 | open | Board outline | Waiting for this from MD | Christian
| 2006-01-26 | open | Tape out date | Exact date is needed -> Currently 15-02-2006 | Flemming Michael Arne
| 26-01-2006 03-02-2006 | closed | Supplier | AT&S? We start with AT&S | Mariann
| 2006-02-03 | open | Slim Lumberg | Still waiting for a final solution, pending accessories confirmation of availability | Poul Erik
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## EA
EMC / Antenna
| Owner: | Arne Bisgaard Kristensen |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 20-01-006 03-02-2006 | Open | Investgation of antenna space | On-going based on similar shaped phones to be prapared for the stack-up Currently considering 2 different solutions depending on components and ID Currently preferred solution is a Cadilac antenna | Arne
| 2006-01-26 | Open | Stack-up | Waiting for a defined stack-up in order to do further investigations | Arne
| 2006-01-26 | Open | VF antenna requirements | Thinner phone might degrade the antenna performance. This might need to be discussed with VF | Arne | Christian Lars
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## RF
RF
| Owner: | Michael Brammer |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 20-01-2006 03-02-2006 | closed | Bright 5E or 6E | Open issue which chip-set to use Check if B5E is going out of production Change from B5E to B6E will take 2-3 days BOM is similar, so no advantage there We will most likely have to change to B6E for size reasons, in order to be able to move the sidekeys further south and increase the antenna length to fulfill VF antenna requirements | Michael |  | 2006-01-25
| 26-01-2006 03-02-2006 | closed | Smarti SD | From SW side there should be no problem shifting to the Smarti SD. Problem could be size if we have to reduce the width of the SP65 PCB, then B6E would be a better option. Smarti SD is supported in SW | Michael
| 2006-02-03 | Open | Bright 6E or Smarti SD | Based on stack-up it must be decided if we use B6E or Smarti SD. B6E is only half the size, but Smarti SD is EUR 1.2 cheaper. Problem is room for sidekeys if we use Smarti SD. | Michael |  | 2006-02-08
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## PE
Procurement Engineering
| Owner: | Mariann Svendsen |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 26-01-2006 03-02-2006 | closed | BOM calculation | Calculation on-going. - Feedback on keypad is that apart from Polaris, this is the most expensive First calculation made based on own parts list. | Mariann |  | 2006-01-26
| 2006-01-26 | open | Parts list | Needed ASAP | Randi | Dorte
| 2006-01-26 | info | Supplier | Plastic part supplier is implicitly choosen already | Mariann | Christian
| 2006-02-03 | open | Key component list |  | Mariann |  | 2006-02-08
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## SW
Software
| Owner: | Hans Henrik Skovgaard |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 20-01-2006 03-02-2006 | closed | B5E or B6E RF or Smarti SD | Clarify impact on SW of changing the RF No problems, support exist for all 3 | Hans Henrik Allan |  | 2006-02-01
| 2006-01-20 | info | Sync-up | Daily telco's with BEJ SW PL Main task is to secure DL support for BEJ | Hans Henrik
| 2006-01-20 | Open | Timeline investigations | Feling is that it will be more than difficult tomeet the timeline 1st guess on top level planning in CW6 Task has shifted to BEJ. BEJ estimate is end of Feb. For planning of SW | Hans Henrik
| 2006-01-26 | info | DL resources | Has been appointed and BEJ notified of names | Hans Henrik Allan
| 2006-01-26 | info | CIT Resources | Has been appointed and BEJ notified of names | Hans Henrik Allan
| 26-01-2006 03-02-2006 | closed | Requirement responsibilities | Responisibilities/Work-flow is un-clear. Who has contact to e.g. VF Who are setting the high level requirements Who are setting requirements to component team -> 1st draft of feature list available 27.01.2006 | Allan
| 2006-01-26 | open | Communication flow | Setting up contacts for: - BEJ - SISL - PSE | Allan
| 2006-01-26 | info | Aries SW | Aries SW currently being transfered to AAL and databases being set-up. Ready for AAL to start working on SW mid CW5. | Allan
| 26-01-2006 03-02-2006 | closed | Aries wing boards | So far we have not managed to find wing boards anywhere -> Henning Boll might be able to find some | Hans Henrik | Henning
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## ST SW
System Test SW
| Owner: | Allan Steensgaard Jensen |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 2006-01-20 | Open | ST support for BEJ | Based on mail from BEJ we do not expect to have anything to do on Jerry. BEJ have both ST1 and ST2 resources available | Allan
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## ST MO
System Test Modem & Approval
| Owner: | Flemming Kokholm |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 2006-01-20 | Open | ST support for BEJ | Based on mail from BEJ we do not expect to have anything to do on Jerry. BEJ have both ST1 and ST2 resources available
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## AS
Applications & Services
| Owner: | NN |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## LCM 3
LCM 3
| Owner: | Katharina Hilker |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 2006-01-20 | closed | Prototype series | Dates will be sync'ed up during next week. Dates can be found in Jerry Primavera plan
| 2006-01-26 | open | Waiting for stack-up concept | Needed for Production Technology people to start working | Katharina
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## LCM 1
LCM 1
| Owner: | Jens Riedel |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## QM PRO
QM PRO (Material Availability)
| Owner: | NN |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## QM HW
QM HW
| Owner: | Thomas Bartel / Poul Søndergaard |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 2006-02-03 | Open | Stack-up solution | Be aware that there might be problems with a single PCB solution, with the BGA's breaking off due to pushing the keypad
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## NPI
Service
| Owner: | Henning Boll |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 26-01-2006 03-02-2006 | closed | GRR document | Template wil be put on the project drive for update Pre-requisite for M0 and M1 | Henning
| 26-01-2006 03-02-2006 | closed | Sample plan | For both Rea and PD team is needed a sample plan | Lars
| 2006-02-03 | info | BEJ NPI support | Andreas Springer
| 2006-02-03 | info | Fixtures | We do not expect to be able to reuse the Penelopy fixtures. Will call a meeting to see what is possible | Henning |  | 2006-02-08
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## AD
Accessory Devices
| Owner: | NN |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## Planning
Planning (Primavera)
| Owner: | Bjarne Lund Thomsen |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 2006-01-26 | open | Detailed planning | People need to start this | Bjarne | PPL's
| 2006-01-26 | open | Mechanical planning | Shift in PL MD will result in different MD startegy and MD timeline | Bjarne | Christian Lars | 2006-02-08
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## TPM
TPM (Technical Product Manager)
| Owner: | Lars Bonde (Telephone +45 7219 5112 ; Mobile +45 2045 6872) |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 2006-01-20 | Info | Workshop in BEJ | The team will call for a WS in Beijing in CW06 in order to allign the AAL and BEJ teams. Agenda and who should attend are still pending | Arjen Broeze Lars
| 2006-01-20 | Info | Project timing | 1st draft of schedule available in Primavera. NOTE: Planning is only based on HW and MD, SW plan still missing | Lars
| 26-01-2006 03-02-2006 | closed | Aries phones | 10 Samples are needed to be modified as "Jerry" targets | Lars
| 2006-01-26 | open | Sample plan | Supply a sample plan to LPD before tape-out of B1 PCB | Lars |  | 2006-02-10
| 2006-01-26 | Info | Industrial design | Current ID with the Aries display has been rejected by VF as being to thick for a 2G entry phone. This puts the timeline under pressure for HW amd Mech development as as design fix is pending and we do not have a PCB board outline available. | Lars
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## Template
Function
| Owner: | NN |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"