## Content
Table of contents | Jerry | 2026-07-28
Project Team | PD- and REA-Team Members
Project Profile | Device- And Feature-Description
Project Status | Reporting Template
MTA | Milestone-Trend-Analysis
PD-Team (Minutes of Meeting)
Participants And Informed Parties
Absence & Holidays
Important PD Decisions And Information
Important Feature Decisions
General Information / Issues
CPM (Category Product Management)
TPM (Technical Product Management)
Planning (Primavera)
HW (Hardware)
SW (Software)
MD (Mechanical Design)
ST MO (Modem and Approval)
QM HW
NPI (New Product Introduction)
PE (Procurement Engineering)

## Project Team
Project Team Jerry |  |  |  | Status: 13.12.05
Names in italics are substitutes
Technical Projectmanager (TPM) |  |  |  |  | Category Prod. Manager (CPM)
Lars Bonde (AAL), Arjen Broeze (BEJ), XinJuan Song - Sara (BEJ) |  |  |  |  | Kheng-Wah Koh (Beijing)
R&D |  | SCM | QM | TPM BO | Marketing
HW | SW | LCM | QM HW | BO-PL
PL HW | SW DL/IM | LCM1 | Thomas Bartel
Poul Erik Rask | Allan Hansen (AAL) | Jens Riedel (KLF) | Poul Søndergaard | N.N. | N.N.
N.N.
|  |  | QM SW | VM
PPL RF |  | LCM3
Michael Brammer (AAL) |  | Katharina Hilker (KLF) | ?? | ??
N.N. |  | N.N. | N.N. | N.N. | N.N.
PPL BB |  | QM PRO | NPI (Service) | Manual / Packaging
Flemming Bach Kristensen (AAL)
N.N. |  |  | Henning Boll (AAL) | ??
| ST | N.N. | N.N. | N.N. | N.N.
PPL EA
Arne Bisgaard Kristensen (AAL) | ST SW |  |  | GPM
N.N. | Handled by BEJ | TPM BA | Planning |  | Sales
PPL LPD |  | Jie gao (Bej) | Bjarne Lund Thomsen (AAL) | N.N.
Randi Bak (AAL) | ST MO | N.N. | N.N. |  | N.N.
Dorte Nielsen | Flemming Kokholm (AAL)
MD |  | Procurement | Accessories | AS | CM BA
Christian Primdahl Nielsen |  | Svendsen, Mariann (AAL) | Thorsten Lange (MCH) | ??
|  | N.N. |  | ?? | N.N.

## Part.&Inf.
BACK
PD-Meeting Hawk |  |  |  | Meeting-Organization | today | next time
|  |  |  | date: | 2006-02-20 | 2006-02-27
minutes / moderation by: | Lars Bonde |  |  | time: | 08:30 - 10:00 | 08:30 - 10:00
|  |  |  | room Aal: | 2.1.13 | 2.1.13
|  |  |  | phone Aal: | +45 7219 xxxx | +45 7219 xxxx
|  |  |  | Dial-In Germany: | +49 (0) 69 - 40359803 | +49 (0) 69 - 40359803
[5 empty] | Code : 45438 # | Code : 45438 #
Team members
name | department | location |  | absence | representative
Allan Hansen | BenQ MD PD SWP 1 PM AAL | AAL
Arjen Broeze | BenQ BMB | BEJ | BEJ
Bjarne Lund Thomsen | BenQ MD PD OS AAL | AAL | AAL
Christian Primdahl Nielsen | BenQ MD PD MD AAL | AAL
Flemming Kokholm | BenQ MD PD ST 2 AAL | AAL | AAL
Henning Boll | BenQ MD CC GRM R | AAL
HuiWen Jiang | BenQ ST WHC | BEJ | BEJ
JianHong Li | BenQ MD | BEJ
Katharina Hilker | BenQ MD SCM TLM LCM 4 | KLF | KLF
Lars Bonde | BenQ MD PBM PPM PM | AAL | AAL
Li Yang | BenQ ST SW | BEJ | BEJ
Mariann Svendsen | BenQ SP D PE MD | AAL | AAL
Poul Erik Rask | BenQ MP PBM PPM PM AAL | AAL | AAL
Stefan Burkert | BenQ SW MC | BEJ
Thomas Bartel | BenQ BMG QM PL PPM | BEJ | BEJ
Thorsten Lange | BenQ BMG PHE RD VAS | MchG
XinJuan Song (Sara) | BenQ BMB | BEJ | BEJ
XueKai Wei | BenQ ST WHC | BEJ | BEJ
|  | participants in total: | 12
|  | Aal: | 5
|  | KLf: | 1
|  | MchG: | 0
|  | BEJ: | 6
Note on E9: dila in code: 36383#

## Abs.-Holiday
BACK
PD-Meeting JERRY
Absence & Holiday List
|  |  |  | CW1 | CW2 | CW3 | CW4 | CW5 | CW6 | CW7 | CW8 | CW9 | CW10 | CW11 | CW12 | CW13 | CW14 | CW15 | CW16 | CW17 | CW18 | CW19 | CW20 | CW21 | CW22 | CW23 | CW24 | CW25 | CW26
Name | Department | Location | Substitute | 2006-01-02 | 2006-01-09 | 2006-01-16 | 2006-01-23 | 2006-01-30 | 2006-02-06 | 2006-02-13 | 2006-02-20 | 2006-02-27 | 2006-03-06 | 2006-03-13 | 2006-03-20 | 2006-03-27 | 2006-04-03 | 2006-04-10 | 2006-04-17 | 2006-04-24 | 2006-05-01 | 2006-05-08 | 2006-05-15 | 2006-05-22 | 2006-05-29 | 2006-06-05 | 2006-06-12 | 2006-06-19 | 2006-06-26
Allan Hansen | BenQ MD PD SWP 1 PM AAL | AAL |  | 2006-02-13: BEJ; 2006-02-20: 20.21; 2006-03-13: BEJ?; 2006-03-20: BEJ?; 2006-03-27: BEJ?; 2006-04-03: BEJ?; 2006-04-10: BEJ?
Arjen Broeze | BenQ BMB | BEJ
Bjarne Lund Thomsen | BenQ MD PD OS AAL | AAL |  | 2006-03-13: Holiday
Christian Primdahl Nielsen | BenQ MD PD MD AAL | AAL |  | 2006-02-13: BEJ
Flemming Kokholm | BenQ MD PD ST 2 AAL | AAL |  | 2006-02-13: BEJ; 2006-02-27: 27.28
Henning Boll | BenQ MD CC GRM R | AAL |  | 2006-02-20: Holiday
HuiWen Jiang | BenQ ST WHC | BEJ
JianHong Li | BenQ MD | BEJ
Katharina Hilker | BenQ MD SCM TLM LCM 4 | KLF
Lars Bonde | BenQ MD PBM PPM PM | AAL |  | 2006-01-30: 30,31,1,2; 2006-02-13: BEJ; 2006-03-20: Holiday
Li Yang | BenQ ST SW | BEJ
Mariann Svendsen | BenQ SP D PE MD | AAL |  | 2006-02-13: BEJ
Poul Erik Rask | ICM MP PBM PPM PM AAL | AAL |  | 2006-02-13: BEJ; 2006-04-10: Holiday; 2006-04-17: Holiday; 2006-04-24: Holiday
Stefan Burkert | BenQ SW MC | BEJ
Thomas Bartel | BenQ BMG QM PL PPM | BEJ
Thorsten Lange | BenQ BMG PHE RD VAS | MchG
XinJuan Song (Sara) | BenQ BMB | BEJ
XueKai Wei | BenQ ST WHC | BEJ

## Project Status
BACK
Project Status Report Jerry |  |  | as of ? | Assessment
|  |  |  | there is a problem | L | x
|  |  |  | might become a problem | K
|  |  |  | no problem | J
| TPM: | Betting Andreas Com MD PD PGG
A. | Project Data
| Project Cost | K
| Schedule | K
| Risk | K
B. | Highlights / activities during reporting period
C. | Main project targets within the next 4 weeks
D. | Problems
| Problems / Risks | Actions | Responsible | Date | Status
E. | Milestone status according to MEP?.?? of ??.??.???? |  |  |  | MEP 6.01
| department | PPL | M0/S0 Target for PD-Team 16.12.2005 | comments
RF
EA
BB
SW
MD
LPD
SP
LCM4
PT1
PT4
SDQM
QM-HW
QM-SW
ST MO
ST SW
AD
Service
Planning
F. | Change Requests against Jerry (platform CRs will not be traced here)
| CR-Nr. | CR Short Description | Status
| 8627 | ME75 customized SW for Vodafone | cw48 summary: VF-SW has been first generated with R7, due to Java-Exit R7* is planned for VF-approval | Closed
| 8731 | ME75 create I_Mode variant - hardware |  | CANCELED
| 8732 | ME75 SWC create I_Mode variant - software |  | CANCELED
Draft

## General
BACK | General Information / Issues
date | issue | who | when
Project Account E???-0??? = Jerry
Milestones Jerry ( basis Draft V?,?)
M0 Milestone
S0 Milestone
M1 Milestone
S15 Milestone
S2 Milestone / S25-SW Milestone
TA-Milestone (Type Approval Start)
S25 Milestone / S3 SW-Milestone
S3 Milestone (Pilot Start)
DS Milestone (Delivery Start) (5k)
S4 SW Milestone (ST/SW, QM-SW)
S4 Milestone
M3 Milestone (tbc)
Product Info:
| Color Versions: ??? | Info
Ramp up: Start Pilot ? Color: ?
Project Drive
Link
Prototype Planning & Delivery
?
Time Scheudle
?
PM documentation (all PM info on IMS)
?
SW PD minutes & activities / SW Release Plan
?
MEP V.6.01
?
Risk Assessment
?
FMEA reviews
?
Service Requirements
?
HW Defect Tracking List
| ? | weekly update
Primavera - Homepage
?
Draft

## MTA
BACK

## MTA Data
| Reference Line | M3 - 01.12.06 | S4 - 01.11.06 | EDS - 22.09.06 | EPS - 08.09.06 | S3 - 17.08.06 | M2 - 22.06.06 | S25 - 18.07.06 | S2 - 18.07.06 | S15 - 25.04.06 | M1 - 21.03.06 | S0 - 28.02.06 | M0 - 23.02.06
2006-01-20 | 2006-01-20 | 2006-12-01 | 2006-11-01 | 2006-09-15 | 2006-09-01 | 2006-08-14 | 2006-06-22 | 2006-06-22 | 2006-05-17 | 2006-04-18 | 2006-03-14 | 2006-02-28 | 2006-02-03
2006-02-20 | 2006-02-20 | 2006-12-01 | 2006-11-01 | 2006-09-22 | 2006-09-08 | 2006-08-17 | 2006-06-22 | 2006-07-18 | 2006-07-18 | 2006-04-25 | 2006-03-21 | 2006-02-28 | 2006-02-23
2006-03-01
2006-04-01
2006-05-01
2006-06-01
2006-07-01
2006-08-01
2006-09-01
2006-10-01
2006-11-01
2006-12-01
2006-12-28
2007-01-27
2007-02-26
2007-03-28
2007-04-27
2007-05-27
2007-06-26

## History-Decisions
BACK | History of important feature decisions
date | issue | decided by
2006-01-13 | Management decision: - Jerry is a PHA project - Change of platform: SGL native instead of EGR w. Apoxi - BEJ must fully control the SW development, outsourced to SISL and PSE Nanjing, DL/CM/IM support from AAL - HW and MD must be driven by AAL until May/June timeframe
2006-01-19 | Working decision to go for the Aries display | Kheng-Wah Koh
2006-02-03 | With the introduction of Poul Erik Rask as PL-HW, it has been decided to let the PL-HW handle all HW related issues towards the PD team meeting, including prototype series. This means that the PD team meetings in the future will consists of: - HW, MD, NPI, PE, SW, ST MO and Planning The HW meetings will include: - dHW, RF, EA, LPD, LCM1, LCM3 with MD as optional The reason is to have more efficient meetings with the PD team meeting focusing on overview and the HW meeting more on detail. After the WS in BEJ in CW7 it is expected that some of our Chinese colleagues will join the PD team meeting via Telco. | Lars Bonde
2006-02-20 | During the WS in BEJ in CW07, it was decided that the S2 and S25 milestones will be declared at the same time due to the missing B1+ run. (We only have B1 and B2). The SW milestones will be detached from the standard "Siemens" milestone system, as we will use Agile development and that the S25 milestone therefore doesn't fit. Will will instead implement 5 Sprints where prioritized features are implemented, and step-wise released for demo to VF. | Arjen Broeze, XinJuan Song, Thomas Bartel, Lars Bonde
2006-02-20 | VF has formally accepted our industrial design (mail from Christopher Frost of the VF-Group). Minor modifications are still expeced. | Vodafone

## CPM
CPM (Category Product Manager)
| Owner: | Kheng-Wah Koh |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 2006-01-20 | open | LCD display | Working decision is to use the Aries display. Reasons: - Big risk on timeline of Amber display - SW can immediately start development based on the Aries wingboards - SW should be able to save time compared to Amber display - Mail from Dirk Didascalou mentions that the display is supported on SGL platform | Kheng-Wah
|  | info | Slim Lumberg connector | In order to reduce the cost of the desktop stand and reduce the SW effort, it has been decided to go fro the Slim Lumberg connector instead of the Nano-IO. Only blocking point could be availbility of accessories portfolio. No blocking points from management.
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## MD
MD (Mechanical Design)
| Owner: | Christian Primdahl Nielsen |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 2006-10-20 | Info | LCD display | Aries 3D data sent to designer Pearl Chen | Erik
| 20-01-2006 03-02-2006 20-02-2006 | closed | ID impact of Aries display | Pearl is currently working on the design. Feedback from this morning is: - Phone is expected to grow 1.6 mm in thickness in the display area - Phone is expected to grow 1.5 mm in length - 1st shot of data will be sent to Erik Friday afternoon - Renderings for VF will be available on Tuesday 24-01-06 Stack-up available. Length of antenna is currently a challenge. A change to B6E could be required in order to lower the sidekeys and increase the antena length. B6E has been choosen. BB chamber has been moved all the way south to the Slim Lumber connector, and any components between the connector and chamber will be moved inside the chamber. Battery connector and battery will move totally 2 mm south. VF has accepted ID with these changes. | Erik Pearl
| 2006-01-20 | Info | Mech. Development | It has been decided to shift from Pochtler to Perlos for the 3D work. Perlos also has a set-up in BEJ wich makes it easier to transfer the project during spring/summer, plus Pochtler has already worked on Hawk that is alive again. | Erik
| 20-01-2006 26-01-2006 03-02-2006 20-02-2006 | closed | Key-lock switch | Implementation of sliding switch must be investigated for space and implementation issues: - Switch or hall sensor? - Size of either solution - Can the switch be moved to the other side of the phone? Hall sensor is most feasible for both parties. Two type are available. Decision not yet made It looks as if there is room for the Hall effect sensor solution Solution for A1 PCB will be with a MR sensor mounted on the PCB and a magnet on the slide switch. Prototypes are needed for mechanical/functional verification. | Erik | Flemming B. | 2006-02-10
| 2006-01-26 | closed | SP65 data | Should arrive today. Based on these data we will put in Aries display, Side switches and Hall sensor, as base for ID rework. | Christian |  | 2006-01-30
| 03-02-2006 20-02-2006 | closed | Use of 600mAh battery | We have been asked if we can use the 600 mAh battery in order to decrease the phone thichness. Standby and talktime will be reduced by 26% We will use the 820 mAh Aries battery | Christian | Flemming B. | 2006-02-08
| 2006-02-03 | Info | Meeting with industrial designer | Pearl Chen and Markus Borchert will be in Aalborg from 7-9 of Feb. | Christian
| 2006-02-03 | Info | Meeting with Perlos | 3 design engineers from Perlos will be in Aalborg from 6-9 of Feb. | Christian
| 09-02-2006 20-02-2006 | closed | Battery | We are investigating a new battery solution with the 750 mAh version from Hydra. This battery is slightly thicker, but a lot shorter than the 820 mAh we originally looked at. Aries 820mAh battery has been used and accepted by VF. | Christian | Pearl Marcus
| 2006-02-09 | Info | Stack-up/board-outline | BB informs that it is possible to move the components between the IO connector and the BB shield inside the shield. This shield will therefore be moved 2 mm to the south of the PCB in order to shift the battery as far south as possible. The components will likewise be moved 1 mm to the right compared to the SP65 layout. | Christian | Flemming B.
| 2006-02-20 | Open | Soft touch on back part | Mentioned as surface on back part by R. Voigt. Not communicated to PD team before 20.02.2006. Within this timeline this can only be achieved with paint. 2k moulding takes too long time. Christian investigates if Perlos has experience with this solution. | Christian
| 2006-02-20 | Info | Design fix | Pearl and Marcus will be in AAL in CW08 to finalize 3D design work including keypad solutions | Christian | Pearl Marcus
| 2006-02-20 | Info | Perlos | Perlos will be in AAL on 21.02.2006 | Christian
| 2006-02-20 | Open | Chrome feature on function keys | Investigations regarding the chrome dish on the function keys are on-going with the keypad suppliers. Will be further addressed with Pearl in CW08. | Christian | Pearl
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## HW
BB (Baseband)
| Owner: | Flemming Bach Kristensen |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 2006-01-26 | closed | Removal of components from SP 65 | Removal has been started, and addition of new connector and switches. Schematic update on-going. Waiting for board outlne for routing | Poul Erik | Flemming
| 2006-01-26 | open | Backlight concept | Investigations on-going. Waiting for answer from Thomas Bartl regarding use case for LED that must be white and also blink Green. Working assumption is 8 white and 1 green LED Latest request from VF now says blue keypad LED's and Green/White for home key. Blue LED's for SEND, END and function keys will make it impossible to see the printed colors on the keys, e.g. green and red. Must be confirmed by VF if this is really acceptable. | Poul Erik | Flemming
| 26-01-2006 03-02-2006 | closed | Power management | Investigating if changing from the Mozart+ to the Mozart Boost+. SW effort could stop this. We will stay with Mozart+ | Poul Erik | Flemming
| 2006-02-03 | Info | Vibra | We will change to the Hera vibra and move it to the top of the phone | Poul Erik | Flemming
| 2006-02-03 | info | USB cable support | If the components needed are removable, we will implement USB support initially on the B1 PCB | Poul Erik | Flemming
| 26-01-2006 09-20-2006 | open | A1 Tape out date | Exact date is needed -> Currently 15-02-2006 -> 24-02-2006-> 01-03-2006 | Poul Erik | Flemming Michael Arne
| 26-01-2006 03-02-2006 | closed | PCB Supplier | AT&S? We start with AT&S | Poul Erik | Mariann
| 2006-02-03 | open | Slim Lumberg | Still waiting for a final solution, pending accessories confirmation of availability | Poul Erik
| 20-01-006 03-02-2006 | Open | Investgation of antenna space | On-going based on similar shaped phones to be prepared for the stack-up Currently considering 2 different solutions depending on components and ID Currently preferred solution is a Cadilac antenna. Waiting for a defined stack-up in order to do further investigations | Poul Erik | Arne
| 2006-01-26 | Open | VF antenna requirements | Thinner phone might degrade the antenna performance. This might need to be discussed with VF | Poul Erik | Arne Christian
| 20-01-2006 03-02-2006 | closed | Bright 5E or 6E | Open issue which chip-set to use Check if B5E is going out of production Change from B5E to B6E will take 2-3 days BOM is similar, so no advantage there We will most likely have to change to B6E for size reasons, in order to be able to move the sidekeys further south and increase the antenna length to fulfill VF antenna requirements | Poul Erik | Michael | 2006-01-25
| 26-01-2006 03-02-2006 | closed | Smarti SD | From SW side there should be no problem shifting to the Smarti SD. Problem could be size if we have to reduce the width of the SP65 PCB, then B6E would be a better option. Smarti SD is supported in SW | Poul Erik | Michael
| 03-02-2006 09-02-2006 | closed | Bright 6E or Smarti SD | Based on stack-up it must be decided if we use B6E or Smarti SD. B6E is only half the size, but Smarti SD is EUR 1.2 cheaper. Problem is room for sidekeys if we use Smarti SD. B6E hass been choosen due to size reasons. Cost impact is 0.3 EUR compared to Smarti SD, but Smarti SD is too big for a single sided layout, and is much more sensitve to noise and PCB layout. | Poul Erik | Michael | 2006-02-08
| 2006-02-09 | Info | Screw towers | It looks as if the screw towers will not be in the same positions as for Penelopy | Poul Erik
| 09-02-2006 20-02-2006 | closed | Top level HW Planning in Primavera | Discussions still on-going regarding 3 or 4 PCB runs. I.e. 1 or 2 runs without plastic. Currently it looks as if we can only manage 3 timewise. Primavera planning must reflect this. We will run with 4 PCB revisions (A1, A1+, B1 and B2) | Poul Erik | Flemming | 2006-02-10
| 2006-02-20 | open | Home key | Check placement of the home key left or right | Poul Erik | Flemming Clemens Lutz
| 2006-02-20 | open | Sample plan | Finalize template and send round for planning | Poul Erik
| 2006-02-20 | open | RF test parameters | New parameters for production/Sample test must be supplied to Katharina | Poul Erik
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## PE
Procurement Engineering
| Owner: | Mariann Svendsen |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 26-01-2006 03-02-2006 | closed | BOM calculation | Calculation on-going. - Feedback on keypad is that apart from Polaris, this is the most expensive First calculation made based on own parts list. | Mariann |  | 2006-01-26
| 2006-01-26 | open | Parts list | Needed ASAP | Randi | Dorthe
| 2006-01-26 | info | Supplier | Plastic part supplier is implicitly choosen already | Mariann | Christian
| 03-02-2006 20-02-2006 | open | Key component list | BOM in SAP must be update based on current A1 schematics, and the key components list will then be generated based on this. List will be used to prioritize components regarding 2nd sourcing and component qualification. | Mariann | Randi Dorthe | 2006-02-08
| 2006-02-09 | open | S0 declaration | 1 week before we need: Parts list including: - Delivery unit (user guides, boxes, sticker, CD-ROM, mech., ...) Mariann will chase Kheng-Wah | Mariann | Kheng-Wah Dorthe | 2006-02-16
| 2006-02-09 | closed | BOM update | Needed for WS in BEJ Monday 11.00 | Mariann
| 2006-02-20 | open | BOM update | Needed for milestone declaration | Mariann
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## SW
Software
| Owner: | Hans Henrik Skovgaard |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 20-01-2006 03-02-2006 | closed | B5E or B6E RF or Smarti SD | Clarify impact on SW of changing the RF No problems, support exist for all 3 | Hans Henrik Allan |  | 2006-02-01
| 2006-01-20 | info | Sync-up | Daily telco's with BEJ SW PL Main task is to secure DL support for BEJ | Hans Henrik
| 20-01-2006 20-02-2006 | Open | Timeline investigations | Feling is that it will be more than difficult tomeet the timeline 1st guess on top level planning in CW6 Task has shifted to BEJ. BEJ estimate is end of Feb. For planning of SW We have received plan from BEJ. Plan will be put in Primavera by Bjarne BEJ Confident of timing except for the PIM part. Reason is lack of experienced PIM resources. All BEJ PIM resources fully loaded. | Hans Henrik
| 2006-01-26 | info | DL resources | Has been appointed and BEJ notified of names | Hans Henrik Allan
| 2006-01-26 | info | CIT Resources | Has been appointed and BEJ notified of names | Hans Henrik Allan
| 26-01-2006 03-02-2006 | closed | Requirement responsibilities | Responisibilities/Work-flow is un-clear. Who has contact to e.g. VF Who are setting the high level requirements Who are setting requirements to component team -> 1st draft of feature list available 27.01.2006 | Allan
| 2006-01-26 | open | Communication flow | Setting up contacts for: - BEJ - SISL - PSE | Allan |  | 2006-02-17
| 2006-01-26 | info | Aries SW | Aries SW currently being transfered to AAL and databases being set-up. Ready for AAL to start working on SW mid CW5. | Allan
| 26-01-2006 03-02-2006 | closed | Aries wing boards | So far we have not managed to find wing boards anywhere -> Henning Boll might be able to find some | Hans Henrik | Henning
| 2006-02-09 | Open | Service light indicator | This functionality must be added to the "Home" key - Clarify "Service light" name, if this is VF name/functionality | Allan | Clemens Lutsch
| 2006-02-09 | Open | Tool chain | Production tools needs to be planned/clarified: - Bootcore, BFC, EESimu, HWKennung, ...... Who own them? | Allan | Yang Yong Qiang | 2006-02-17
| 09-02-2006 20-02-2006 | closed | Hydra battery | If this battery is choosen, these characteristics must be transferred from the SG2 platform to SGL Aries battery will be used | Allan
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## ST MO
System Test Modem & Approval
| Owner: | Flemming Kokholm |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 2006-01-20 | closed | ST support for BEJ | Based on mail from BEJ we do not expect to have anything to do on Jerry. BEJ have both ST1 and ST2 resources available AAL will support
| 2006-02-09 | Info | Test fixtures | Flemming Kokholm will coordinate the needed test fixtures - Needs layout and mechanical data (ASAP) | Flemming K.
| 2006-02-09 | Open | Internal TA test | Current set-up indicates that AAL will do the test | Flemming K.
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## QM HW
QM HW
| Owner: | Thomas Bartel / Poul Søndergaard |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 2006-02-03 | Open | Stack-up solution | Be aware that there might be problems with a single PCB solution, with the BGA's breaking off due to pushing the keypad
| 20-02-206 | Open | HW System/Design FMEA | Planned when? Thomas is in Europe in CW09/10 and maybe we should allign with this. | Thomas Poul Erik Christian |  | CW10
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## NPI
Service
| Owner: | Henning Boll |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 26-01-2006 03-02-2006 | closed | GRR document | Template wil be put on the project drive for update Pre-requisite for M0 and M1 | Henning
| 26-01-2006 03-02-2006 | closed | Sample plan | For both Rea and PD team is needed a sample plan | Lars
| 2006-02-03 | info | BEJ NPI support | Andreas Springer
| 2006-02-03 | info | Fixtures | We do not expect to be able to reuse the Penelopy fixtures. Will call a meeting to see what is possible | Henning |  | 2006-02-08
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## Planning
Planning (Primavera)
| Owner: | Bjarne Lund Thomsen |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 2006-01-26 | open | Detailed planning | People need to start this | Bjarne | PPL's
| 2006-01-26 | closed | Mechanical planning | Shift in PL MD will result in different MD startegy and MD timeline | Bjarne | Christian Lars | 2006-02-08
| 2006-02-09 | info | PPL Successors | All has been created in Primavera, except AD | Bjarne
| 2006-02-09 | open | M0-M1 planning | From CW7 we are ready to do detailed planning from M0 to M1 | Bjarne
| 2006-02-20 | open | SW planning | SW plan has been received as agreed from BEJ in MS Project format, and will be put into Primavera. Target is to have a plan ready for W. Klebsch before the VF meeting Wednesday 22.02.06 | Bjarne | Lars
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## LCM 3
Function
| Owner: | Katharina Hilker / |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 2006-02-20 | Open | Production WS | Needed before M1. MD must be involved. | Katharina
| 2006-02-20 | Open | Test technology WS | Special focus must be put on the on/off key and the slide switch. | Katharina |  | CW10
| 2006-02-20 | Open | Parts list | List needed to check component availability for A1 run | Poul Erik
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## PL-T
TPM (Technical Product Manager)
| Owner: | Lars Bonde (Telephone +45 7219 5112 ; Mobile +45 2045 6872) |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
| 2006-01-20 | Info | Workshop in BEJ | The team will call for a WS in Beijing in CW06 in order to allign the AAL and BEJ teams. Agenda and who should attend are still pending | Arjen Broeze Lars
| 20-01-2006 20-02-2006 | Info | Project timing | 1st draft of schedule available in Primavera. NOTE: Planning is only based on HW and MD, SW plan still missing SW plan is currently being made in Primavera | Lars
| 26-01-2006 03-02-2006 | closed | Aries phones | 10 Samples are needed to be modified as "Jerry" targets | Lars
| 2006-01-26 | closed | Sample plan | Supply a sample plan to LPD before tape-out of B1 PCB Poul Erik is currently compiling a plan. | Lars |  | 2006-02-10
| 2006-01-26 | Info | Industrial design | Current ID with the Aries display has been rejected by VF as being to thick for a 2G entry phone. This puts the timeline under pressure for HW amd Mech development as as design fix is pending and we do not have a PCB board outline available. | Lars
| 2006-02-09 | open | Variants | Clarify language groups and variants | Kheng-Wah | Lars
| 2006-02-09 | open | SWUOTA | Shall we support SWUOTA in Jerry (Not required by VF) | Kheng-Wah | Lars | 2006-02-17
| 2006-02-20 | Info | PD Team meetings | Our BEJ colleagues are now participating in the PD team minutes. Lars Bonde will still host the meetings. | Lars
| 2006-02-20 | Info | Primavera planning | The planning has been update in Primavera has been updated. Most milestones have shifted about 1 week compared to planning in mid January. DS is now 22.09.2006 | Lars
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"

## Template
Function
| Owner: | NN |  |  |  |  | Today: | 2026-07-28
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"
Note on A26: Click +/- to view/close "Notes"