## Change History
Jerry Prioritized Feature cluster
History of Change
Version | Date | Editor | Status | Description
1.0_001 | 2006-02-14 | Huang Qian | in work | First draft created during the requirement and feature list workshop.
1.1_000 | 2006-02-20 | Yang Yong Qiang | in review | refined in workshop. Offline review.

## All Features
ID | Feature | Sprint | Timeline | Remark
1 | Start-up/power on dialogs | sprint 1 | 31.03.2006 | Only PIN input in sprint 1, rest by sprint 3
2 | Show Startup Assistant | sprint 3 | 31.05.2006
3 | PC Simu setup | sprint 1 | 31.03.2006
4 | Idle screen | sprint 1 | 31.03.2006 | Only as VF Simply Styleguide (version 1.5, 02.02.2006) page 5 figure 1.Idle, incl all functional scenario, w/o transition, headline, softkeys effect. Rest by sprint 4
5 | Home/Contact/Menu hard key invocation | sprint 1 | 31.03.2006
6 | Phone spaces, color schemes, Icons, Fonts | sprint 1 | 31.03.2006
7 | Voice call screens basic | sprint 1 | 31.03.2006 | Full functions by sprint 3
8 | Headline and soft key look and feel | sprint 1 | 31.03.2006
9 | Menu look and feel basic | sprint 1 | 31.03.2006 | Full compliance by sprint 3
10 | Remove or hide or disable features | sprint 1 | 31.03.2006
11 | Tips | sprint 2 | 28.04.2006
12 | Volume side key, Ringer side key and lock key invocation | sprint 2 | 28.04.2006
13 | Contact list and menu options (without functionality inside) after pressing Contact hard key | sprint 1 | 31.03.2006 | Full functions by sprint 3
14 | Screen transitions | sprint 2 | 28.04.2006 | Only sliding effect. Menu and popup selection transitions by sprint 3.
15 | Unified Inbox (Layout) | sprint 2 | 28.04.2006 | Full functions by sprint 4
16 | Synchronization including remote sync and sync with SIM | sprint 2 | 28.04.2006
17 | Key lock screen after switching the key lock hard key. | sprint 3 | 31.05.2006
18 | Settings | sprint 3 | 31.05.2006 | Ring tong, keypad tone, time/date, display my number, language and change PIN shall be available by sprint 2
19 | Contact log | sprint 2 | 28.04.2006
20 | Voice call screens (full functions) | sprint 3 | 31.05.2006
21 | VF Simply Alarm Clock | sprint 4 | 07.07.2006
22 | Voice messaging | sprint 3 | 31.05.2006
23 | Picture messaging | sprint 3 | 31.05.2006
24 | Message setting | sprint 3 | 31.05.2006
25 | Inbox UI (all message list) | sprint 3 | 31.05.2006
26 | Menu look and feel - full compliance | sprint 3 | 31.05.2006
27 | Sleep mode with timer settings | sprint 4 | 07.07.2006
28 | Hover functionality in Contact list | sprint 4 | 07.07.2006
29 | Unified Inbox Functionality | sprint 4 | 07.07.2006
30 | Text message (SMS) | sprint 4 | 07.07.2006
31 | Idle split screen | sprint 4 | 07.07.2006
32 | MsgAE | sprint 4 | 07.07.2006
33 | Templates/Drafts | sprint 4 | 07.07.2006
34 | Unified sent message | sprint 4 | 07.07.2006
35 | Delete (All) wizard | sprint 4 | 07.07.2006

## sprint 1
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
Feature | WP ID | WP = 4 weeks x # resources | # weeks | # resources | #SISL MW | #Beijing MW | responsible site | contact person | Timeline | Dependency | comment
Identify all text/icon resources and delivery to ResUI team for integration into project database (initially for sprint 1 and 2, and then cover all sprints) |  |  | 4 | 1 | 4 |  | SISL | Lovleen | sprint 1
Integration of texts/graphics/fonts into project database (initially for sprint 1 and 2, and then cover all sprints) |  |  | 4 | 1 | 4 |  | SISL | Wu Ying Yu | sprint 1
define Font in UIOS |  |  | 1 | 1 |  | 1 | Beijing | Lu Qi Wen | sprint 1 | text resources
Start-up/power on dialogs | 1_1 | PIN input, incl. error handling | 4 | 2 | 8 |  | SISL | Rajeev Chauhan | sprint 1 | text resources
| 1_2 | Date and Time settings |  |  |  |  | SISL |  | sprint 2
Show Startup Assistant | 2_1 | (TCD-MESG_SIM-990002) At power on, the device shall check EF_MSISDN on the SIM for the presence of an MSISDN. If the field is blank then the device shall prompt the user to "Enter own number"; details of the UI interaction shall be in accordance with the MMI spec | 1 | 1 | 1 |  | SISL |  | sprint 2
| 2_2 | invoke SyncML and Sync between sim and phone | 1 | 1 | 1 |  | SISL |  | sprint 3
PC Simu setup | 3_1 | 3 hard keys (Home, Contact, Menu) simu, blinking effect for home key | 4 | 1 | 4 |  | SISL | Rajeev Chauhan | sprint 1 | DL
| 3_1 | side keys simu | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | sprint 1 | DL
| 3_1 | Changes in C_MobSIM for removing/disabling/hiding features | 2 | 1 | 2 |  | SISL | Rajeev Chauhan
Idle screen | 4_1 | Refer to VF Simply Styleguide (version 1.5, 02.02.2006) page 5 figure 1.Idle, incl all functional scenario, w/o transition, headline, softkeys effect | 4 | 2 | 8 |  | SISL | Rajeev Chauhan | sprint 1 | text/icon
| 4_2 | new event dialog (part of Unified Inbox) | 2 | 1 | 2 |  | SISL |  | sprint 3
| 4_3 | Idle UI adaption on network selection | 2 | 1 | 2 |  | SISL |  | sprint 2
| 4_4 | show call setting: call barring incoming/outcoming if abroad (new ), effect in Idle | 4 | 1 | 4 |  | SISL |  | sprint 2
| 4_5 | TCD-USRX-BAS-008053 Interruption by Events (Partly (nearly not) implemented in X75, needs separate call CSM. (Part 1) Separation of Call functionality from the Idle | 6 | 3 | 18 |  | SISL |  | sprint 4
| 4_6 | (Part 2) Call CSM Message Handling | 6 | 3 | 18 |  | SISL |  | sprint 4
| 4_7 | (Part 3) Dial Dialog Updation Handling | 4 | 3 | 12 |  | SISL |  | sprint 4
| 4_8 | Welcome tour | 1 | 1 | 1 |  | SISL |  | sprint 4
| 4_9 | Charging display adaption | 1 | 1 | 1 |  | SISL |  | sprint 4 | text/icon, ApiCore
Home/Contact/Menu hard key invocation | 5_1 | Invocation of native applications on hard keys press, light effect at home space | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | sprint 1 | UIOS, DL
Phone spaces, color schemes, Icons, Fonts | 6_1 | color scheme switching interface, define additional virtual colors | 2 | 1 |  | 2 | Beijing | Lu Qi Wen | sprint 1 | text resource
| 6_2 | text resource to define color scheme | 1 | 1 |  | 1 | Beijing | Wu Ying Yu | sprint 1
| 6_3 | phone space color scheme switching (IDC) | 1 | 1 | 1 |  | SISL | Rajeev Chauhan | sprint 1 | color scheme switching in UIOS
Voice call screens basic | 7_1 | calling use case: call origination, termination, call setup | 4 | 3 | 12 |  | SISL with Beijing IDC support | Rajeev Chauhan Xu Peng | sprint 1
| 7_2 | all calls list (call records) | 2 | 1 | 2 |  | SISL |  | sprint 3
Headline and soft key look and feel | 8_1 | UIOS | 4 | 3 | 12 |  | SISL | Rajeev | sprint 1 |  | with support from Beijing
Menu look and feel basic | 9_1 | look and feel w/o transition effects | 4 | 2 |  | 8 | Beijing | Lu Qi Wen | sprint 1
| 9_2 | scroll bar | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | sprint 1
Remove or hide or disable features | 10_1 | Irda, BT (remove) | 2 | 1 | 2 |  | SISL |  | sprint 2 | PS, connectivity
| 10_2 | Camera (remove) | 2 | 1 | 2 |  | SISL |  | sprint 2
| 10_3 | MultiMedia removing | 2 | 1 | 2 |  | SISL |  | sprint 3
| 10_4 | Browser (hide) | 4 | 1 | 4 |  | SISL |  | sprint 2
| 10_5 | Java (remove) | 1 | 1 |  | 1 | Beijing |  | sprint 1
| 10_6 | showing UI notification about accessory from connectivity (disable) | 2 | 1 | 2 |  | SISL |  | sprint 2
| 10_7 | DRM (disable) | 4 | 1 |  | 4 | Beijing | Lu Qi Wen | sprint 3
Preparation for sprint N+1 |  |  | 4 | 3 | 12 |  | SISL
Preparation for sprint N+1 | [5 empty] | 0 | Beijing
total effort(MW) |  |  |  |  | 127 | 12
total effort(MW) | [5 empty] | 139

## spint 2
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
Feature | WP ID | WP = 4 weeks x # resources | # weeks | # resources | #SISL MW | #BeijingMW | responsible site | contact person | Timeline | Dependency | comment
Tips | 11_1 | Tips and sub-menu | 4 | 2 | 8 |  | SISL | Rajeev Chauhan | sprint 2 | resource management
Volume side key, Ringer side key and lock key invocation | 12_1 | ringer side key in idle | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | sprint 2 | UIOS
| 12_2 | volume side key in In-call | 1 | 1 | 1 |  | SISL |  | sprint 2
| 12_3 | lock key | 1 | 1 | 1 |  | SISL |  | sprint 2
Contact list and menu options after pressing Contact hard key | 13_1 | list address book (without functionality inside) | 2 | 2 | 4 |  | SISL | Rajeev Chauhan | sprint 1 | UIOS | With Beijing PIM team support
| 13_1 | display menu options with some functions, e.g. copy, delete, add | 3 | 2 | 6 |  | SISL | Rajeev Chauhan | sprint 1 | UIOS | With Beijing PIM team support
| 13_2 | contact editor | 4 | 1 | 4 |  | SISL | Rajeev Chauhan | sprint 2 | list address book | With Beijing PIM team support
| 13_3 | merge entry in sim to contact list | 4 | 1 | 4 |  | SISL | Rajeev Chauhan | sprint 2 | list address book | With Beijing PIM team support
| 13_4 | complicated functions: add reminder, sim backup w/o view log | 4 | 2 | 8 |  | SISL | Rajeev Chauhan | sprint 2 | display menu options | With Beijing PIM team support
| 13_5 | launch external application, e.g. Voice Messaging, SMS, call | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | sprint 3 | need interface from other components, i.e. messaging, IDC | With Beijing PIM team support
| 13_6 | PIM settings | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | sprint 3 | display menu options | With Beijing PIM team support
| 13_7 | export inteface (insert contact, select contact) to external appl. i.e. messaging, IDC | 4 | 2 | 8 |  | SISL | Rajeev Chauhan | sprint 3 | list address book | With Beijing PIM team support
| 13_8 | call record look and feel | 4 | 2 | 8 |  | SISL | Rajeev Chauhan | sprint 2 |  | could be started in sprint 1 if resources OK in PIM
Screen transitions | 14_1 | sliding effect | 4 | 2 |  | 8 | Beijing | Lu Qi Wen | sprint 2
| 14_2 | menu selection transition | 4 | 2 |  | 8 | Beijing | Lu Qi Wen | sprint 3
| 14_3 | popup transition | 4 | 2 |  | 8 | Beijing | Lu Qi Wen | sprint 3
Unified Inbox (Layout) | 15_1 | Jerry look and feel of Unified Inbox in SGL functionality w/o MMS | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | sprint 2
Synchronization including remote sync and sync with SIM | 16_1 | SyncML UI adaption | 4 | 2 | 8 |  | SISL |  | sprint 2 | could start in parallel beginning of Mar
| 16_2 | SyncML workflow adaption | 5 | 2 | 10 |  | SISL |  | sprint 2 | could start in parallel beginning of Mar
customization(mapping, FFS) |  |  | 2 | 1 |  | 2 | Beijing
Preparation for sprint N+1 |  |  | 4 | 3 | 12 |  | SISL
Preparation for sprint N+1 | [5 empty] | 0 | Beijing
[5 empty] | 90 | 26
total effort(MW) | [5 empty] | 116

## sprint 3
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
Feature | WP ID | WP = 4 weeks x # resources | # weeks | # resources | #SISL MW | #Beijing MW | responsible site | contact person | Timeline | Dependency | comment
Key lock screen after switching the key lock hard key. | 17_1 | implementation of keylock screen | 4 | 1 | 4 |  | SISL | Rajeev | sprint 3
Settings | 18_1 | ring tong, keypad tone, time/date, display my number, language, change PIN | 3 | 2 | 6 |  | SISL |  | sprint 2
| 18_2 | Complete settings | 3 | 2 | 6 |  | SISL |  | sprint 3 | AppIDC, PIM, messaging settings
Contact log | 19_1 | new msg info table support in PIM AE | 4 | 2 | 8 |  | SISL |  | sprint 2
| 19_2 | sorting mechanism | 4 | 1 | 4 |  | SISL |  | sprint 2
| 19_3 | UI implementation in PIM | 4 | 1 | 4 |  | SISL |  | sprint 2
| 19_4 | call record adaption | 4 | 1 | 4 |  | SISL |  | sprint 2
| 19_5 | export inteface (insert contact, select contact) to external appl. i.e. messaging, IDC | 4 | 1 | 4 |  | SISL |  | sprint 2
| 19_6 | adaption in messaging | 2 | 1 | 2 |  | SISL |  | sprint 3 | msgAE
Voice call screens (full functions) | 20_1 | handling different network release codes | 4 | 2 | 8 |  | SISL |  | sprint 3
| 20_2 | call reminder | 4 | 1 | 4 |  | SISL |  | sprint 3
| 20_3 | in-call menu adaption | 2 | 2 | 4 |  | SISL |  | sprint 3
VF Simply Alarm Clock | 21_1 | list all alarm events | 4 | 1 | 4 |  | SISL |  | sprint 3 | list all alarm events | depending on resource situation
| 21_2 | time/date editor | 2 | 2 | 4 |  | SISL |  | sprint 4
| 21_3 | alarm text | 1 | 1 | 1 |  | SISL |  | sprint 4
| 21_4 | alarm tone/volume/vibration | 3 | 2 | 6 |  | SISL |  | sprint 4 | volume adjust from Appbase
| 21_5 | menu options in alarm clock, i.e. delete, add | 2 | 2 | 4 |  | SISL |  | sprint 4
Voice messaging | 22_1 | view and editor | 9 | 2 | 18 |  | SISL |  | sprint 3
| 22_2 | send and receive | 2 | 2 | 4 |  | SISL |  | sprint 3
Picture messaging | 23_1 | Picture messaging | 5 | 2 | 10 |  | SISL |  | sprint 3
Message setting | 24_1 | Message setting | 3 | 1 | 3 |  | SISL |  | sprint 3
Inbox UI (all message list) | 25_1 | Inbox UI | 5 | 2 | 10 |  | SISL |  | sprint 3
menu look and feel - full compliance | 26_1 | UIOS full compliance (incl. progress bar) | 3 | 3 |  | 9 | Beijing |  | sprint 3
| 26_2 | VF menu full compliance (incl. progress bar) | 4 | 3 | 12 |  | SISL
customization(mapping, FFS) |  |  | 2 | 1 |  | 2 | Beijing
Preparation for sprint N+1 |  |  | 4 | 3 | 12 |  | SISL
Preparation for sprint N+1 | [5 empty] | 0 | Beijing
[5 empty] | 122 | 0
total effort (MW) | [5 empty] | 122

## sprint 4
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
Feature | WP ID | WP = 4 weeks x # resources | # weeks | # resources | #SISL MW | #BeijingMW | responsible site | contact person | Timeline | Dependency | comment
Sleep mode with timer settings | 27_1 | back to last screen from where the sleep mode was activated | 4 | 2 | 8 |  | SISL | Rajeev | sprint 4
| 27_2 | screen saver handling in idle | 2 | 1 | 2 |  | SISL |  | sprint 4
Hover functionality in Contact list | 28_1 | UIOS provide this function | 2 | 1 | 2 |  | SISL |  | sprint 4
| 28_2 | PIM adaption | 2 | 1 | 2 |  | SISL |  | sprint 4
| 28_3 | messaging adaption | 2 | 1 | 2 |  | SISL |  | sprint 4
Unified Inbox Functionality | 29_1 | Unified Inbox Functionality | 6 | 2 | 12 |  | SISL |  | sprint 4
| 29_2 | welcome tour handling | 3 | 1 | 3 |  | SISL |  | sprint 4 | Idle
Text message (SMS) | 30_1 | view and editor | 5 | 2 | 10 |  | SISL |  | sprint 4
| 30_2 | send and receive | 2 | 2 | 4 |  | SISL |  | sprint 4
Idle split screen | 31_1 | Full functional Idle split screen | 4 | 1 | 4 |  | SISL |  | sprint 4
MsgAE | 32_1 | get and update msg table from inbox UI/sent msg UI | 4 | 2 | 8 |  | SISL |  | sprint 3
| 32_2 | delete msg and delete all | 4 | 1 | 4 |  | SISL |  | sprint 3
| 32_3 | sync between msg table in PIM and msg DB in Appmsg | 3 | 2 | 6 |  | SISL |  | sprint 4
| 32_4 | SMS/MMS client updation | 2 | 2 | 4 |  | SISL |  | sprint 3
Templates/Drafts | 33_1 | Templates/Drafts | 4 | 2 | 8 |  | SISL |  | sprint 2
Unified sent message | 34_1 | Unified sent message | 3 | 2 | 6 |  | SISL |  | sprint 4
Delete (All) wizard | 35_1 | Delete (All) wizard | 4 | 2 | 8 |  | SISL |  | sprint 4
customization(mapping, FFS) |  |  | 3 | 1 |  | 3 | Beijing | Chai Chun Qian
Preparation for sprint N+1 |  |  | 4 | 4 | 16 |  | SISL
Preparation for sprint N+1 |  |  | 4 | 1 |  | 4 | Beijing
[5 empty] | 109 | 7
total effort (MW) | [5 empty] | 116
Overall Effort (MW) |  |  |  |  | 448 | 45
493
4 sprints scheduled for development and unit&integration test. S25 SW freeze would be sprint 4. Full run of System test starts in sprint 5.