## Aries Review
|  |  |  | high | open
|  |  |  | medium | pending
|  |  |  | low | closed
C75 "Aries" Text Entry Review
ID | Issue | Description | SMART Requirement | Prioritization | Status
General issues
1 | Screensaver | Screensaver should not exit the text editor! After unlocking the device the user should get back to the editor |  | high | open
2 | Tool tip | After a delay of ~ 5 seconds a tool tip should appear at the buttom of the screen that explains where the mode can be changes, where symbols can be entered and where the space can be insert. Automatic Tips shouldn't interfere with user's goal to finish text |  | high | open
3 | Clear soft key label | "<C" might not be understood by all users. Better: Clear |  | high | open
4 | Undesired deletion of words | If the word is not recognized in predictive entry ( "_ _ _ _" is displayed and the LSK says "Spell") and the user presses up/down or left/right the word is deleted |  | high | open
5 | No emoticons in symbol list | The symbol list shall contain in addition to the special characters the major emoticons (i.e. :) , :( , :¦ , :D, ;). | TCD-USRX-BAS-008107: Emoticons in the Symbol List | high | open
6 | Toggling through the candidates in predictive text entry | Currently the toggling mechanism is assigned to the right soft key. This interferes with the "spell" assignment if a word is not in the candidate list. --> if the user toggles through all candidates the "spell" mechanism is on left soft key --> inconsistent Possible solutions: A) Always assign "spell" to the right softkey. Attention: - Nokia patent. B) Always assign "spell" to the left softkey. Attention: Only if "Jerry" has a dedicated clear key C) Assign the toggling to the up/down key. The user would then be able to go to the end of the candidate list with one click on the up key. Attention: impact on the general navigation. | TCD-USRX-BAS-008102: Add Word to Candidate Word List | medium | open
7 | Inconsitent entry mode | Multitap is used to enter symbols via 0 key even in predictive entry and on 1 key for space, new line and 1. --> inconsitent |  | medium | open
8 | ABC Mode | The user has to be in "upper mode" (e.g. Abc or T9 Abc) in order to access the ABC or the T9 ABC mode via shortcut. |  | medium | open
9 | Emoticons support in predictive entry | The editor recognize emoticons only if the user inserts a symbol and enters another symbol after a short delay. Very odd behaviour. |  | medium | open
10 | Candidate word list | The candidate word list (while in single-tap entry) shall be organised dynamically based on the user's frequency of use for each word. | TCD-USRX-BAS-008101: Dynamic Reordering of the Candidates List | medium | open
11 | No "Word Choice List" | No "Word Choice List" implemented | TCD-USRX-BAS-008100: Word Choice List | medium | open
12 | Mode and Shift Change combined | The Change of Mode (Predictive vs. Multitap) is combined with Capitalisation Change ( Abc, abc, ABC, 123). This might cause confusion. | TCD-USRX-BAS-008091: Change of Entry Mode | medium | open
13 | Assignment of Space | Space is assigned to 1. 0-key is more common. User might be irritated. |  | medium | open
14 | T9 Guide | It would be good to have a T9 start guide -> culd be provided by Tegic |  | medium | open
15 | Predictive TE icon/ Multitap icon | Multitap icon may be misleading (-> Nokia icon for T9 is similar). Better without "pen" | TCD-USRX-BAS-008095: Text Field Indication Line | low | open
4-way Navigation to 2-way navigation ("Aries" uses 4-way navigation. Recommendations for the 2-way implementation)
16 | General 2-way navigation in the text | The down key should move the cursor one position to the right. The up key should move the cursor one postion to the left |  | high | open
17 | 2-way navigation in predictive entry | Navigate word by word as the words are the subjects of editing. It should be reassured that the end and the beginning can be reached, so that the user can add prefixes and suffixes to the words. The user should be able access the word and change it. See picture right |  | high | open
18 | Longpress Navigation | There shall be a mechanism to accelerate the navigation (e.g. short press navigates characters and long press navigates word by word, or the speed is increased). But long press should not jump to the beginning/end of the text. The long press behaviour should be congruent with the deletion long press behaviour. |  | high | open
Option Menu
19 | Mark | Marking function might be to advanced for simply |  | high | open
20 | Format | Formating function might be to advanced for simply |  | high | open
Symbol Entry
21 | Symbol list | The oder of the symbols is odd and doesn't follow the ETSI Guidelines. Better: Stick to the ETSI Guidelines | TCD-USRX-BAS-008105: Special Characters | high | open
22 | Space after Interrogation symbols | After entering a interrogation symbol (e.g. . , ? !) a space should be entered automatically. |  | medium | open
23 | Symbol list | Initial highlight is on "*". The key is labelled "*" but most users understand that the symbol list can be accessed via the "*" key and looking for other symbols. Better: most frequent symbol (e.g. "." or space) |  | medium | open
24 | Symbols on 0 key | Why is the dot (.) double? |  | medium | open
Minor issues
25 | Cursor | In predictive entry the cursor at the end of a word should be flashing |  | low | open
26 | *-key shortcut | Longpress short cut on * key should not be used for "option menu" |  | low | open
27 | Delete text | "Delete text" unnececary for simpley |  | low | open
28 | T9 symbol | T9 symbol in predictive entry icon should be bigger |  | low | open

## Requirements
SMART Requirements R9
# | Title | Detailed Text
1 | TCD-USRX-BAS-008087: Support for Multiple Language Character Sets | The terminal shall support all language specific keypad assignments of digits and letters as well as all language specific character sets as specified in ETSI ES 202 130.
2 | TCD-USRX-BAS-008088: Input Language | The device should support multiple input languages. The user shall be able to change the input language independently of the current UI language. The user setting shall be preserved.
3 | TCD-USRX-BAS-008089: Entry Methods | The terminal shall support multi-tap alphanumeric text entry and single-tap alphanumeric text entry (predictive text input).
4 | TCD-USRX-BAS-008090: Entry Modes | The user shall have access to the following text entry modes: - Automatic capitalisation mode (Abc) - All upper case mode (ABC) - Numeric mode (123) - All lower case mode (abc) The user shall be able to quickly cycle between all available text entry modes with a single click or key press. In "Abc" mode the next element in the cycle shall be "abc" and the other way around.
5 | TCD-USRX-BAS-008091: Change of Entry Mode | The user shall be able to quickly cycle between all available text entry modes with a single click or key press. Language selection and Single-tab on/off shall be separate from changing the text entry modes.
6 | TCD-USRX-BAS-008092: Availability, Default Assignments and Preservation of Text Entry Method and Mode | The availability of text entry modes and methods and the default setting of modes and methods shall meet the characteristics of the different text field types (e.g. For a PIN field numeric entry mode should be active but for a name field multi-tap with capitalisation should be active). The following table describes the required - default assignment of method and mode for the different text entry situations, - availability of method and mode for the different text entry situations and - specifications about the preservation of method and mode for the different text entry situations. If the preservation is "save last" the user's last used setting for entry method and mode shall be remembered in that text entry situation.
7 | TCD-USRX-BAS-008093: Entering Numbers when not in Numeric Mode | When entering text a long press on a numeric key should enter the respective number. This does not apply when the numeric text entry mode is active.
8 | TCD-USRX-BAS-008094: Indication of a Text Entry | It shall be clear to the user when a text field is ready for input (e.g. by a flashing cursor).
9 | TCD-USRX-BAS-008095: Text Field Indication Line | It shall be made clear to the user in a consistent way, which text entry mode (e.g. ABC, Abc, abc, 123) is currently active. It shall be made clear to the user whether predictive text is turned on or off.
10 | TCD-USRX-BAS-008096: Indication of the Number of Available Characters in Text Entry Fields | In multi-line text fields and if the maximal number of characters is limited it shall be clear to the user how many characters can yet be entered (i.e. the text field restricted to 1024 characters, the user has already entered 24 characters: '1000' may be displayed).
11 | TCD-USRX-BAS-008097: Deletion Behaviour | The user shall be able to delete text character by character. There shall be a mechanism to accelerate the deletion (e.g. short press deletes characters and long press delete word by word) but a text field shall never be deleted all at once.
12 | TCD-USRX-BAS-008098: Active Word Highlighting | In single-tap text method the active word shall be highlighted.
13 | TCD-USRX-BAS-008099: No Extra Confirmation of Candidate Words in Single-Tap | The user shall not need to confirm a candidate word in an extra step to be able to proceed typing.
14 | TCD-USRX-BAS-008506: Re-Editing of Words in Single-tap Entry | The user shall be able to re-select a word already entered and edit it again. (E.g. the user shall be able to navigate back to a word and toggle through the candidates).
15 | TCD-USRX-BAS-008100: Word Choice List | In Single-tap the user shall be able to select candidate words from a choice list
16 | TCD-USRX-BAS-008101: Dynamic Reordering of the Candidates List | The candidate word list (while in single-tap entry) shall be organised dynamically based on the user's frequency of use for each word.
17 | TCD-USRX-BAS-008102: Add Word to Candidate Word List | The user shall be able to add words to the list of predictive words for Single-tap entry. This functionality shall be offered prominently immediately after typing a word that is not recognized by Single-tap but shall not interfere with the user's goal to continue entering text.
18 | TCD-USRX-BAS-008103: Phonebook Entries in Single-Tap | All phonebook entries (i.e. names, email addresses, ..) shall be available as candidate words in the candidate list in Single-tap entry.
19 | TCD-USRX-BAS-008104: Character Choice List | For multi-tap mode a character choice list shall be supported. In the character choice list the selected character shall be highlighted. The indication shall show all available characters and shall disappear upon selection or after timeout.
20 | TCD-USRX-BAS-008105: Special Characters | The symbols of the language independent keypad assignment of special characters specified in the ETSI Standard (ETSI ES 202 130) shall be used for the symbol list. The order of the characters shall follow the specified order.
21 | TCD-USRX-BAS-008106: Adding Symbols | The user shall be able to use two ways to insert symbols: - a full list of symbols shall be accessible from the text editor by a single click or key press (e.g. by assigning it to the #-key) - most relevant symbols (e.g. an '@' character for an email addresses field) shall be accessible from the text editor with a single click or key press
22 | TCD-USRX-BAS-008107: Emoticons in the Symbol List | The symbol list shall contain in addition to the special characters the major emoticons ( i.e. :) , :( , :¦ , :D, ;).
23 | TCD-USRX-BAS-008108: Input Masks and Restrictions | Where appropriate the terminal shall support masked alpha numeric input (e.g. when entering a date the mask [__:__:____] shall be provided to avoid that the user has to enter separators manually). Invalid input shall be restricted (e.g. a numeric month-field shouldn't accept a 13).