## Sheet1
BenQ Siemens Simply Jerry - Action Log |  |  |  |  | = overdue
AI No. | Subject | Action Item - Description | Who? |  | Issue date | Due date | Close date | Status | Vodafone Remarks / Resolution | BenQ Remarks / Resolution
1 | Voice Calls | Investigate further why 200 min instead of 300 min for voice calls - due by 21st Nov | B |  | 2005-11-14 | 2005-11-21 |  | Closed | 250 hrs
2 | SyncML | Investigate further whether SyncML via HTTP is supported | B |  | 2005-11-14 | 2005-11-21 |  | Closed
3 | PC application | Provide specification (interface and application) and Vf contact for PC application to BenQ | VF | Chris Wellock | 2005-11-14 | 2005-11-15 |  | Closed | PC application specs sent to BenQ Siemens on 18th Nov.
4 | Dummies | Investigate further the feasibility of country specific language on the dummies 21st Nov update: Provide minimum volume figuers | B |  | 2005-11-14 | 16th Dec |  | Closed | minimum number: 5k per OpCo
5 | Sales Box | Provide sales box specs to BenQ | VF |  | 2005-11-14 | 2006-01-03 |  | Open | Revised due date Update 20th Jan: The sales box guide hasn't changed so far.
6 | ID | Send pictures and existing samples of the charger / docking station | B |  | 2005-11-14 | 2005-11-21 |  | Closed | updated 2nd Dec: BenQ provides with samples prosumably by 6th Dec. Update 22nd: Sample cradle received.
7 | Vf Zuhause | Check the feasibility of the Vf Zuhause feature implementation in Jerry | B |  | 2005-11-14 | 2005-11-30 |  | Closed | updated 2nd Dec: Ongoing clarification with supplier Infineon, defenitive statement by 15th Dec at the latest.
8 | Autorun | Investigate further the autorun / USB interface for the PC application 24th Nov update: including price related information (USB adapter) | B |  | 2005-11-14 | 2005-11-30 |  | Open | Update 15th Dec: Under Vf internal review.
9 | Battery | Investigate whether the battery supports the cradle use case (memory effect etc.) | B |  | 2005-11-14 | 2005-11-30 |  | Closed | updated 2nd Dec: Clarity with Infineon for final confirmation.
10 | User Experience | Provide high level UE flows / requirements (high level, concept, part of the detailed specs) to BenQ | B |  | 2005-11-14 | 2005-11-15 |  | Closed | UE flows and UE test results sent out by Nancy on 16.11.05 to BenQ Siemens.
11 | User Experience | UE workshop to discuss the high level concept required scheduled on 21st Nov | VF |  | 2005-11-14 | 2005-11-15 |  | Closed | workshop scheduled on 21st Nov
12 | User Experience | Clarify whether centre key is acceptable for Vf | VF |  | 2005-11-14 | 2005-11-18 |  | Closed | Preferred position of centre key communicated by UE Nancy B.
13 | User Experience | Check whether unified message inbox is supported | B |  | 2005-11-14 | 2006-01-15 |  | Open | updated 2nd Dec: Re-opend - final confirmation expected by 8th Dec update 9th Dec: expected mid Jan
14 | User Experience | Provide a kind of prototype / simulator to get insight in the implemented UE | B |  | 2005-11-14 | 2006-01-15 |  | Open | Update 9th Dec: Mid Jan at the earliest expected
15 | User Experience | Provide UE flow charts / screen shots | B |  | 2005-11-14 | 2005-11-18 |  | Closed | Sent on 18th Nov
16 | User Experience | Check the BenQ Siemens text editor in terms of its compliancy | VF |  | 2005-11-14 | 2006-02-17 |  | Open | updated 2nd Dec: Ongoing clarification updated 3rd Feb: Due date revised and agreed during conf call.
17 | User Experience | Provide test results of Simply the user experience testing | VF |  | 2005-11-14 | 2005-11-25 |  | Closed | Sent on 17th Nov.
18 | User Experience | Investigate further the feasibility of 3 ways navigation instead of 5 ways | B |  | 2005-11-14 | 2005-11-23 |  | Closed
19 | User Experience | Provide UE flows on the 3 soft key navigation | B |  | 2005-11-14 | 2005-12-21 |  | Closed | Update 9th Dec: ongoing clarification by BenQ Update 9th Jan: 2 ways navigation agreed on 23rd Dec ID conf call with Roland Aubauer.
20 | ID | Jerry ID to be re-evaluated further in order to differentiate more from BenQ Siemens Polaris (position of hardkeys, on/off key etc.) | B |  | 2005-11-14 | prior to ID workshop |  | Closed | Update 2nd Dec: Monika Reiss to provide Vf with more detailed information why the implementation of 3 hardkeys above the display would blow up the costs.
21 | ID | ID workshop to be organised | B |  | 2005-11-14 | 2005-11-15 |  | Closed | ID workshop scheduled on 8th Dec.
22 | ID | Investigate further a solution for the LED‘s implementation | B |  | 2005-11-14 | 2006-01-09 |  | Open | updated 2nd Dec:Proposal will be provided by Monika Reiss presumably by 6th Dec Update 19th Dec: ongoing clarification
23 | ID | Continue to work on stack up with 3 Simply hardkeys below display | B |  | 2005-11-14 | ongoing |  | Closed
24 | ID | Detailed planning on the ID work | B |  | 2005-11-14 | 2005-11-18 |  | Closed
25 | ID | Provide OpCo feedback on ID to BenQ and the 2 ZIBA designs | B |  | 2005-11-14 | 2005-11-18 |  | Closed | 2 ZIBA designs already shared during the kick-off workshop - OpCo feedback will be provided prosumably Monday 21st Nov.
26 | UE | UE requirement ID 8463: Hide Call History to be confirmed | B | Clemens Lutsch | 2005-11-21 | 2006-01-15 |  | Open | Update 15th Dec: BenQ indicated that UE compliancy feedback will be available by mid Jan 06
27 | UE | UE requirement ID 8154: VF provide help screen text as implementation sample. | VF | Nancy Birkhölzer | 2005-11-21 | 2006-01-15 |  | Open | updated 2nd Dec: ongoing clarification updated 9th Dec: Help is specified as part of the overall flows and will be sent with the package on Monday.
28 | UE | UE requirement ID 8470: Investigate the implementation feasibility of in call volume setting. | B | Clemens Lutsch | 2005-11-21 | 2006-01-15 |  | Open | Update 15th Dec: BenQ indicated that UE compliancy feedback will be available by mid Jan 06
29 | UE | Check in call volume settings with regard to the Vf live! Requirements. | VF | Nancy Birkhölzer | 2005-11-21 | 2005-11-25 |  | Closed | updated 2nd Dec: ongoing clarification updated 9th Dec: when the in call volume is changed while not in a call this should be clearly communicated to the user (text/icon). Alternatively we are willing to look at BenQ's proposal on this topic and will decide based on the proposed Jerry spec.
30 | UE | Provide available BenQ UE specs incl. UE flows and feasibility assessment (feedback on schedule expected by 25th Nov) | B | Clemens Lutsch | 2005-11-21 | 2006-01-15 |  | Open | Update 15th Dec: BenQ indicated that UE compliancy feedback will be available by mid Jan 06
31 | UE | 2. UE workshop to be scheduled on 28th Nov (reviewed information by 25th noon) | VF/B |  | 2005-11-21 | 2005-11-25 |  | Closed | updated 9th Dec: BenQ to propose new date
32 | UE | Selection distinction of content elements to be investigated further. | B | Clemens Lutsch | 2005-11-21 | 2006-01-15 |  | Open | Update 15th Dec: BenQ indicated that UE compliancy feedback will be available by mid Jan 06
33 | UE | Provide information which font size is planned for text entry mode. | B | Clemens Lutsch | 2005-11-21 | 2006-01-15 |  | Open | Update 15th Dec: BenQ indicated that UE compliancy feedback will be available by mid Jan 06
34 | UE | Clarify the T9 version that will be implemented | B | Thomas Bartl | 2005-11-21 | 2005-11-30 |  | Closed | T9 version 6.3 will be implemented
35 | UE | Provide TCP / TPD of voice messaging implementation (n number of received voicemessages) | VF | Florian Pummer | 2005-11-21 | 2005-11-25 |  | Closed | Voice Messaging requirements provided
36 | UE | Simply font to be clarified | VF | Nancy Birkhölzer | 2005-11-21 | end Jan |  | Open | updated 9th Dec: clarification in progress
37 | UE | Which font is currently implemented by BenQ Siemens | B | Clemens Lutsch | 2005-11-21 | 2006-01-15 |  | Open | Update 15th Dec: BenQ indicated that UE compliancy feedback will be available by mid Jan 06
38 | Project Planning | Provide VF Terminal project planning filled out with key milestones (first feedback by 30th Nov) | B | Thomas Bartl | 2005-11-21 | 2005-12-13 |  | Closed | updated 2nd Dec: to be discussed again on 5th Dec between Thomas Bartl and Florian Pummer update 9th Dec: due date revised - 13th morning
39 | UE | Contacts in Menu to be clarified | VF | Nancy Birkhölzer | 2005-11-21 | 2005-11-25 |  | Closed | updated 2nd Dec: ongoing clarification updated 9th Dec: Contacts wont be in the Menu
40 | UE | Vibrate setting in profiles to be clarified | VF | Nancy Birkhölzer | 2005-11-21 | 2005-11-25 |  | Closed | updated 2nd Dec: to be included in final UE specs
41 | UE | SyncML requirement to be clarified / (to be configurable per OpCo) | VF | Florian Pummer | 2005-11-21 |  |  | Closed | Updated 8th Dec: Resolution: SyncML should be configurable per OpCo.
42 | UE | Jerry concept paper update | B | Clemens Lutsch | 2005-11-21 | 2006-01-15 |  | Open | Update 15th Dec: BenQ UE compliancy feedback will be delivered by mid Jan 06
43 | UE | Provide updated Simply Jerry compliance sheet to BenQ | VF | Nancy Birkhölzer | 2005-11-21 | 2005-11-23 |  | Closed | Sent out on 22nd Nov
44 | UE | Provide updated UE flows to BenQ | VF | Nancy Birkhölzer | 2005-11-21 | 2005-11-23 |  | Closed | updated version sent 23.11.05
45 | ID | Provide with detailed information on the issue to position the 3 Simply hardkeys above the display (impact on ID and price). | B | Monika Reiss | 2005-12-02 | 2005-12-06 |  | Closed | raised during 2nd dec conf call
46 | ID | By 12th Dec EOB BenQ will provide Vf with the updated renderings for Pearl II (with final shape/size) and the Polaris Simply version incl. decoration as well as with the 3 Simply hard keys placed above the display. | B | Thomas Bartl / Rudolf Voigt | 2005-12-08 | 2005-12-13 |  | Closed | Update 15th Dec: revised renderings have been provided on 13th Dec.
47 | ID | Gary Vincent to agree the commercial impact of the Simply hardkeys above the display with Chris Frost. | B | Gary Vincent | 2005-12-08 | 2005-12-13 |  | Closed | Update 15th Dec: BenQ analysed additional costs and currently reviewed by Vf. Update 22nd Dec: Due to the decision to move the 3 hard keys below the display the action became obsolete.
48 | ID | BenQ to clarify the technical and project related impact of the 3 Simply hard keys implementation above the display. | B | Thomas Bartl / Monika Reiss | 2005-12-09 | 2005-12-16 |  | Closed | Update 15th Dec: In reference to Gary Vincent the technically feasibility hasn't been completed. Update 22nd Dec: Impact analysis received and currently under evaluation.
49 | TCD | List of third party suppliers for the Jerry software components (i.e. messaging, etc) requested. | B | Thomas Bartl | 2005-12-05 | 2006-01-25 |  | Open | Update 22nd Dec: BenQ committed to provide the information on 22nd Dec. 20th Jan: Action re-opended due to the changed platform.
50 | Project Planning | Double check the understanding of the updated UE flows with Clemens Lutsch so that no open questions are remaining. | B | Thomas Bartl | 2005-12-09 | 2005-12-19 |  | Closed | Update 22nd Dec: Clemens Lutsch confirmed on 21st Dec that the UE flows are understood without any open questions.
51 | Deliverable | Provide with Visual Request Sheet | B | Thomas Bartl | 2005-12-16 | 2006-01-06 |  | Closed | Update 9th Jan: Benq provided with the filled out Visual Customization sheet. Information is based on Goldfinch platform.
52 | Deliverable | Provide with first draft of the visual styleguide | VF | Florian Pummer | 2005-12-16 | end Jan 06 |  | Closed | First draft provided on 27th Jan to BenQ, closing action.
53 | ID | On BenQ to analyze a potential slippage of the ID freeze originally scheduled on 24th Dec in terms of the target launch date by Wednesday 21st Dec. The result of the analysis should include the exact reasons of target launch date slippage, e.g. dependant activities that are scheduled on the critical path. | B | Roland Aubauer / Thomas Bartl | 2005-12-19 | 2005-12-22 |  | Closed | Update 22nd Dec: Feedback received without giving detailed information that justifies the delay. Further information requested from BenQ. Update 20th Jan: Due to the changed platform the overall planning is being revised by BenQ, therefore the indicated 2 weeks delay became obsolete.
54 | ID | On BenQ to provide Vf with the revised renderings by the latest Friday 23rd Dec 10:00am CET. The renderings should include (partially agreed offline between Daniel Schubert and Rudolf Voigt): - Prio 1 -> Option 1 representing the 'S' curve Pearl design with the indicated reduction of the thickness. - Prio 2 -> Option 2 with the projected Pearl design on the Polaris - keypad variants of option 1 with the rocker key function a) up - ok - down, b) ok - up - down and c) up - down only - 1 - 2 variants of option 1 with Vf / BenQ Siemens branding according to the hardware branding guidelines for class A devices | B | Roland Aubauer / Thomas Bartl | 2005-12-19 | 2005-12-23 |  | Closed
55 | ID | On BenQ to confirm the 4th Jan milestone on which it is strived to agree the Jerry ID based on the availability of final mock-ups and renderings by Wednesday 21st Dec | B | Roland Aubauer / Thomas Bartl | 2005-12-19 | 2005-12-22 |  | Closed | Update 22nd Dec: Next ID workshop still be to agreed, 5th Jan proposed by BenQ has not been accepted.
56 | ID | In reference to an still open action assigned on 18th Nov (see attached email) BenQ should ensure that the user experience of the rocker key is not negatively impacted by the taken solution listed in the attached email. Due to the compromise to position the 3 hard keys below the display it is even more important to reduce the complexity by the selected solution: -> Preferred solution with the most efficient reduction of the complexity is option rocker up - down only with the back function implemented in the red key. The other 2 options should be seen as fall back solutions if the rocker up - down only option jeopardizes the launch target date. | B | Roland Aubauer / Thomas Bartl | 2005-12-19 | 2005-12-22 |  | Closed | Update 22nd Dec: Vodafone expressed on 21st Dec conf call that the 2 way navigation is the favored option in comparison with the 3 ways navigation as it reduces the increased complexity of the keypad.
57 | ID | To provide Vodafone with the detailed information about the impact on price and ID if the 3 hard keys would be implemented above the display by Wednesday 21st Dec. | B | Roland Aubauer / Thomas Bartl | 2005-12-19 | 2005-12-22 |  | Closed
58 | Project Management | BenQ to provide with a detailed impact analysis of the changed PCB. BenQ took the decision on 16th Jan to take sgold litet instead of egold radio for Jerry. Content of the assessment: - revised key milestones (TPD, TCD, specs freeze, target launch date etc.) - impact on ID - impact on features (hardware / software) | B | Thomas Bartl | 2006-12-16 | 2006-01-25 |  | Open | Update 20th Jan: Delivery date of impact analysis postponed to 25th Jan. Update 27th Jan: Final assessment on ID due by 30th Jan.
59 | Project Management | Provide revised BenQ project team organisation chart | B | Thomas Bartl | 2006-01-19 | 2006-01-23 |  | Open
60 | Commercial / Project Management | To investigate pre-production / production capacity and ramp-up planning in order to compensate the delay, due by end Feb | B | Monika Reiss | 2006-01-25 | end Feb |  | Open
61 | Project Management | Incorporate the revised key milestones in the Jerry project plan. | B | Monika Reiss | 2006-01-27 | 2006-02-03 |  | Open
62 | TCD | To confirm that BenQ have the correct (197 line) TCD document. | VF | Chris Frost | 2006-02-17 | 2006-02-17 |  | Closed | 21st Feb: Latest version provided to BenQ on 21st Dec 06
63 | ID | Rudolf to forward updated renderings by EOB Feb 17 to allow VF to sign-off | B | Rudolf Voigt | 2006-02-17 | 2006-02-17 |  | Open | 22nd Feb: Final mock-up rendering still not uploaded
64 | ID | Rudolf to investigate moving the key lock 'north' on the side of the design | B | Rudolf Voigt | 2006-02-17 | 2006-02-17 |  | Closed | 21st Feb: Key lock moved to the right hand side again
65 | Project Management | BenQ presentation to be updated in terms of the explanation of acronyms, project experience of the teams | B | Thomas Bartl | 2006-02-22 | 2006-02-28 |  | Open
66 | ID | BenQ to clarify the 3D icon jewel implementation (exact postion in height - z direction, 3D rendering) on the battery door | B | Rudolf Voigt | 2006-02-22 | 2006-02-23 |  | Open
67 | ID | BenQ investigate fall back solution of the keypad backlighting in paralell to the preferred option (white numeric key backlighting and Simply hardkey option a) | B | Thomas Bartl | 2006-02-22 | asap |  | Open
68 | ID | Close open ID issue list by 24th Feb - action plan to be set up (lanyard connector) | B | Thomas Bartl | 2006-02-22 | 2006-02-23 |  | Open
69 | Project Management | Software and Hardware planning of Jerry | B | Thomas Bartl | 2006-02-22 | tbd |  | Open
70 | Project Management | Define the UI based on which the sprint review will be performed (Aries, emulator etc.) | B | Thomas Bartl | 2006-02-22 | 2006-03-08 |  | Open
71 | Project Management | refine and optimize sprint planning via overlapping sprint 1, 2, 3 and introducing sprint 5 which should not include any feature develpopment und should only serve as a bug fixing cycle. | B | Thomas Bartl | 2006-02-22 | 2006-03-01 |  | Open
72 | Project Management | TCD (version 3.3) scheduled on 3rd March should include the UE compliance assessment | B | Thomas Bartl | 2006-02-22 | 2006-03-03 |  | Open
73 | Project Management | Provide with updated UE TCD version | B | Thomas Bartl | 2006-02-22 | 2006-02-23 |  | Open
74 | UE | BenQ to clarify when the help animation needs to be delivered by Vf. | B | Thomas Bartl | 2006-02-22 | 2006-03-01 |  | Open
75 | UE | BenQ to provide Vodafone with the help structure based on which the help animation will be developped. | B |  | 2006-02-22 | end April 06 |  | Open
76 | UE | Provide updated text editor compliance assessment. In case of a non-compliance it is required to describe the current solution, the desired solution and the implementation effort. | B | Clemens Bartl | 2006-02-22 | 2006-03-02 |  | Open
77 | ID / UE | BenQ to provide white illuminated numeric keypad sample (Mars) | B | Thomas Bartl | 2006-02-22 | 2006-02-28 |  | Open
78 | Project Management | 3d Icon jewel to be sent to mock-up manufacturer | V | Florian Pummer | 2006-02-22 | 2006-02-23 |  | Open