## Change History
Jerry Prioritized Feature cluster
History of Change
Version | Date | Editor | Status | Description
1.0_001 | 2006-02-14 | Huang Qian | in work | First draft created during the requirement and feature list workshop.
1.1_000 | 2006-02-20 | Yang Yong Qiang | in review | refined in workshop. Offline review.

## All Features
ID | Feature | Sprint | Timeline | Remark
| Start-up/power on dialogs | sprint 1 | 31.03.2006 | Only PIN input in sprint 1, rest by sprint 3
| Show Startup Assistant | sprint 3 | 31.05.2006
| PC Simu setup | sprint 1 | 31.03.2006
| Idle screen | sprint 1 | 31.03.2006 | Only as VF Simply Styleguide (version 1.5, 02.02.2006) page 5 figure 1.Idle, incl all functional scenario, w/o transition, headline, softkeys effect. Rest by sprint 4
| Home/Contact/Menu hard key invocation | sprint 1 | 31.03.2006
| Phone spaces, color schemes, Icons, Fonts | sprint 1 | 31.03.2006
| Voice call screens basic | sprint 1 | 31.03.2006 | Full functions by sprint 3
| Headline and soft key look and feel | sprint 1 | 31.03.2006
| Menu look and feel basic | sprint 1 | 31.03.2006 | Full compliance by sprint 3
| Remove or hide or disable features | sprint 1 | 31.03.2006
| Tips | sprint 2 | 28.04.2006
| Volume side key, Ringer side key and lock key invocation | sprint 2 | 28.04.2006
| Contact list and menu options (without functionality inside) after pressing Contact hard key | sprint 1 | 31.03.2006 | Full functions by sprint 3
| Screen transitions | sprint 2 | 28.04.2006 | Only sliding effect. Menu and popup selection transitions by sprint 3.
| Unified Inbox (Layout) | sprint 2 | 28.04.2006 | Full functions by sprint 4
| Synchronization including remote sync and sync with SIM | sprint 2 | 28.04.2006
| Key lock screen after switching the key lock hard key. | sprint 3 | 31.05.2006
| Settings | sprint 3 | 31.05.2006 | Ring tong, keypad tone, time/date, display my number, language and change PIN shall be available by sprint 2
| Contact log | sprint 2 | 28.04.2006
| Voice call screens (full functions) | sprint 3 | 31.05.2006
| VF Simply Alarm Clock | sprint 4 | 07.07.2006
| Voice messaging | sprint 3 | 31.05.2006
| Picture messaging | sprint 3 | 31.05.2006
| Message setting | sprint 3 | 31.05.2006
| Inbox UI (all message list) | sprint 3 | 31.05.2006
| menu look and feel - full compliance | sprint 3 | 31.05.2006
| Sleep mode with timer settings | sprint 4 | 07.07.2006
| Hover functionality in Contact list | sprint 4 | 07.07.2006
| Unified Inbox Functionality | sprint 4 | 07.07.2006
| Text message (SMS) | sprint 4 | 07.07.2006
| Idle split screen | sprint 4 | 07.07.2006
| MsgAE | sprint 4 | 07.07.2006
| Templates/Drafts | sprint 4 | 07.07.2006
| Unified sent message | sprint 4 | 07.07.2006
| Delete (All) wizard | sprint 4 | 07.07.2006

## sprint 1
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
ID | Feature | WP = 4 weeks x # resources | # weeks | # resources | #SISL MW | #Beijing MW | responsible site | contact person | Timeline | Dependency | comment
| Identify all text/icon resources and delivery to ResUI team for integration into project database (initially for sprint 1 and 2, and then cover all sprints) |  | 4 | 1 | 4 |  | SISL | Lovleen | sprint 1
| Integration of texts/graphics/fonts into project database (initially for sprint 1 and 2, and then cover all sprints) |  | 4 | 1 |  | 4 | Beijing | Wu Ying Yu | sprint 1
| define Font in UIOS |  | 1 | 1 |  | 1 | Beijing | Lu Qi Wen | sprint 1 | text resources
1 | Start-up/power on dialogs | PIN input, incl. error handling | 4 | 2 | 8 |  | SISL | Rajeev Chauhan | sprint 1 | text resources
|  | Date and Time settings | [6 empty] | sprint 2
| Show Startup Assistant | (TCD-MESG_SIM-990002) At power on, the device shall check EF_MSISDN on the SIM for the presence of an MSISDN. If the field is blank then the device shall prompt the user to "Enter own number"; details of the UI interaction shall be in accordance with the User Experience TCD | 1 | 1 | 1 |  | SISL |  | sprint 2
|  | invoke SyncML and Sync between sim and phone | 1 | 1 | 1 |  | SISL |  | sprint 3
4 | PC Simu setup | 3 hard keys (Home, Contact, Menu) simu, blinking effect for home key | 4 | 1 | 4 |  | SISL | Rajeev Chauhan | sprint 1 | DL
|  | side keys simu | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | sprint 1 | DL
| Idle screen | Refer to VF Simply Styleguide (version 1.5, 02.02.2006) page 5 figure 1.Idle, incl all functional scenario, w/o transition, headline, softkeys effect | 4 | 2 | 8 |  | SISL | Rajeev Chauhan | sprint 1 | text/icon
|  | new event dialog (part of Unified Inbox) | 2 | 1 | 2 |  | SISL |  | sprint 3
|  | Idle UI adaption on network selection | 2 | 1 | 2 |  | SISL |  | sprint 2
|  | show call setting: call barring incoming/outcoming if abroad (new ), effect in Idle | 4 | 1 | 4 |  | SISL |  | sprint 2
|  | TCD-USRX-BAS-008053 Interruption by Events (Partly (nearly not) implemented in X75, needs separate call CSM. (Part 1) Separation of Call functionality from the Idle | 6 | 3 | 18 |  | SISL |  | sprint 4
|  | (Part 2) Call CSM Message Handling | 6 | 3 | 18 |  | SISL |  | sprint 4
|  | (Part 3) Dial Dialog Updation Handling | 4 | 3 | 12 |  | SISL |  | sprint 4
|  | Welcome tour | 1 | 1 | 1 |  | SISL |  | sprint 4
|  | Charging display adaption | 1 | 1 | 1 |  | SISL |  | sprint 4 | text/icon, ApiCore
| Home/Contact/Menu hard key invocation | Invocation of native applications on hard keys press, light effect at home space | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | sprint 1 | UIOS, DL
| Phone spaces, color schemes, Icons, Fonts | color scheme switching interface, define additional virtual colors | 2 | 1 |  | 2 | Beijing | Lu Qi Wen | sprint 1 | text resource
|  | text resource to define color scheme | 1 | 1 |  | 1 | Beijing | Wu Ying Yu | sprint 1
|  | phone space color scheme switching (IDC) | 1 | 1 | 1 |  | SISL | Rajeev Chauhan | sprint 1 | color scheme switching in UIOS
| Voice call screens basic | calling use case: call origination, termination, call setup | 4 | 3 | 12 |  | SISL with Beijing IDC support | Rajeev Chauhan Xu Peng | sprint 1
|  | all call list | 2 | 1 | 2 |  | SISL |  | sprint 3
| Headline and soft key look and feel | UIOS | 4 | 3 | 12 |  | SISL | Rajeev | sprint 1 |  | with support from Beijing
| Menu look and feel basic | look and feel w/o transition effects | 4 | 2 |  | 8 | Beijing | Lu Qi Wen | sprint 1
|  | scroll bar | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | sprint 1
| Remove or hide or disable features | Irda, BT (remove) | 2 | 1 | 2 |  | SISL |  | sprint 2 | PS, connectivity
|  | Camera (remove) | 2 | 1 | 2 |  | SISL |  | sprint 2
|  | MM removing | 2 | 1 |  | 2 | SISL |  | sprint 3
|  | Browser (hide) | 4 | 1 | 4 |  | SISL |  | sprint 2
|  | Java (remove) | 1 | 1 |  | 1 | SISL |  | sprint 1
|  | showing UI notification about accessory from connectivity (disable) | 2 | 1 | 2 |  | SISL |  | sprint 2
|  | DRM (disable) | 4 | 1 |  | 4 | Beijing | Lu Qi Wen | sprint 3
| Preparation for sprint N+1 |  | 4 | 3 | 12 |  | SISL
| Preparation for sprint N+1 |  |  |  |  | 0 | Beijing
| total effort(MW) |  |  |  | 121 | 16
| total effort(MW) |  |  |  |  | 137

## spint 2
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
ID | Feature | WP = 4 weeks x # resources | # weeks | # resources | #SISL MW | #BeijingMW | responsible site | contact person | Timeline | Dependency | comment
| Tips | Tips and sub-menu | 4 | 2 | 8 |  | SISL | Rajeev Chauhan | sprint 2 | resource management
| Volume side key, Ringer side key and lock key invocation | ringer side key in idle | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | sprint 2 | UIOS
|  | volume side key in In-call | 1 | 1 | 1 |  | SISL |  | sprint 2
|  | lock key | 1 | 1 | 1 |  | SISL |  | sprint 2
| Contact list and menu options (without functionality inside) after pressing Contact hard key | list address book | 2 | 2 |  | 4 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 1 | UIOS | might be or start from sprint 1
|  | display menu options with some functions, e.g. copy, delete, add | 3 | 2 |  | 6 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 1 | UIOS | might be or start from sprint 2
|  | contact editor | 4 | 1 |  | 4 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 2 | list address book
|  | merge entry in sim to contact list | 4 | 1 |  | 4 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 2 | list address book
|  | complicated functions: add reminder, sim backup w/o view log | 4 | 2 |  | 8 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 2 | display menu options
|  | launch external appl., e.g. MMS, SMS, call | 2 | 1 |  | 2 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 3 | need interface from other components, i.e. messaging, IDC
|  | PIM settings | 2 | 1 |  | 2 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 3 | display menu options
|  | export inteface (insert contact, select contact) to external appl. i.e. messaging, IDC | 4 | 2 |  | 8 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 3 | list address book
|  | call record look and feel | 4 | 2 |  | 8 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 2 |  | could be started in sprint 1 if resources OK in PIM
| Screen transitions | sliding effect | 4 | 2 |  | 8 | Beijing | Lu Qi Wen | sprint 2
|  | menu selection transition | 4 | 2 |  | 8 | Beijing | Lu Qi Wen | sprint 3
|  | popup transition | 4 | 2 |  | 8 | Beijing | Lu Qi Wen | sprint 3
| Unified Inbox (Layout) | Jerry look and feel of Unified Inbox in SGL functionality w/o MMS | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | sprint 2
| Synchronization including remote sync and sync with SIM | SyncML UI adaption | 4 | 2 | 8 |  | PSE NJ |  | sprint 2 | could start in parallel beginning of Mar
|  | SyncML workflow adaption | 5 | 2 | 10 |  | PSE NJ |  | sprint 2 | could start in parallel beginning of Mar
| customization(mapping, FFS) |  | 2 | 1 |  | 2 | Beijing
| Preparation for sprint N+1 |  | 4 | 3 | 12 |  | SISL
| Preparation for sprint N+1 |  |  |  |  | 0 | Beijing
[5 empty] | 44 | 72
| total effort(MW) |  |  |  |  | 116

## sprint 3
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
ID |  | WP = 4 weeks x # resources | # weeks | # resources | #SISL MW | #Beijing MW | responsible site | contact person | Timeline | Dependency | comment
| Key lock screen after switching the key lock hard key. | implementation of keylock screen | 4 | 1 | 4 |  | SISL |  | sprint 3
| Settings | ring tong, keypad tone, time/date, display my number, language, change PIN | 3 | 2 | 6 |  | SISL |  | sprint 2
|  | Complete settings | 3 | 2 | 6 |  | SISL |  | sprint 3 | AppIDC, PIM, messaging settings
| Contact log | new msg info table support in PIM AE | 4 | 2 |  | 8 | Beijing |  | sprint 2
|  | sorting mechanism | 4 | 1 |  | 4 | Beijing |  | sprint 2
|  | UI implementation in PIM | 4 | 1 |  | 4 | Beijing |  | sprint 2
|  | call record adaption | 4 | 1 |  | 4 | Beijing |  | sprint 2
|  | adaption in messaging | 2 | 1 | 2 |  | SISL |  | sprint 3 | msgAE
| Voice call screens (full functions) | handling different network release codes | 4 | 2 | 8 |  | SISL |  | sprint 3
|  | call reminder | 4 | 1 | 4 |  | SISL |  | sprint 3
|  | in-call menu adaption | 2 | 2 | 4 |  | SISL |  | sprint 3
| VF Simply Alarm Clock | list all alarm events | 4 | 1 |  | 4 | Beijing PIM (to be confirmed by Juergen) | Yi Jing | sprint 3 | list all alarm events | depending on resource situation
|  | time/date editor | 2 | 2 |  | 4 |  |  | sprint 4
|  | alarm text | 1 | 1 |  | 1 |  |  | sprint 4
|  | alarm tone/volume/vibration | 3 | 2 |  | 6 |  |  | sprint 4 | volume adjust from Appbase
|  | menu options in alarm clock, i.e. delete, add | 2 | 2 |  | 4 |  |  | sprint 4
| Voice messaging | view and editor | 9 | 2 | 18 |  | SISL |  | sprint 3
|  | send and receive | 2 | 2 | 4 |  | SISL |  | sprint 3
| Picture messaging |  | 5 | 2 | 10 |  | SISL |  | sprint 3
| Message setting |  | 3 | 1 | 3 |  | SISL |  | sprint 3
| Inbox UI (all message list) |  | 5 | 2 | 10 |  | SISL |  | sprint 3
| menu look and feel - full compliance | UIOS full compliance (incl. progress bar) | 3 | 3 |  | 9 | Beijing |  | sprint 3
|  | VF menu full compliance (incl. progress bar) | 4 | 3 | 12 |  | SISL
| customization(mapping, FFS) |  | 2 | 1 |  | 2 | Beijing
| Preparation for sprint N+1 |  | 4 | 3 | 12 |  | SISL
| Preparation for sprint N+1 |  |  |  |  | 0 | Beijing
[5 empty] | 79 | 39
| total effort (MW) |  |  |  |  | 118

## sprint 4
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
ID | Feature | WP = 4 weeks x # resources | # weeks | # resources | #SISL MW | #BeijingMW | responsible site | contact person | Timeline | Dependency | comment
| Sleep mode with timer settings | back to last screen from where the sleep mode was activated | 4 | 2 | 8 |  | SISL | Rajeev | sprint 4
|  | screen saver handling in idle | 2 | 1 | 2 |  | SISL |  | sprint 4
| Hover functionality in Contact list | UIOS provide this function | 2 | 1 | 2 |  | SISL |  | sprint 4
|  | PIM adaption | 2 | 1 |  | 2 | Beijing |  | sprint 4
|  | messaging adaption | 2 | 1 | 2 |  | SISL |  | sprint 4
| Unified Inbox Functionality | Unified Inbox Functionality | 6 | 2 | 12 |  | SISL |  | sprint 4
|  | welcome tour handling | 3 | 1 | 3 |  | SISL |  | sprint 4 | Idle
| Text message (SMS) | view and editor | 5 | 2 | 10 |  | SISL |  | sprint 4
|  | send and receive | 2 | 2 | 4 |  | SISL |  | sprint 4
| Idle split screen | Idle | 4 | 1 | 4 |  | SISL |  | sprint 4
| MsgAE | get and update msg table from inbox UI/sent msg UI | 4 | 2 | 8 |  | SISL |  | sprint 3
|  | delete msg and delete all | 4 | 1 | 4 |  | SISL |  | sprint 3
|  | sync between msg table in PIM and msg DB in Appmsg | 3 | 2 | 6 |  | SISL |  | sprint 4
|  | SMS/MMS client updation | 2 | 2 | 4 |  | SISL |  | sprint 3
| Templates/Drafts |  | 4 | 2 | 8 |  | SISL |  | sprint 2
| Unified sent message |  | 3 | 2 | 6 |  | SISL |  | sprint 4
| Delete (All) wizard |  | 4 | 2 | 8 |  | SISL |  | sprint 4
| customization(mapping, FFS) |  | 3 | 1 |  | 3 | Beijing | Chai Chun Qian
| Preparation for sprint N+1 |  | 4 | 4 | 16 |  | SISL
| Preparation for sprint N+1 |  | 4 | 1 |  | 4 | Beijing
[5 empty] | 107 | 9
| total effort (MW) |  |  |  |  | 116
| Overall Effort (MW) |  |  |  | 351 | 136
487
4 sprints scheduled for development and unit&integration test. S25 SW freeze would be sprint 4. Full run of System test starts in sprint 5.