## Change History
Jerry Prioritized Feature cluster
History of Change
Version | Date | Editor | Status | Description
1.0_001 | 2006-02-14 | Huang Qian | in work | First draft created during the requirement and feature list workshop.

## Feature cluster priority
No. | Features clusters | Priority
1 | Start-up/power on dialogs | 1
2 | Idle screen basic layout | 1
3 | Home/Contact/Menu hard key invocation | 1
4 | Volume side key, Ringer side key and lock key invocation | 3
5 | Phone spaces, color schemes, Icons, Fonts | 1
6 | Help | 2
7 | Contact list and menu options (Without functionality inside) after pressing Contact hard key | 2
8 | Voice call screens | 1
9 | Key lock screen after switching the key lock hard key. | 3
10 | Sleep mode with timer settings | 4
11 | Headline and soft key look and feel | 1
12 | Sound recorder | 5
13 | Voice messaging | 5
14 | Settings | 3
15 | Delete wizard (basic functionality) | 3
16 | Prompt to store numbers | 5
17 | SMS Viewer and Editor | 3
18 | Screen transitions (Sliding effect) | 2
19 | Menu look and feel | 1
20 | Idle split screen | 2 | shifted after discussion
21 | Picture message | 5
22 | Unified Inbox (Layout) | 2
23 | hover functionality in Contact list | 4
24 | Synchronization including remote sync and sync with SIM | 4
25 | Unified Inbox Functionality | 3
26 | View log | 3
27 | VF Simply Alarm Clock | 5

## Prio 1
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
|  | WP = 4 weeks x # resources | # weeks | # resources | #SISL MW | #BeijingMW | responsible site | contact person | Timeline | Dependency | comment
1 | Create all text/icon resource and integration(initial text for sprint 1 and 2) |  | 4 | 1 | 4 |  | SISL | Lovleen, Wu Ying Yu | sprint 1
1 | Create all text/icon resource and integration(initial text for sprint 1 and 2) |  | 4 | 1 |  | 4 | Beijing | Lovleen, Wu Ying Yu | sprint 1
2 | define Font in UIOS |  | 1 | 1 |  | 1 | Beijing | Lu Qi Wen | sprint 1 | text resources
[5 empty] | 0 | 0
3 | Start-up/power on dialogs | pin iput, incl. error handling | 4 | 2 | 8 |  | SISL | Rajeev Chauhan | sprint 1 | text resources
[5 empty] | 0 | 0
4 | pc simu setup | 3 hard keys(home, contact, menu) simu, blinking effect for home key | 4 | 1 | 4 |  | SISL | Rajeev Chauhan | sprint 1 | DL
|  | side key simu | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | sprint 1 | DL
[5 empty] | 0 | 0
5 | Idle screen basic layout | refer to styleguide page5 1.idle, incl all functional scenario, w/o transition, headline, softkeys effect | 4 | 2 | 8 |  | SISL | Rajeev Chauhan | sprint 1 | text/icon
[5 empty] | 0 | 0
6 | Home/Contact/Menu hard key invocation | invoke of native appl of hard keys, light effect at home space | 2 | 1 | 2 |  | SISL | Rajeev Chauhan | sprint 1 | UIOS
|  |  | 1 | 1 |  | 1 | Beijing | Lu Qi Wen | sprint 1 | DL support
[5 empty] | 0 | 0
7 | Phone spaces, color schemes, Icons, Fonts | color scheme switching interface | 1 | 1 |  | 1 | Beijing | Lu Qi Wen | sprint 1 | text resource
|  | text resource define color scheme | 1 | 1 |  | 1 | Beijing | Wu Ying Yu | sprint 1
|  | phone space color scheme switching(IDC) | 1 | 1 | 1 |  | SISL | Rajeev Chauhan | sprint 1 | clolor scheme switching in UIOS
[5 empty] | 0 | 0
8 | Voice call screens basic | calling use case: call origination, termination, call setup | 4 | 3 | 12 |  | SISL with Beijing IDC support | Rajeeve Chauhan Xu Peng | sprint 1
[5 empty] | 0 | 0
9 | Headline and soft key look and feel | UIOS | 4 | 3 | 12 |  | SISL | Rajeev | sprint 1 |  | with support from Beijing
[5 empty] | 0 | 0 | [5 empty] | \
[5 empty] | 0 | 0
10 | Menu look and feel basic | look and feel w/o transition | 4 | 2 |  | 8 | Beijing | Lu Qi Wen
|  | scroll bar | 2 | 1 | 2 |  | SISL | Rajeev Chauhan
11 | Idle split screen | [7 empty] | sprint 2
| total effort(MW) |  |  |  | 55 | 16
| total effort(MW) |  |  |  |  | 71

## Prio 2
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
|  | WP = 4 weeks x # resources | # weeks | # resources | #SISL MW | #BeijingMW | responsible site | contact person | Timeline | Dependency | comment
6 | Tips | Tips and sub-menu | 4 | 2 | 8 |  | SISL | Rajeev Chauhan |  | resource management
7 | Contact list and menu options (Without functionality inside) after pressing Contact hard key | list address book | 2 | 2 |  | 4 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 1 | UIOS | might be or start from sprint 1
|  | display menu options with some functions, e.g. copy, delete, add | 3 | 2 |  | 6 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 1 | UIOS | might be or start from sprint 2
|  | contact editor | 4 | 1 |  | 4 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 2 | list address book
|  | merge entry in sim to contact list | 4 | 1 |  | 4 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 2 | list address book
|  | complicated functions: add reminder, sim backup w/o view log | 4 | 2 |  | 8 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 2 | display menu options | view log is in unified inbox
|  | launch external appl., e.g. mms, sms, call | 2 | 1 |  | 2 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 3 | need interface from other components, i.e. messaging, IDC
|  | PIM settings | 2 | 1 |  | 2 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 3 | display menu options
|  | export inteface (insert contact, select contact) to external appl. i.e. messaging, IDC | 4 | 2 |  | 8 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 3 | list address book
|  | call record look and feel | 4 | 2 |  | 8 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 2 |  | could be started in sprint 1 if resources OK in PIM
| VF Simply Alarm Clock | list all alarm events | 4 | 1 |  | 4 | Beijing PIM(to be confirmed by Juergen) | Yi Jing | sprint 3 | list all alarm events | depending on resource situation
|  | time/date editor | 2 | 2 |  | 4 |  |  | sprint 4
|  | alarm text | 1 | 1 |  | 1 |  |  | sprint 4
|  | alarm tone/volume/vibration | 3 | 2 |  | 6 |  |  | sprint 4 | volume adjust from Appbase
|  | menu options in alarm clock, i.e. delete, add | 2 | 2 |  | 4 |  |  | sprint 4
18 | Screen transitions | sliding effect | 4 | 2 |  | 8 | Beijing | Lu Qi Wen | sprint 2
|  | menu selection transition | 4 | 2 |  | 8 | Beijing | Lu Qi Wen | sprint 3
|  | popup transition | 4 | 2 |  | 8 | Beijing | Lu Qi Wen | sprint 3
20 | Idle split screen |  |  |  | 0 | 0
22 | Unified Inbox (Layout) | Jerry look and feel of Unified inbox in SGL functionality w/o MMS | 2 | 1 | 2 |  | SISL | Rajeev Chauhan
[5 empty] | 10 | 89
| total effort(MW) |  |  |  |  | 99

## Prio 3
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
| WP = 4 weeks x # resources | # weeks | # resources | #SISL MW | #BeijingMW | responsible site | contact person | Timeline | Dependency | comment
Volume side key, Ringer side key and lock key invocation | ringer side key in idle | 2 | 1 | 2 |  | SISL | Rajeev |  | UIOS
| volume side key in call | 1 | 1 | 1 |  | SISL
| lock key | 1 | 1 | 1 |  | SISL
Key lock screen after switching the key lock hard key. | implementation of keylock screen | 4 | 1 | 4 |  | SISL
Settings |  | 3 | 4 | 12 |  | SISL |  |  | AppIDC, PIM, messaging settings
Delete wizard | delete messages | 1 | 1 | 1 |  | SISL
SMS Viewer and Editor | look & feel adaption |  |  |  | 0
Unified Inbox Functionality |  |  |  |  | 0
View log |  |  |  |  | 0
|  |  |  | 21 | 0
total effort(MW) |  |  |  |  | 21

## Prio 4
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
| WP = 4 weeks x # resources | # weeks | # resources | #SISL MW | #BeijingMW | responsible site | contact person | Timeline | Dependency | comment
Sleep mode with timer settings | back to idle screen, instead of last screen | 2 | 1 | 2 |  | SISL | Rajeev
hover functionality in Contact list | UIOS provide this function, and PIM should be adapted |  |  | 0
Synchronization including remote sync and sync with SIM | SyncML and PIM |  |  | 0
|  |  |  | 2 | 0
total effort(MW) |  |  |  |  | 2

## Prio 5
Working assumption
All clarified Features/requirements would be covered;
Unclear features/requirements would be dropped or implemented as we expect
| WP = 4 weeks x # resources | # weeks | # resources | #SISL MW | #BeijingMW | responsible site | contact person | Timeline | Dependency | comment
Sound recorder |  | 3 | 1 | 3 |  | SISL | Rajeev
Voice messaging
Picture message
|  |  |  | 3 | 0
total effort(MW) |  |  |  |  | 3
Total Total Effort(MW) |  |  |  | 91 | 105
196