## Slide 1: JERRY Project Planning > Software <
Yang Yong Qiang
PL SW
BenQ Mobile, 28.02.2006

## Slide 2: CONTENTS
Resource Profile
Sprint Planning

## Slide 3
BenQ Siemens Jerry –Org Chart per site & function
CPM Koh KhengWah
PL-T Arjen Broeze
PL-T Lars Bonde
PL-T Sara Song
Planning
PL CM/IM/DL
NPI
PL QM
PL MD
ST MO
PE
PL- HW
PL SW Yang YQ
SW Architecture
SW QM
3rd Party: SISL India
TPM Zhang Shuai
System Test
Beijing: Software / UE
Aalborg: HW / Mechanics
Beijing / Shanghai:
Business Operations
UE
LCM 1
Accessory Devices
Variant Management
Customer Care
Application Services
Strategy Procurement
QM
BO PL

## Slide 4
BenQ Siemens Jerry –Org Chart per site & function

## Slide 5: Project organization - Device Layer

## Slide 6: Integration Management support

## Slide 7: Meaning of Acronyms
Organizational
  QA = Quality Assurance
  HW = Hardware
  MD = Mechanical Design
  ST = System Test
  LCM = Lifecycle Management
  NPI = New Products Introduction
Project
  CPM = Category Product Manag.
  PL-T = Technical Project Leader
  TPM = Technical Product Manager
  BA = Business Administration
Technical
  CA = Core Applications
  IM = Integration Management
  BM = Build Management
  CM = Configuration Management
  CIT = Core Integration Team
  CDB = Component Data Base
  IDB = Integration Data Base

## Slide 8: Jerry – Resource Profile
PL-T: Lars Bonde (Aalborg / Denmark)
Experienced leader of ODM projects
  Xelebri GPRS module (developed in France)
  Xelibri X8 (Developed in FIN / DK)
  Luna (Developed in Taiwan)
  Mars CC75 (Developed in Finland)
Technical Project Leader of JERRY in Aalborg - responsible for all work-packages assigned to Aalborg

## Slide 9: Jerry – Resource Profile
PL-MD: Christian P. Nielsen (Aalborg / DK)
Experienced leader of mechanical projects:
  Dual 909, Dual 909S
  Xelibri X3
  Hera Nop1, 2 and 3
  Cormorant
Mechanical project leader of JERRY (in Aalborg)

## Slide 10: Jerry – Resource Profile
PL-HW: Poul Erik Rask (Aalborg / DK)
Experienced technical project leader of ODM projects:
  CL50
  ST55
  ST60
  CFX65
  CL75 (Taiwan)
Hardware project leader of JERRY (in Aalborg)

## Slide 11: Jerry – Resource Profile
PL-IM/DL: Allan Hansen (Aalborg / DK)
Software and Integration Manager of Projects like
  PoC for Ulysses Refresh
  “Next generation software platform”
Project leader Integration Management and Device Layer for JERRY (working in Beijing)

## Slide 12: Jerry – Resource Profile
Part Project Leaders (PPL) working in Aal / DK:
Flemming Kokholm (JERRY: System Test): Venus (ODM), S56 Marlin, Aries, Cormorant
Randi Bak (JERRY: Layout / Production Data): Xelibri X3, Hera, Cormorant
Flemming Bach Kristensen (JERRY: Digital HW): S56, C56, Janus, Venus, Robin, Wolf 4
Arne Bisgaard Kristensen (JERRY: EMC/Ant): Hera C65, C66, C70, C71, Pegasus AX75, AX76, AX72
Michael Brammer (JERRY: RF): HP4000, Dual com 738, World 718, Dual com 439/939, Dual GSM 300, SP55, SX1, Hydra.

## Slide 13: Jerry – Resource Profile
PL SW: Yang Yong Qiang (Beijing, PRC)
More than 9 years in software development Mobile phones and IS-95 CDMA Basestation
Leading Java topics in Beijing R&D Center, BenQ/Siemens Mobile, incl. CLDC HI, DoJa, JSR177
PL SW Dorado and Libra
Software Project Leader of JERRY (in Beijing)

## Slide 14: Jerry – Resource Profile
PL Feature: Hu Chun Yan (Beijing, PRC)
More than 8 years in software development Mobile phones
Leading DoJa Development in Beijing R&D Center, BenQ/Siemens Mobile
Features Project Leader of JERRY (in Beijing)

## Slide 15: Jerry – Resource Profile
BenQ Beijing Development Team
More than 5 years SW development experience on average, with 2 years in BenQ/Siemens Mobile
System Architect:
  Stefan Burkert (coach)
  Chen Mian
Development Team
  Cui Yi (Lead) Lu Qi Wen (SW Arch)
  Song Wen Juan (SW Arch) Yi Xiao Qiang (SE*)
  Zhou Tong (SE*)
  2 local consultants
  -- SE* = Senior Engineer

## Slide 16: Jerry – Resource Profile
SISL PL off-shore: Rajeev Chauhan
More than 11 years in software development and system testing for Mobile phones
UMTS NodeB OAM, transportation systems and protocol development
Leader of the UI development team in India

## Slide 17: Jerry – Resource Profile
SISL Development Team
More than 5 years SW development experience on average
Rajeev Bhatia: Architect AppMsg (messaging)
Sunisha Aggarwal: Architect AppBase/Avatar
Gagan Kashyap: Architect AppBase/AppIDC
25 SW Engineers (with 2 - 11 years experience)

## Slide 18: JERRY – Software Project going AGILE
BACKLOG = list of all tasks to be performed [Ref.: C75-Aries / SGlite SW]

## Slide 19: JERRY – Software Project going AGILE
BACKLOG (continued) [Ref.: C75-Aries / SGlite SW]

## Slide 20: JERRY – Software Project going AGILE
BACKLOG (continued) [Ref.: C75-Aries / SGlite SW]

## Slide 21: JERRY – SW Implementation in Sprints (I.1)

## Slide 22: JERRY – SW Implementation in Sprints (I.2)

## Slide 23: JERRY – SW Implementation in Sprints (I.3)

## Slide 24: JERRY – SW Implementation in Sprints (I.4)

## Slide 25: JERRY – SW Implementation in Sprints (II.1)

## Slide 26: JERRY – SW Implementation in Sprints (II.2)

## Slide 27: JERRY – SW Implementation in Sprints (III.1)

## Slide 28: JERRY – SW Implementation in Sprints (III.2)

## Slide 29: JERRY – SW Implementation in Sprints (III.3)

## Slide 30: JERRY – SW Implementation in Sprints (IV.1)

## Slide 31: JERRY – SW Implementation in Sprints (IV.2)

## Slide 32: Jerry Key Milestones
M0: 23-02-2006
S0: 28-02-2006
M1: 21-03-2006
S15: 25-04-2006
S2/S25: 18-07-2006
S3: 17-08-2006
PS: 02-10-2006
DS: 09-10-2006
Agreed Product Backlog 03 Mar
B1(+) samples to VF: 10 July
Start acceptance tests: 10 July
Global SW approval: 29 Sept
Software Milestones (Agile)
Product Milestones
Sprint 1 + Demo by 03 Apr
VF Feedback by 07 Apr
Sprint 2 + Demo by 04 May
VF Feedback by 11 May
Sprint 3 + Demo by 05 Jun
VF Feedback by 09 Jun
Sprint 4 + Demo by 10 Jul
S25-SW 10 Jul
S3-SW 28 July

## Slide 33: Jerry Vodafone Approval plan (SGL)
VF final
acceptance
start shipment
GCF / TA samples
pre-test
acceptance tests
Final
test
8 weeks
Start Test Phase A
B2 Samples
Start Test Phase B
Start Test Phase C
Start Pre Test
B2 Samples
SW Drop 2
SW Drop 1
SW Drop 3
37
36
38
39
25
27
26
28
29
30
35
34
31
32
33
B1 Samples
10.07.06
SW Drop Pre
S25
S3
40
2.10.06
25.09.06
31.07.06
28.8.06
Bugfix +retest

## Slide 34: Jerry Key Milestones
M0: 23-02-2006
S0: 28-02-2006
M1: 21-03-2006
S15: 25-04-2006
S2/S25: 18-07-2006
S3: 17-08-2006
PS: 02-10-2006
DS: 09-10-2006
= Design Freeze
B1(+) samples to VF: 03 July
Start acceptance tests: 10 July
Global SW approval: 29 Sept
Shipment to Opcos by: 13 Oct
Customer Milestones
Product Milestones

## Slide 35: Jerry Project Plan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
S0
M0
S15
S2
S3
PS
DS
M3/S4
M1
A1
A1+
B1
B2
Ramp-Up
Pilot Run
Design Freeze
Design Work
Hardtool
Plastic Parts B1
Plastic Parts B2
Sprint 1
Sprint 2
Sprint 3
Sprint 4
pc simu setup
Start-up / power on dialogs
Idle screen
Phone spaces, colour schemes, icons, fonts
Voice call screen basic
Menu look and feel basic
Contact list and menu options
Remove or disable or hide features
Startup Ass.
Startup/ power on dialogues
Idle Screen
Contact list & menu options
Screen Trans. (Sliding Effect)
Volume Side, Ringer Side & and lock key
Sync. incl. remote sync.
Settings
View Contact Log
Remove,disable or hide features
Startup Ass.
Idle Screen
Voice call screens full funct.
Voice messaging
MsgAE
Menu look & Feel – full compliance
Contact List & Menu Options
Screen Transitions (Sliding Effect)
View contact log
Remove, disable or hide features
VF Simply Alarm Clock
Idle Screen
Interruption by events
Sleep mode with timer settings
Text messages (SMS)
hover functionality in Contact list
VF Simply Alarm
MsgAE
Hardware
Sprint 1
Approval
by VF
Global SW Approval
Mechanics
Software
Sprint 2
Approval
by VF
Sprint 3
Approval
by VF
Sprint 4 Approval by VF
Pre-Tests
by VF