## Slide 1: Project JERRY Sprint Planning
Yang Yong Qiang
PL SW
BenQ Mobile, 28.02.2006

## Slide 2: CONTENTS
Resource Profile
Sprint Planning
Current Status

## Slide 3: Jerry – Resource Profile
PL SW: Yang Yong Qiang
More than 9 years in software development Mobile phones and IS-95 CDMA Basestation
Leading Java topics in Beijing R&D Center, BenQ/Siemens Mobile, incl. CLDC HI, DoJa, JSR177
PL SW Dorado and Libra

## Slide 4: Jerry – Resource Profile
PL Feature: Hu Chun Yan
More than 8 years in software development Mobile phones
Leading DoJa Development in Beijing R&D Center, BenQ/Siemens Mobile

## Slide 5: Jerry – Resource Profile
BenQ Beijing Development Team
More than 5 years SW development experience on average, with 2 years in BenQ/Siemens Mobile
System Architect:
  Stefan Burkert (coach)
  Chen Mian
Development Team
  Cui Yi (Lead) Lu Qi Wen (SW Arch)
  Song Wen Juan (SW Arch) Yi Xiao Qiang (SE*)
  Zhou Tong (SE*)
  2 local consultants
  -- SE* = Senior Engineer

## Slide 6: Jerry – Resource Profile
SISL PL off-shore: Rajeev Chauhan
More than 11.5 years in software development and system testing for Mobile phones, UMTS NodeB OAM, transportation systems and protocol development

## Slide 7: Jerry – Resource Profile
SISL Development Team
More than 5 years SW development experience on average
Rajeev Bhatia: Architect AppMsg
Sunisha Aggarwal: Architect AppBase/Avatar
Gagan Kashyap: Architect AppBase/AppIDC
25 SW Engineers (with 2 - 11 years experience)

## Slide 8: Jerry - Feature Sprint 1
WP name | Sub-activity | Site | Start | Finish
pc simu setup |  |  | 2/22/2006 | 3/21/2006
 | 3 hard keys simulation including blinking effect for Home key | SISL | 2/22/2006 | 3/21/2006
 | side keys simulation | SISL | 2/22/2006 | 3/7/2006
 | Changes in C_MobSIM for removing/disabling/hiding features | SISL | 2/28/2006 | 3/21/2006
Start-up/power on dialogs |  |  | 2/22/2006 | 3/21/2006
 | PIN input including error handling | SISL | 2/22/2006 | 3/21/2006
Idle screen |  |  | 2/22/2006 | 3/21/2006
 | Idle screen basic layout | SISL | 2/22/2006 | 3/21/2006
 | Home/Contact/Menu hard key invocation | SISL | 2/22/2006 | 3/21/2006

## Slide 9: Jerry - Feature Sprint 1
WP name | Sub-activity | Site | Start | Finish
Phone spaces, color schemes, Icons, Fonts |  |  | 3/6/2006 | 3/17/2006
 | color scheme switching interface, define additional virtual colors | Beijing | 3/6/2006 | 3/17/2006
 | text resource define color scheme | Beijing | 3/6/2006 | 3/13/2006
 | phone space color scheme switching(IDC) | SISL | 3/6/2006 | 3/13/2006
Voice call screen basic |  |  | 2/22/2006 | 3/21/2006
 | call origination, termination, call setup | SISL | 2/22/2006 | 3/21/2006
 | Headline and soft key look and feel | SISL | 2/22/2006 | 3/21/2006
Menu look and feel basic |  |  | 2/22/2006 | 3/21/2006
 | look and feel w/o transition | Beijing | 2/22/2006 | 3/21/2006
 | scroll bar | SISL | 3/6/2006 | 3/17/2006

## Slide 10: Jerry - Feature Sprint 1
WP name | Sub-activity | Site | Start | Finish
Contact list and menu options (Without functionality inside) after pressing Contact hard key |  |  | 3/6/2006 | 3/24/2006
 | list address book | SISL | 3/6/2006 | 3/17/2006
 | display menu options with some functions, e.g. copy, delete, add | SISL | 3/6/2006 | 3/24/2006
Remove or disable or hide features |  |  | 2/22/2006 | 3/31/2006
 | Java (removal) | Beijing | 2/22/2006 | 2/28/2006
 | Development test and Sprint 1 ST | Beijing | 3/29/2006 | 3/31/2006

## Slide 11: Jerry - Feature Sprint 2
WP name | Sub-activity | Site | Start | Finish
Tips including sub-menus |  | SISL | 3/13/2006 | 4/7/2006
Startup Assistant |  |  | 3/13/2006 | 3/17/2006
 | Enter own number | SISL | 3/13/2006 | 3/17/2006
Start-up/power on dialogs |  |  | 3/13/2006 | 3/13/2006
 | date and time setup (covered by Sprint 2 - Settings) | SISL | 3/13/2006 | 
Idle screen |  |  | 3/29/2006 | 4/25/2006
 | Idle UI adaption on network selection | SISL | 4/3/2006 | 4/14/2006
 | show call setting: call barring incoming/outgoing if abroad (new ), effect in Idle | SISL | 3/29/2006 | 4/25/2006

## Slide 12: Jerry - Feature Sprint 2
WP name | Sub-activity | Site | Start | Finish
Contact list and menu options (Without functionality inside) after pressing Contact hard key |  |  | 3/27/2006 | 4/21/2006
 | contact editor | SISL | 3/27/2006 | 4/21/2006
 | merge entry in sim to contact list | SISL | 3/27/2006 | 4/21/2006
 | complicated functions: add reminder, sim backup w/o view log | SISL | 3/27/2006 | 4/21/2006
 | call record look and feel | SISL | 3/27/2006 | 4/21/2006
Volume side key, Ringer side key and lock key invocation |  |  | 3/8/2006 | 4/5/2006
 | ringer side key in idle | SISL | 3/8/2006 | 3/21/2006
 | volume side key in call | SISL | 3/22/2006 | 3/29/2006
 | lock key | SISL | 3/29/2006 | 4/5/2006

## Slide 13: Jerry - Feature Sprint 2
WP name | Sub-activity | Site | Start | Finish
Screen transitions (Sliding effect) |  |  | 3/22/2006 | 4/18/2006
 | sliding effect | Beijing | 3/22/2006 | 4/18/2006
Synchronization including remote sync and sync with SIM |  |  | 2/22/2006 | 3/28/2006
 | SyncML UI adaption | SISL | 2/22/2006 | 3/21/2006
 | SyncML workflow adaption | SISL | 2/22/2006 | 3/28/2006
Settings |  |  | 3/22/2006 | 4/21/2006
 | ring tong, keypad tone, time/date | SISL | 4/3/2006 | 4/21/2006
 | display my number, language, change PIN | SISL | 4/3/2006 | 4/21/2006
 | Templates/Drafts | SISL | 3/27/2006 | 4/21/2006
 | Unified Inbox (Layout) | SISL | 3/22/2006 | 4/4/2006

## Slide 14: Jerry - Feature Sprint 2
WP name | Sub-activity | Site | Start | Finish
View contact log |  |  | 3/27/2006 | 4/21/2006
 | new msg info table support in PIM AE | SISL | 3/27/2006 | 4/21/2006
 | sorting mechanism | SISL | 3/27/2006 | 4/21/2006
 | UI implementation in PIM | SISL | 3/27/2006 | 4/21/2006
 | export interface (insert contact, select contact) to external appl. i.e. messaging, IDC | SISL | 3/27/2006 | 4/21/2006
 | call record adaption | SISL | 3/27/2006 | 4/21/2006

## Slide 15: Jerry - Feature Sprint 2
WP name | Sub-activity | Site | Start | Finish
Remove or disable or hide features |  |  | 3/27/2006 | 4/28/2006
 | Irda, BT (remove) | SISL | 4/3/2006 | 4/14/2006
 | Camera (remove) | SISL | 4/3/2006 | 4/14/2006
 | Browser (hide) | SISL | 3/27/2006 | 4/21/2006
 | showing UI notification about accessory from connectivity (disable) | SISL | 4/3/2006 | 4/14/2006
 | customization | Beijing | 4/10/2006 | 4/21/2006
 | Development test and Sprint 2 ST | Beijing | 4/25/2006 | 4/28/2006

## Slide 16: Jerry - Feature Sprint 3
WP name | Sub-activity | Site | Start | Finish
Key lock screen after switching the key lock hard key. |  | SISL | 4/19/2006 | 5/19/2006
Inbox UI (all message list) |  | SISL | 3/27/2006 | 4/28/2006
Settings complete |  | SISL | 4/24/2006 | 5/17/2006
Startup Assistant | SyncML invocation | SISL | 3/29/2006 | 4/4/2006
Idle screen | new event dialog (part of Unified Inbox) | SISL | 5/8/2006 | 5/19/2006

## Slide 17: Jerry - Feature Sprint 3
WP name | Sub-activity | Site | Start | Finish
Voice call screens full function |  |  |  | 
 | all call list | SISL | 5/8/2006 | 5/19/2006
 | handling different network release codes | SISL | 4/24/2006 | 5/24/2006
 | call reminder | SISL | 4/24/2006 | 5/24/2006
 | in-call menu adaption | SISL | 5/8/2006 | 5/19/2006
Voice messaging |  |  | 3/20/2006 | 5/24/2006
 | view and editor | SISL | 3/20/2006 | 5/24/2006
 | send and receive | SISL | 5/8/2006 | 5/19/2006

## Slide 18: Jerry - Feature Sprint 3
WP name | Sub-activity | Site | Start | Finish
MsgAE |  |  | 4/10/2006 | 5/24/2006
 | get and update msg table from inbox UI/sent msg UI | SISL | 4/10/2006 | 5/10/2006
 | delete msg and delete all | SISL | 4/17/2006 | 5/17/2006
 | SMS/MMS client updation | SISL | 5/4/2006 | 5/17/2006
 | Picture messaging | SISL | 4/24/2006 | 5/24/2006
 | Message Setting | SISL | 4/24/2006 | 5/17/2006
Menu look and feel - full compliance |  |  | 3/22/2006 | 5/12/2006
 | UIOS full compliance (incl. progress bar) | Beijing | 3/22/2006 | 4/11/2006
 | VF menu full compliance (incl. progress bar) | SISL | 4/12/2006 | 5/12/2006

## Slide 19: Jerry - Feature Sprint 3
WP name | Sub-activity | Site | Start | Finish
Contact list and menu options (Without functionality inside) after pressing Contact hard key |  |  | 4/24/2006 | 5/17/2006
 | launch external application, e.g. Voice Messaging, SMS, call | SISL | 4/24/2006 | 5/10/2006
 | PIM settings | SISL | 5/4/2006 | 5/17/2006
Screen transitions (Sliding effect) |  |  | 4/19/2006 | 5/19/2006
 | menu selection transition | Beijing | 4/19/2006 | 5/19/2006
 | popup transition | Beijing | 4/19/2006 | 5/19/2006
View contact log |  |  | 4/24/2006 | 5/10/2006
 | adaption in messaging | SISL | 4/24/2006 | 5/10/2006

## Slide 20: Jerry - Feature Sprint 3
WP name | Sub-activity | Site | Start | Finish
Remove or disable or hide features |  |  | 4/24/2006 | 5/24/2006
 | MM removing | SISL | 5/8/2006 | 5/19/2006
 | DRM (disable) | Beijing | 4/24/2006 | 5/24/2006
VF Simply Alarm Clock |  |  | 4/24/2006 | 5/31/2006
 | list all alarm events | SISL | 4/24/2006 | 5/24/2006
 | customization | Beijing | 5/12/2006 | 5/25/2006
 | Development test and Sprint 3 ST | Beijing | 5/26/2006 | 5/31/2006

## Slide 21: Jerry - Feature Sprint 4
WP name | Sub-activity | Site | Start | Finish
Idle split screen |  | SISL | 6/1/2006 | 6/28/2006
Idle screen |  |  | 3/20/2006 | 6/9/2006
 | Welcome tour | SISL | 6/5/2006 | 6/9/2006
 | Charging display adaption | SISL | 6/5/2006 | 6/9/2006
Interruption by Events |  |  | 3/20/2006 | 5/30/2006
 | Separation of Call functionality from the Idle | SISL | 3/20/2006 | 4/28/2006
 | Call CSM Message Handling | SISL | 4/10/2006 | 5/24/2006
 | Dial Dialog Updation Handling | SISL | 4/28/2006 | 5/30/2006

## Slide 22: Jerry - Feature Sprint 4
WP name | Sub-activity | Site | Start | Finish
Sleep mode with timer settings |  |  | 5/22/2006 | 6/23/2006
 | back to last screen | SISL | 5/22/2006 | 6/16/2006
 | screen saver handling in idle | SISL | 6/12/2006 | 6/23/2006
Text Message (SMS) |  |  | 5/8/2006 | 6/14/2006
 | view and editor | SISL | 5/8/2006 | 6/9/2006
 | send and receive | SISL | 6/1/2006 | 6/14/2006
hover functionality in Contact list |  |  | 5/22/2006 | 6/16/2006
 | Implementation by UIOS | SISL | 5/22/2006 | 6/2/2006
 | PIM Adaption | SISL | 6/5/2006 | 6/16/2006
 | messaging adaption | SISL | 6/5/2006 | 6/16/2006

## Slide 23: Jerry - Feature Sprint 4
WP name | Sub-activity | Site | Start | Finish
VF Simply Alarm Clock |  |  | 5/4/2006 | 6/28/2006
 | time/date editor | SISL | 5/29/2006 | 6/9/2006
 | alarm text | SISL | 5/29/2006 | 6/2/2006
 | Alarm tone/volume/vibration | SISL | 5/29/2006 | 6/16/2006
 | menu options in alarm clock, i.e. delete, add | SISL | 6/1/2006 | 6/14/2006
 | Unified Inbox Functionality | SISL | 5/4/2006 | 6/28/2006
 | Unified sent message | SISL | 5/29/2006 | 6/23/2006
 | Delete (All) wizard | SISL | 5/29/2006 | 6/23/2006

## Slide 24: Jerry - Feature Sprint 4
WP name | Sub-activity | Site | Start | Finish
MsgAE |  |  | 4/24/2006 | 7/28/2006
 | Sync between message table in PIM and message DB in AppMsg | SISL | 4/24/2006 | 5/17/2006
 | customization | Beijing | 6/5/2006 | 6/23/2006
 | Development test and Sprint 4 ST | Beijing | 6/26/2006 | 6/30/2006

## Slide 25: Jerry – Current Status
Database setup done in SISL, Beijing and AAL
Sprint 1 development in progress