## Slide 1: Jerry Kick off workshop Agenda
Lars Bonde, XinJuan Song, Arjen Broeze
2006-02-05

## Slide 2: Preconditions
Project setup (handover timeline preferences) per department agreed (detailed handover planning will be discussed in the workshop) (week 6)
SW estimation finished
Planning for “Work” is determined by SW, HW and ST
Primavera access for all PPLs

## Slide 3: Agenda
Monday 13.02.06
  10:00 – 10:30 Introduction / background (Koh Kheng Wah)
  10:30 – 11:00 Current project setup
    Organisation – Set-up BEJ and AAL – PL-T
    Communication scenarios, mailing lists PL-T
  11:00 – 12:00 Project status
    Status HW/MD/ID – Aalborg – HW-PPL
    Status SW – Beijing – SW-PPL
  12:00 – 13:30 Lunch
  13:30 – 17:00 Define process (tailoring) – Thomas Bartel
    Milestones for HW/SW/ST
    Synchronization points
    Define key activities (must have) for each milestones and nice to have’s (based on MEP 7.02)

## Slide 4: Agenda
Tuesday 14.02.06
  9:00 – 17:00 Work
    Split in 3 main groups: HW, SW and ST
    SW: define work packages, feasibility study, CM scenario, contractors, contracts
    HW: review stack-up concept, mechanical design, layout, part list, suppliers
    ST: HW performance test, TA, Cradle/fixture, Test spec, R&D support

## Slide 5: Agenda
Wednesday 15.02.06
  9:00 – 12:00 Continue with work started on Tuesday
  12:00 – 13:30 Lunch
  13:30 – 17:00 Project planning per department (PL-T)
    Create planning per department and define dependencies
    Input planning in PV

## Slide 6: Agenda
Thursday 16.02.06
  9:00 – 9:30 Prototype shops (LCM1 & 3)
    Define which prototype runs take place where
  9:30-12:00 Create handover planning (PPL)
    Detailed steps
  12:00 – 13:30 Lunch
  13:30 – 16:00 Optimize planning (PL-T)
    Based on input from work-days and dependencies
    Create committed milestone planning
  16:00-17:30 Conclusion (PL-T)
    Identify open action items and plan activities
    How far are we from S0/M1?