## Sheet1
Hardware
| Owner: | [5 empty] | Today: | 2006-02-16
Date:
Week:
ü | Participants:
Notes:
| open | open issue
| info | for information only
| closed | issue closed
| Text | new since last meeting
| Text | weekly issue
| Text | important
No. | Entry Date | Status | Topic | Action Item/decision | Owner | Support | Due Date | Est. Date
1 |  | Closed | HW status | A presentation was given about HW decisions and open questions. Please see the slides "Jerry Kick off workshop HW" There were no objections to the decisions presented. | Poul Erik Rask
2 | 20060213 | Info | Stack up | New stack up was shown based on the latest appearance design (going to be presented to VP this Wednesday). Battery is the Aries 820 mAh battery. The display is turned 180 degree and the connector must be placed at the cut out for the receiver. The distance for the connector-pads to the pcb edge must be checked. We must also find a solution to avoid short circuit of the connector/speaker. | Poul Erik Rask
3 |  | open | Prototype run A1 | A1 is limited to app. 50 pcs to achieve a quick and small series. Samples are basicly for Aalborg engineers. Board outline only 80 to 90% fixed. Maturity to be as B1, except EMC/ESD, audio/acustic, display and Antenna. Should be done in Kamp Lintfort. Pcb should come from AT&S, Austria. | Poul Erik
4 |  | open | Prototype run A1+ | A1+ HW Maturity B1+ except EMC/ESD, audio/acustic, display and antenna Should be done in Kamp Lintfort Pcb should come from AT&S from Austria | Poul Erik
5 |  | open | Prototype run B1 | S2 and S25 is based on B1 series. Should be done in Shanghai. Pcb should come from AT&S from Shanghai | Poul Erik
6 |  | open | Prototype run B2 | Should be done in Shanghai. Pcb should come from AT&S from Shanghai | Poul Erik
7 |  | open | Leadfree | For A1 there will be some few components which are not leadfree. As soon as we have the A1 BOM we will start the conversion work. A1+ is expected to be leadfree | Poul Erik Rask
8 |  | open | Sample plan | Will be worked out/finalized next week by Poul Erik and Jiang | Poul Erik Rask and Jiang
9 |  | Closed | Wingboards | Will not be made for Jerry, instead SW will use modified Aries or Condor wingboard
10 |  | open | Fixtures | A Fixture plan is not started yet. | Flemming Kokholm and Jiang
11 |  | open | Dummy batteries | We will use the existing Aries dummy battery. | Flemming Kokholm
12 |  | open | RFT fixtures | Aalborg BB will take care. | Flemming Bach Kristensen
13 |  | open | Second source qualification | When a correct BOM is available Marian will create a list over possible second source components. When we have a decision, then we will take the second source components in consideration in the prototype planning. Eventual second source qualification will be done in B2 run | Marian and Lars
14 |  | Info | Risk discussion | Some of the known risks were discussed and put into a preliminary Risk List | Poul Erik
15 |  | Closed | Procedures | S15 declaration will be more extensive than normal. S2 and S25 will be based on B1 prototype run. A discussion was made about to reduce or to work out a kind of combined MEP, but we don’t think that we will save any effort in this. Therefore we decided to go for the standard MEP, but with the above mentioned changes.
16 |  | Closed | Working split | Aalborg will be the driver and Beijing the supporter up to B1 tape out. From there on Beijing will be the driver and Aalborg will be the supporter. A1 will mainly be done by Aalborg engineers. When the A1+ testing starts Beijing engineers will come to Aalborg to assist – especially the last two weeks before tape out for B1. More Aalborg/Beijing lines have already planned Aalborg support until end June. This means that Aalborg will declare milestones including S15 and thereafter Beijing will declare the succeeding milestones.
17 |  | open | China production | Is recommended to be done in SSMC, Shanghai. | Lars Bonde
18 |  | open | Access to the coax connector during development | We expect a solution like the Pelican, meaning that there are not access to the RF coax connector on assembled phones We need special rear parts for RF conducted measurements in R&D and also for VF qualification measurements. Must be co-ordinated with ME | Poul Erik
19 |  | open | Access to the coax connector for PQA tests | How can PQA test fully assembled phones? | Thomas Bartel
Note on A15: Click +/- to view/close "Date, # of Meeting, Participants"