## Slide 1: Jerry “Vodafone Simply Exclusive“ PBR Status Report at M0
Kheng-Wah Koh
Category Product Management
Date: 16 Mar 2006
CPM: Kheng-Wah Koh VF Acc PM: Thomas Bartl
TPM: Zhang Shuai (Sean) VF Acc Project Mgr: Monika Reiss
PL-Ts: Lars Bonde VF Acc Sales: Gary Vincent
Arjen Broeze BA: Gao Jie (Gina)
Sara Song

## Slide 2: Quality Gate Rating Jerry 1/2 Status M0
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
Volume: 150k till Jan.15, 2007 committed by VF (contract not
signed) vs. target 450k over lifecycle (used in BC, no
written confirmation by VF)
Sales margin: 7’6 € (=23.9 %) vs.17’6 € (=48.1%) @M alpha
Price: launch 90 € , EOL 65 € , ASP 70.22 €
Profitability
Product Profit Contribution: 6’1 € (=19.2%) vs.14’9 @M alpha
Time to Break-Even: 67% of the PLC
(LC: 12 months; DS: Oct. 2006; Break-even: May. 2007)
Direct R&D cost: 4’5 € = internal cost 9’0 € - VF NRE 4’5 € (based on MS achievement )
Volume risk result in Sales Margin deduction of 0’3 €, PPC deduction of 0’2 €
Strategy Fit
Exclusive for Vodafone Simply
Sales channel: 100% operator
Required in-time DS by VF for the year-end Christmas business
QG
Rating Meeting: Mar.14, 2006 PSO support: Jing Wei

## Slide 3: Quality Gate Rating Jerry 2/2 Status M0
Time-to-Market
M0: Feb.23, 2006 vs. Mar.16, 2006 (actual)
M1: Mar.21, 2006 vs. Mar.31, 2006 (latest plan)
S25/M2: Jul.18, 2006
DS: Sep.22, 2006 (internally); Communicated DS to VF is
Oct.9, 2006, shipment arrival at VF OpCos by Oct.13
S4: Nov.13, 2006
PLT: 30% possibility of 2-weeks-delay based on DS in Sep.
Project Quality
Signatures complete
50% PPLs in BJ site relatively unexperienced as PPLs
Product Quality
Current estimated return rate:
4.5% (SW 1.3 % +HW 3.2 %) vs. 4.5% (target)
No experience with mechanical concept of slider key ,on /off key; MD concept not finalized based on ongoing D FMEA
Transfer of project from AAL to BJ midway through project has risk impact on schedule
Software features not completely fixed
3-4 weeks potential delay in case of MD problems due to missing of 3rd prototype run
Rating Meeting: Mar.14, 2006 PSO support: Jing Wei
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
QG

## Slide 4
  Lifecycle:
  The original lifecycle in M-alpha was from Sept’06 to Aug’07.
  Current lifecycle has been delayed by one month, from Oct’06 to Sept’07, in total 12 months.
  Units:
  450K is an estimation by Vodafone account management.
  Risk: VF will probably commit to only 150K units till Jan 15th 2007. Committed volume to be fixed by final contract early Apr’06.
  ASP:
  Launch Price: 90 Euro; End-of-Life Price: 65 Euro.
  Current Business Case price has already considered the lower price line (15 Euro less per unit, in order to compensate VF’s 4.5 Mio Euro NRE payment.
  HK:
  M-alpha BOM was based on EGR platform and unclear product profile, therefore it is lower than current BOM.
  Current BOM declared by PE is 48.68 Euro. Business Case BOM 49.3 Euro has included variant adder.
  There is a potential NES of 1.2 Euro for Housing.
  Exchange rate EUR/USD = 1.2
  Other PRC:
  Therein 2.4% IPR risk.
  Service cost is 1.66 Euro/unit with 4.5% return rate.
  R&D:
  Total 4’5 Mio Euro budget includes the 4‘5 Mio Eur NRE from VF, and 9 Mio Euro internal direct cost from PMC planning. However, after a close investigation, there is some over-estimation on this 9 Mio Euro, and real efforts should be lower. Update of the budget will be finalized before M1.
  PPC:
  Target PPC was based on M-alpha Business Case.
Analysis DS Business Case
  Break even on Direct R&D in May 2007
Jerry – M0 Business Case

## Slide 5: Risks - Impact vs M0 Business Case

## Slide 6
Measures, Responsibles and Due Dates
Q-gate Axis | Measure | Status | Due Date | Responsible
Strategy Fit | No yellow/red rated items currently. |  |  | 
Sales Fit | Secure NRE and volume commitment by contract asap | Open | Early April | GAM, CPM
Profitability | Investigate on measures to reduce direct R&D cost without impacting TTM | Open | Before M1 | PL-Ts, BA
Product Quality | Finalize remaining sw features clarification with VF. AAL to BJ project handover planning was already made in Feb workshop: Ensure minimal progress impact when project transferred from AAL to BJ by phasing in BJ staff in project asap. Arrange visa and support for BJ staff to station in AAL throughout the whole handover phase. | Open Open | Before M1 April | Arjen, KhengWah K., Thomas Bartl Arjen B., Sara S, Lars B.
TTM | No yellow/red rated items currently. |  |  | 
Project Quality | Provide adequate project training for Beijing PPLs before May | Open | May | PD
Others |  |  |  | 

## Slide 7
Decision Proposals in case of yellow Q-Gate
We propose to Go ahead with the project.
Jerry is part of a “package deal” and is a strategic project with Vodafone.
Sufficient measures for most yellow rated issues are prepared for project to continue.

## Slide 8: Backup

## Slide 9
Special buttons enable user to access the commonly used features easily.
Easy to use User Interface designed to Vodafone Simply specification.
Large display allow the older aged users to view numbers and messages with no difficulty.
Bundled Desktop charger makes experience of charging the mobile as simple and familiar as charging a home cordless phone. Bundled headset enables user to have long conversation comfortably.
CORE CATEGORY: Affordable Quality
CONSUMER SEGMENT: Reassurance, VF’s APU/MB
THEME POSITION: Convenience
Consumer Value prop.
Simplicity – easy to use mobile phone for practical consumers.
Selling prop.
Gender: f/m = 50:50
Age Focus: >40
WE, EE, Australia/NZ
Income: mid
Lifestage: middle-aged, empty nesters
Demo-
graphics
VF’s Adult Personal User (APU): Manage a hectic life and want to be in control. Value driven - cautious money managers who rely on tried and trusted brands
VF’s Mature Basic: Typically older aged, empty nesters
Lifesyle
Target Group (Who)?
Jerry is part of a “package deal” for Vodafone together with Kestrel and Merlin. Support the growth of Vodafone Simply customer base with Jerry.
Strategy &
History
My phone should not be complicated and have too many features that I don’t use frequently.
It should be convenient & contains self-explaining features.
I need a mobile for security/emergencies and family contact, it is not core to my life and I only used it when away from fixed line.
I’m value driven - cautious money managers who rely on tried and trusted brands
I have low technology engagement.
Selling & Value Proposition (What)?
Target Group Benefits (Why)?
Product Story Target Group & Key Product Arguments
Emotional
Functional
Consumer Positioning
Notes: <number>
<footer>
<header>
<date/time>