## Metrics v2.0
"QG@Com MD" Quality Gates Metrics V2
|  | Relevance | [7 empty] | Assessor | Deficiencies
Category | Metrics | Mα | M0 | M1 | M2/S25 | DS | M3/S4 | PBR | OPC |  | prohibitive | major | none minor
[11 empty] | CEO of MD | Head of PBM | PGM
Strategy Fit
Cannibalisation | Cannibalisation with other products in the portfolio | x | x | x | - | - | - | PBR |  | PM / RPM | strong cannibalization effects | modest cannibalization effects | weak cannibalization effects
Congruence | Deviations to defined Window of Opportunity | x | x | x | o1) | o | o | PBR |  | PM | low fit, major deviations in more than one category | modest fit, change in only one category | strong fit
| Fit to defined untouchables features and portfolio differentiators | x | x | x | o1) | o | o | PBR | OPC | PM | low fit, key features changed | modest fit | strong fit
| Fit / buffer of the Enthusiasm features | x | x | x | o1) | o | o | PBR |  | TM | more than 1 competitors will adress E-feature at launch time or 1 competitor will adress it earlier | one competitor will adress E-feature at launch time or up to 4 months later | no competitor will fulfill the E-feauture within 4 months after launch | not aligned yet with TM, until then use PM
Quality of strategy | Did we choose the right strategy for the product? (Does the Enthusiasm Model have the right profile?) | - | x | x | o | o | o | PBR |  | CM / RPM | strong weaknesses | modest weaknesses | none or minor weaknesses
VAS product portfolio | If accessories are important for the product story: Are the accessessories available? | x | x | x | - | - | - | PBR |  | CPM | no | yes, but only me-too accessories | yes, with USP
Design acceptance test | Consumer feedback | - | x | x | - | - | - | PBR |  | CMM | negative/ rejected | neutral | positive
Sales Fit
Basis of customer feedback | Product presented to the most important tier1 customers/retailers per area? | - | - | x | o | o | - | PBR |  | RPM | no rating, for information, only
Minimum operator requirements | Are the minimum operator feature and customisation requirements met to ensure the sell-in? (not rated if product has pure retail focus) | x | x | x | o | o | o | PBR |  | RPM | rejected, inacceptable | average | positive
Minimum retail requirements | Are the minimum reatail requirements met to ensure the sell-in? (not rated if product has pure operator focus) | x | x | x | o | o | o | PBR |  | RPM | rejected, inacceptable | average | positive
Regional feedback | about design, size, feature set, USP to ensure the sell-out | x | x | x | o | o | o | PBR |  | RPM | rejected, inacceptable | average | positive
Sales margin deviation | Sales margin deviation of RPM price/volume feedback vs. BC | x | x | - | - | - | - | PBR |  | BA | > 25% | 25% < x < 15% | < 15%
| Sales margin deviation of current ROF/priceline vs. M1 commitment | - | - | - | o | o | o | PBR |  | BA | > 25% | 25% < x < 15% | < 15%
Marketing | Concept fit Fit of the current product definition to the marketing positioning | x | x | x | o | o | o | PBR |  | CMM | low fit | modest fit | strong fit
| Concept perception | x | x | x | x | - | - | PBR |  | CPM | concept is unclear, contradictory or does not support the product strategy | parts of the concept are unclear | concept is convincing
| Budget: Increasing or decreasing the marketing budget would ... | x | x | x | x | x | x | PBR |  | CPM | ...significantly improve the business case (budget is wrong) | ... not effect the business case (the effect of additional budget is equal to the costs) | ... significantly decrease the business case (budget is ok)
Time-to-market
Delivery start (DS) | vs. Mα | - | x | - | - | - | - | PBR | OPC | PSO | > 2 months or confidence level <90% | 1 - 2 months | < 1 month
based on not best-case but on most probable (>=90%) timeschedule | delay of DS vs. M0 | - | - | x | - | - | - | PBR | OPC | PSO | > 1 months or confidence level <90% | 3 - 4 weeks | < 3 week
| vs. M12) | - | - | - | x | o | - | PBR | OPC | PSO | > 2 weeks or confidence level <90% | 1 - 2 weeks | < 1 week
Allocation | Can we produce as many units as required by the customer? Shortage in production capacity in % for the ramp-up phase. (Production capacity VKL + free capacity in ramp-up plan compared to sales forecast in i2 + BTO + BTS. Material availability has been taken into account) | - | - | - | x | x | - | PBR | OPC | TPM | >20% shortage | 5 - 20% shortage | <5% shortage
Product Quality
Platform | Hardware platform (i.e. predevelopments, components) | x | x | x | x | - | x | PBR | OPC | QM
| Software platform | x | x | x | x | - | x |  |  | QM
Software | Software | - | x | x | x | x | x | PBR | OPC | QM
(inhouse) | Signal processing Software | - | x | x | x | x | x |  |  | QM
RF | Radio | - | x | x | x | x | x | PBR | OPC | QM
| EMC / Antenna | - | x | x | x | x | x |  |  | QM
Hardware | Digital & mixed signal HW | - | x | x | x | x | x | PBR | OPC | QM
| Layout / production data | - | x | x | x | x | x |  |  | QM
Mechanics |  | - | x | x | x | x | x | PBR | OPC | QM
Procurement Engineering | Global procurement | x | x | x | - | - | x | PBR | OPC | QM
Systemtest | Systemtest | - | x | x | x | x | x | PBR | OPC | QM
Overall Product Quality | Quality (excluding staffing & planning) | x | x | x | x | x | x | PBR | OPC | QM
| Quality System Efficiency | - | x | - | x | x | x |  |  | QM
Production Process | Material availability | - | x | x | x | x | x | PBR | OPC | QM / SCM | prohibitive deviations acc. to SCM QM | major deviations acc. to QM / SCM QM | none/minor deviations acc. to QM / SCM QM
| Production technology (SCM) | x | x | x | x | x | x |  |  | QM / SCM | prohibitive deviations acc. to SCM QM | major deviations acc. to QM / SCM QM | none/minor deviations acc. to QM / SCM QM
Classification of metrics based on detailed checklists of MD's Milestone Development Plan ( MEP V7 )
Project Quality
Availability of Signatures | Has the milestone declaration according to MEP been signed by all relevant faculties? | x | x | x | x | x | x | PBR | OPC | CPM | signature of one or more faculties missing | signature of one or more faculties currently unavailable but contentwise agreed upon (formal deviation) | all signatures available
Estimation workshops | SW Estimation workshops; Based on Delphi method for project specific software workpackages | - | x | x | - | - | - |  | OPC | QM (QPM SW) | ./. | none | max. some not
Risk management plan | Permanent risk analysis, early warnings and preventive actions (for the whole team) | - | x | x | x | o | o |  | OPC | QM | no plan | incomplete | complete and reliable
Staffing of PLs | All PL roles covered | x | x | x | x | o | - | PBR | OPC | CPM TPM | important roles not covered | partly incomplete | complete (skills might not be sufficient)
Skills of PLs | SPM, Realization Manager, Product Champion, PL-T, PL SCM and PL SW have sufficient skills for the appropriate PL levels | o | o | o | - | - | - |  | OPC | PSO | SPM or PL-T are neither certified nor have they successfully completed 2 product projects | PLs are not certified | all PLs are certified
Quality of project plan | Is everything included? Appropriate workpackages, all dependencies included and checked in Primavera | - | x3) | x | - | - | - |  | OPC | TPM | insufficient | incomplete | complete, but maybe not agreed
Main dependencies with other projects | Are there main dependencies with other projects (e.g. platform, lead projects) that will influence time to market, costs, quality, resources, time to volume) | x | x | x | x | x |  | PBR | OPC | CPM/ TPM | main dependencies and changes from other projects will have direct influence | main dependencies, but effects from other projects can be handled | no dependencies or main dependencies, but no negative input on the project is expected
Formal quality of project plan | E.g. activities ... - w/o assigned resources - assignments > 8h/day - w/o predecessor or successor - that are overdue | - | x | x | x | o | - | PBR | OPC | PL- Coord | insufficient | major constraints | max. minor constraints
Ressource overload | Total load on resources planed for this project | - | x | x | x | o | - | PBR | OPC | PL- Coord | 3 months or more of the next 12 months show >20% overload | 1 or 2 months of the next 12 months show >20% overload | 0 of the next 12 months show >20% overload
Tracking & Reporting | of critical path in Primavera | - | - | x | x | o | - | PBR | OPC | PL- Coord | not at all | sporadic | weekly
Profitability
Product Profit Contribution Deviation | Negative deviation from absolute target vs. Malpha target | - | x | x | - | - | - | PBR |  | BA | > 20% | 5 - 20% | < 5 %
| vs. final M1 target | - | - | - | x | o | o |  |  | BA | > 20% | 5 - 20% | < 5%
Time to Break-Even on direct R&D | Duration from Launch date to Break-Even date (on direct R&D) | x | x | x | - | - | - | PBR |  | BA | > 100% of PLC duration ( Break even will not be reached) | 75% - 100% of PLC duration ( for 12 m. PLC 10 - 12 m.) | < 75% of PLC duration ( for 12 m. PLC < 9 m.)
Total risk impact | (Target - BC + sum of weighted single risks) / M-alpha target | - | x | x | - | - | - | PBR |  | BA | > 25% | 10 - 25% | < 10 %
| (…) / M1 target | - | - | - | x | o | o
| BoM risk | - | x | x | x | o | o | PBR |  | SP | Impact incorporated and evaluated in Risk Analysis Calculation of weighted impact per risk = Financial impact (100%) x probability (<50%)
| Price risk | - | x | x | x | o | o | PBR |  | RPM
| Volume risk derived from RPM estimations/ROF vs. BC | - | x | x | x | o | o | PBR |  | RPM
| TTM risk (probability <10%) in weeks | - | x | x | x | - | - | PBR |  | TPM
Cost Deviation | R&D Effort: Direct cost over lifecycle M0 vs. Malpha | - | x | - | - | - | - |  | OPC | TPM BA | > 50% | 25 - 50% | < 25%
| M1 vs. S0 | - | - | x | - | - | - |  |  | TPM BA | > 25% | 10 - 25% | < 10%
| vs. M1 | - | - | - | x | x | x |  |  | TPM BA
| HK M0 vs. Malpha | - | x | - | - | - | - |  | OPC | TPM BA | > 5,0% | 2,5 - 5,0% | < 2,5%
| M1 vs. S0 | - | - | x | - | - | - |  |  | TPM BA
| vs. M1 | - | - | - | x | x | x |  |  | TPM BA
Footnotes: | 1) relevance for a milestone:
"x": assessment and relevant for decision
"o": assessment for performance monitoring reasons but not relevant for decision
"-": no assessment, not relevant for decision
2) ... or vs. the current roadmap launch date, if it differs from the M1 target
3) Detailed plan until M1, rough plan M1-M3
Abbreviations: | BA: Business Administration
BC: Business Case
EMC: Electromagnetic Compatibility
HW: Hardware
HR: Human Resources
Mech: Mechanics
CMM: Marketing Manager
R&D: Research & Development
CM: Category Manager
PL-Coord.: Primavera Planning Coordinator
TM: Theme Manager
TPM: Technical Project Manager
QG: Quality Gate
QM: Quality Management, stands for the quality project leader
RF: Radio Frequency
RPM: Regional Product Manager
SCM: Supply Chain Management Devices, stands for the SCM Q Team member.
ST: System test
SW: Software
Milestone declaration recommended or at least possible
Action items in case of deviations to be tracked by SPM.
Milestone declaration not signed by QM.
Milestone declaration blocked.
State of emergency. Most strictly follow-up.
Major deviation according to conformance assessment of QM.
Copyright (C) Siemens AG – COM MD 2005 All Rights Reserved - Confidential

## Rating sheet
Q-Gate Rating |  |  |  | Rating Meeting: | Mar.14,2006
|  |  |  | Moderation: | Jing Wei
Jerry | M0 |  |  | [ conclusion
| Assessor | Depart. |  | Comment | Measure | Resp. | Due date
Strategy Fit |  |  | 3 |  |  |  |  | Legend:
Cannibalisation | PDM:Karine Ratsimbazafy / kheng Wah; VF: Stefan Hanika | PM RPM | 3 | - PDM: no concern from Karine, Exclusive for Vodafone Simply - VF GAM:Green |  |  |  | prohibitive | 1
Congruence | kheng Wah | PM | 3 | - WoO: Vodafone has requested DS for their year-end Christmas business - Untouchables: - E-feature buffer: |  |  |  | major | 2
Quality of strategy | PDM:Karine Ratsimbazafy / kheng Wah; VF: Stefan Hanika | CM RPM | 3 | - PGM: no concern from Karine - VF GAM: green |  |  |  | none/minor | 3
VAS product portfolio | Shuai Zhang | TPM | 3 | Reuse headset,charger, carkit.
Design Acceptance Test |  | CMM | ./.
Sales Fit |  |  | 2
Basis of Customer Feedback | Person |  | ./.
Minimum Operator Requirements | VF: Stefan Hanika | GAM | 3 | - VF GAM: Green - PM: Fulfill Vodafone Simply requirements
Minimum Retail Requirements |  | GAM | ./.
Regional Feedback | VF: Stefan Hanika | GAM | 3 | - VF GAM:Green
Sales Margin Deviation | Gao Jie | BA | 2 | - In total: 7’6 € (=23.9 %) vs.17’6 €(=48.1%) @M alpha
Marketing |  | CMM CPM | ./. | - concept fit: - concept perception - budget:
Time-to-market |  |  | 3
Delivery Start | Person | PSO | 3 | --> DS deviation: 0 weeks in PV currently @M0 plan: M0: Feb.23 vs.Mar.16 as planned M1: Mar.21 shift to Mar.31 S25/M2: Jul.18 DS: Sep.22, 2006 (internally); Communicated DS to VF is Oct.9, 2006, shipment arrival at VF OpCos by Oct.13 S4: Nov.13
Allocation |  |  | ./.
Product Quality |  |  | 2 | Current Return Rate estimation: 4,5 % (SW 1,3 % +HW 3,2 %)
Platform | Person | QM | 3
Software | Person | QM | 2 | SW requirements with VF not yet completely clarified | clarify features with VF | A. Broeze | Mar.21
RF, EMC, Antenna | Person | QM | 2 | Antenna mockup 2 is depending on FDM parts to be delivered by end of March from MD. MD stack up concept is not finalized yet and due to workload and late FMEAs (March 21-23) there is a risk for late delivery | MD provides FDM parts | C.Nielsen | Mar.27
Hardware | Person | QM | 2 | Open, Acoustic sealing, eg. ON/OFF button, not clarified. Hall sensor placement & the distance the magnet can move, not clarified. | Finalize MD concept | C.Nielsen P. Erik Rask
Mechanics | Person | QM | 2 | On/off key possible problems (damaged microswitches during drops, malfunction due to tolerances) Potential acoustical leakage on speaker/back volume (concept not yet finalized) Slighter key (keypad lock) possible problems (slider breakage during drop test, un-intended activation due to external magnetic force, activated in pocket due to low activation force, unstable function due to magnetic tolerance) Function keys possible problems (poor tactile feeling due to clicked keys, light leakage around the decoration part) Uneven light illumination/distribution on simply keys | Perform DFMEAs and define corrective actions & timeline | C. Nielsen
Procurement Engineering | Person | QM | 2 | Keypad suppliers not yet choosen |  |  | Mar.17
System Test | Person | QM | 3
Overall product quality | Person | QM | 2
Production Process | Person | QM/SCM | 2 | Assembly concept is missing Draft SD production process flow is missing Productions risks: - (VF logo on battery cover: misalignment of logo in the case of in-house assembly, - Alps Microswitch for On/Off key: SIPLACE accuracy is not suitable to use the component with taps -> has to be considered for the component selection (version with and without tap available), - Tape on earpiece: required due to display rotation by 180°, additional assembly steps lead to increased costs, lack of tape possible | # planned for S0 # planned for S0 to be clarified with VF and internal alignment | A.Broeze/C. Nielsen
Project Quality |  |  | 2
Availability of Signatures | Person | CPM/ TPM | 3 | The team declared <milestone> on <date>, complete
Main dependencies with other projects | Person | CPM/ TPM | 3 | No dependence with other platform and projects
Estimation workshops | Person | QM | ./.
Risk management plan | Person | QM | 3
Staffing of PLs | Person | CPM/ TPM | 3 | all PPLs nominated
Skills of PLs | Person | PSO | 2 | 50% PPLs unexperienced in BJ
Quality of project plan | Person | TPM | 3
Formal quality of project plan | Person | PL-Coord | 3
Resource Overload | Person | PL-Coord | 2 | In Primavera most AAL resource on Jerry are overload more than 100%
Tracking & Reporting | Person | PL-Coord | ./.
Profitability |  |  | 2
Product Profit Contribution | Person | BA | 2 | 6'1€ (=19.2%, current) vs. 14'9 (=40.5%) @M alpha --> deviation: z%; Direct R&D cost: 4’5 € = internal cost 9’0 € - VF NRE 4’5 € (based on MS achievement ) -> 6'8EUR of R&D in PMC,2'2EUR CC/SCM internal service 2' EUR for consultant cost 758k EUR (2.4% of TO) for IPR (Jerry:Class 3)
Time to Break-Even | Person | BA | 2 | 67% of the PLC duration(LC:12m，DS: Oct,2006; Break-Even: May,2007)
Total Risk Impact | Person | BA | 2 | Absolute delta value: Volume risk result in Sales Margin deduction of 0’3 €,PPC deduction of 0’2 € BoM risk (PE) : No mentioned. Current BoM 49.33 including variant adder Price risk (RPM) - 70.22€ ASP, 90€ launch price, 65€ EOL Volume risk (RPM) 18k volume risk due to every two weeks delay from goods in VF warehouse (Mid of Oct.,2006) 150k till Jan.15,2007 committed by VF(contract not signed) vs. target 450k over lifecycle (used in BC) TTM risk (PL-T): 30% about 2 weeks delay(based on DS in Sep)
Cost deviation | Person | TPM BA | 2 | R&D effort: 4'5 EUR for direct R&D cost vs.6'5 @Malpha HK: 24'0 EUR (=76.1% of TO) 53.4 per unit vs.42.3 @Malpha
Legend:
| prohibitive | 1
| major | 2
| none/minor | 3

## RT Comments
<Product> Round Table, <date> | [5 empty] | Moderation: <name>
Department | Participant | AIs to close | Sign. possible | Sign. given | Sig. Target | Current Status
GPM | [5 empty] | Blocking points: - Other issues: -
SM | [5 empty] | Blocking points: - Other issues: -
AS | [5 empty] | Blocking points: - Other issues: -
BA | [5 empty] | Blocking points: - Other issues: -
BO | [5 empty] | Blocking points: - Other issues: -
PE | [5 empty] | Blocking points: - Other issues: -
Sales | [5 empty] | Blocking points: - Other issues: -
SCM | [5 empty] | Blocking points: - Other issues: -
PD | [5 empty] | Blocking points: - Other issues: -
QM | [5 empty] | Blocking points: - Other issues: -
CC | [5 empty] | Blocking points: - Other issues: -
AD | [5 empty] | Blocking points: - Other issues: -
PM | [5 empty] | Blocking points: - Other issues: -
PBM | [5 empty] | Blocking points: - Other issues: -
Note on C2: I confirm that there are no concerns in form and content prohibiting the milestone declaration / affirmation if all action items are successfully completed
Note on D2: I confirm that there are no concerns in form and content prohibiting milestone declaration/affirmation
Note on E2: Signature was already given
Note on F2: Target due date for signature

## RT AI
| <Product> Action Items, <date> | Moderation: <name>
# | Action Item Description | Responsible | Due date | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
AI overdue
AI closed

## Version Control
Included in version | Changed on | Changed by | Description | Reason | Requester | Aligned with
2.02 | 2006-03-02 | Assan | "Minimum operator requirements" replaced by "Minimum operator / retail requirements" | for products with strong retail focus, operator reuqirements have only low relevance | Ulirke Lohbrunner, Andreas Betsch | Ulirke Lohbrunner, Andreas Betsch
2.02 | 2006-03-02 | Assan | Assessors in strategy fit adapted to new roles: mainly PDM -> PM | PDM role no longer exists | Marcell Assan | Karine Ratsimbazafy, Marco Mildenberger
2.02 | 2006-03-02 | Assan | TPM BA metrics included | split in PH and CM part for Q-Gates | Marcell Assan | Byrne Wilson
2.02 | 2006-03-02 | Assan | Assignment to PBR and PH | split in PH and CM part for Q-Gates | Marcell Assan
2.02 | 2006-03-02 | Assan | Profitability metrics adapted to Product Profit contribution | switch from EBIT to Product Profit Contribution | Roland Schmidt | Roland Schmidt