## Spec. Timeline
Jerry MMI Specification Delivery Plan
S. No. | Topic | SW Sprint | MMI Spec Release | Date
1 | Content |  |  | .
2 | Overview |  |  | .
2.1 | 3 Hard Keys (Home, Contacts, Menu) | 1 | 1 | 2006-03-03
2.2 | Blinking Indicator | 1 | 1 | 2006-03-03
2.3 | Volume Key handling | 2 | 3 | 2006-03-31
2.4 | Ringer Key Concept | 2 | 3 | 2006-03-31
2.5 | Lock Key Concept | 2 | 3 | 2006-03-31
3 | Text Design Spec (Layout and Textdefines) |  |  | .
4 | Idle |  |  | .
4.1 | Idle Overview |  |  | .
4.2 | Switching On&Off | 1 | 1 | 2006-03-03
4.3 | Startup Procedures | 1 | 1 | 2006-03-03
4.4 | Shutdown Procedure |  | 3 | 2006-03-31
4.5 | General Behavior |  | 3 | 2006-03-31
4.6 | Idl_Operation_wo_SIM.vsd | 1 | 1 | 2006-03-03
4.7 | Keylock | 3 | 5 | 2006-04-25
4.8 | Idle Events / Info-Prompt | 3 | 5 | 2006-04-25
4.8.1 | Info Prompt - Basic layout | 2 | 2 | 2006-03-15
4.8.2 | Info Prompt - Detailed flows for events |  | 6 | 2006-05-15
4.8.2.1 | Events - Missed Calls | 4 | 6 | 2006-05-15
4.8.2.2 | Events - Text Message | 4 | 6 | 2006-05-15
4.8.2.3 | Events - Voice Message | 4 | 6 | 2006-05-15
4.8.2.4 | Events - Voice Mail | 4 | 6 | 2006-05-15
4.8.2.5 | Events - Picture Message | 4 | 6 | 2006-05-15
4.8.2.6 | Events - Reminders | 4 | 6 | 2006-05-15
4.8.2.7 | Events - Alarms | 4 | 6 | 2006-05-15
4.8.2.8 | Events - Welcome Tour | 4 | 6 | 2006-05-15
4.8.3 | Own number prompt on startup | 2 | 2 | 2006-03-15
4.8.4 | Network Selection | 2 | 3 | 2006-03-31
4.8.5 | Call Barring if abroad-Efect on Idle | 2 | 2 | 2006-03-15
5 | Call Handling |  |  | .
5.1 | Calls - Basic MO / MT | 1 | 1 | 2006-03-03
5.2 | Calls- Advanced | 3 | 5 | 2006-04-25
5.3 | All Calls - Call Log | 3 | 5 | 2006-04-25
5.4 | Handling of network release codes | 3 | 5 | 2006-04-25
5.5 | Call reminder | 3 | 5 | 2006-04-25
5.6 | Call Alerts - Different Ringer Modes | 3 | 5 | 2006-04-25
6 | Menu |  |  | .
6.1 | Main Menu |  | 3 | 2006-03-31
7 | Contacts |  |  | .
7.1 | Contacts List | 1 | 1 | 2006-03-03
7.2 | Contact List Options | 1 | 1 | 2006-03-03
7.3 | Contact Editor | 2 | 3 | 2006-03-31
7.4 | Contact Log | 3 | 5 | 2006-04-25
7.5 | Reminders | 2 | 3 | 2006-03-31
7.6 | SIM Backup | 2 | 3 | 2006-03-31
7.7 | Interface to SMS, MMS, Call | 3 | 5 | 2006-04-25
7.8 | Contact Settings | 3 | 5 | 2006-04-25
7.9 | Contact Deletion | 3 | 5 | 2006-04-25
7.10 | Contact Synchronization | 3 | 5 | 2006-04-25
8 | Messaging |  |  | .
8.1 | Unified inbox | 3 | 5 | 2006-04-25
8.2 | Unified Inbox Details | 3 | 5 | 2006-04-25
8.3 | Text Message (SMS) |  |  | .
8.3.1 | SMS - View | 4 | 6 | 2006-05-15
8.3.2 | SMS - Editor | 4 | 6 | 2006-05-15
8.3.3 | SMS - Send | 4 | 7 | 2006-05-30
8.3.4 | SMS - Receive | 4 | 7 | 2006-05-30
8.4 | Voice Message |  |  | .
8.4.1 | Voice Msg - View | 3 | 2 | 2006-03-15
8.4.2 | Voice Msg - Editor | 3 | 2 | 2006-03-15
8.4.3 | Voice Msg - Send | 3 | 5 | 2006-04-25
8.4.4 | Voice Msg - Receive | 3 | 5 | 2006-04-25
8.5 | Picture Message
8.5.1 | Picture Message - Receive | 3 | 4 | 2006-04-10
8.5.2 | Picture Message - Forward | 3 | 4 | 2006-04-10
8.6 | Delete Msg & Delete All | 3 | 5 | 2006-04-25
8.7 | Templates & Drafts | 2 | 3 | 2006-03-31
8.8 | Unified Sent Box | 4 | 7 | 2006-05-30
8.9 | USSD | 4 | 7 | 2006-05-30
8.10 | Cell Broadcast | 4 | 7 | 2006-05-30
9 | Tips
9.1 | Tips Menu/List | 2 | 3 | 2006-03-31
9.2 | All Tips Screens
9.2.1 | Phone Basics | 2 | 3 | 2006-03-31
9.2.2 | Call Tips | 2 | 3 | 2006-03-31
9.2.3 | Message Tips | 2 | 3 | 2006-03-31
9.2.4 | Contacts Tips | 2 | 3 | 2006-03-31
9.2.5 | Events & Alerts Tips | 2 | 3 | 2006-03-31
9.2.6 | Manage Content on PC | 2 | 3 | 2006-03-31
9.2.7 | International Tips | 2 | 3 | 2006-03-31
9.2.8 | Accessories | 2 | 3 | 2006-03-31
9.2.9 | Settings Tips | 2 | 3 | 2006-03-31
9.3 | Welcome tour | 5 | 7 | 2006-05-30
10 | Settings |  |  | .
10.1 | Settings - Audio (Ring tones) | 2 | 2 | 2006-03-15
10.2 | Settings - Keys | 2 | 2 | 2006-03-15
10.3 | Settings - Alarms | 3 | 5 | 2006-04-25
10.4 | Settings - Date/Time | 2 | 1 | 2006-03-03
10.5 | Settings - Own Number | 2 | 2 | 2006-03-15
10.6 | Settings - Language | 2 | 2 | 2006-03-15
10.7 | Settings - Contact Settings | 3 | 5 | 2006-04-25
10.8 | Settings - Message Settings | 3 | 5 | 2006-04-25
10.9 | Settings - Call Settings | 3 | 5 | 2006-04-25
10.10 | Settings - Security | 2 | 2 | 2006-03-15
10.11 | Settings - Screensaver | 3 | 5 | 2006-04-25
10.12 | Settings - Network | 3 | 5 | 2006-04-25
10.13 | Settings - Area Info | 3 | 5 | 2006-04-25
10.14 | Settings - Master Reset | 3 | 5 | 2006-04-25
10.15 | Settings - Vodaphone Services | 3 | 5 | 2006-04-25
11 | Miscellaneous |  |  | .
11.1 | Screensaver - preserve state | 4 | 7 | 2006-05-30
11.2 | Delete Wizard | 4 | 6 | 2006-05-15
11.3 | SyncML |  |  | .
11.3.1 | SyncML-UI | 2 | 2 | 2006-03-15
11.3.2 | SyncML-Flow | 2 | 2 | 2006-03-15
11.3.3 | Sync | 3 | 5 | 2006-04-25
11.4 | SyncML ErrorCodes | 3 | 5 | 2006-04-25
11.5 | Editor Concept |  |  | .
11.6 | Accessories |  |  | .
11.6.1 | Headset |  | 7 | 2006-05-30
11.6.2 | Car Kit |  | 7 | 2006-05-30
11.6.3 | Charging Display | 4 | 7 | 2006-05-30

## Text-Icon Resource Timeline
Jerry MMI Specification Delivery Plan - Text/Icon Defines
S. No. | Topic | SW Sprint | Date
1 | Sprint 1 Resources | 1 | 2006-03-03
1.1 | Text ID / Defines | 1 | 2006-03-03
1.2 | Icon ID / Defines | 1 | 2006-03-03
1 | Sprint 2 Resources | 2 | 2006-03-31
1.1 | Text ID / Defines | 2 | 2006-03-31
1.2 | Icon ID / Defines | 2 | 2006-03-31
1 | Sprint 3 Resources | 3 | 2006-04-25
1.1 | Text ID / Defines | 3 | 2006-04-25
1.2 | Icon ID / Defines | 3 | 2006-04-25
1 | Sprint 4 Resources | 4 | 2006-05-15
1.1 | Text ID / Defines | 4 | 2006-05-15
1.2 | Icon ID / Defines | 4 | 2006-05-15