## Slide 1: Agenda
1. Update on commercial agreement with VF
2. Update on timeline
3. VF concerns around project
3. Action-plan to ensure stock in channel by Oct 14th with min. 5 VF-countries
4. Identify opportunities to improve timeline

## Slide 2: Vodafone would invest a total of 4.5€ million in the development of the Jerry, which would directly reduce the price of the device to the Vodafone operators. This model (when applied to the commercial agreement already in place) would reduce the net net price from launch until the end of month 3 to 75€ and from the beginning of month 4 to the end of month 6 to 69€. The NRE payment to BenQ mobile would be equally split in to 3, 1.5€ million installments and will be paid at the following project milestones: a) 1st payment – upon availability to Vodafone of Jerry B1+ samples (definition of sample to be agreed) b) 2nd Payment – upon start of acceptance test phase A c) 3rd payment – upon a mutually agreed level of product acceptance If BenQ mobile does not achieve milestones, for reasons which BenQ is directly responsible, within an agreed period, Vodafone reserves the right not to pay the NRE for that specific milestone. If the product is not launched before December 31st, VF reserves the right to a full refund on NRE payments made. In any such case the price of the product will increase by 5€ per unit (for both quarters) for every NRE installment (1.5€ million) not paid or refunded. Vodafone will commit to purchase a minimum of 150,000 units between launch and 15th January 2006. If for reasons which BenQ mobile is directly responsible for, the product has not been launched by 15th October 2006, BenQ understands that this volume commitment will reduce by 18,000 units per 2 week period (commencing from the 16th October).
Status Commercial Discussion
*
*

## Slide 3: VF Perception of Project
“I don't believe that BenQ is planning the project with the correct attitude and I have very little confidence that we will launch by the agreed date in October”
“The current planning indicates that there is zero buffer in the project and your colleagues have even reduced the Vodafone Acceptance Testing by one week in order to hit the date to which BenQ senior management committed at 3GSM. This suggests that just one unanticipated problem will push the launch past the latest acceptable date of October 13th.”
“As communicated before, the mid-October launch date is already very late for the Christmas period and key markets such as Vodafone Germany are extremely keen to launch this device much earlier and, if so, they would obviously order more devices from BenQ. In addition, certain OpCos may not launch the Jerry due to this late delivery date.”
“only possible chance of improving a launch date/de-risking the a plan is to invest in shortening the development time. By the time we begin Pre-Acceptance there will be no opportunity to save time.”

## Slide 4: Drivers to maximise Jerry potential
75€ @ market introduction
Time to Market:
  Action-plan to ensure stock in channel by Oct 14th with min. 5 VF-countries
  Identify opportunities to improve timeline