## Slide 1: Jerry “Vodafone Simply Exclusive“ PBR Status Report at M1
Kheng-Wah Koh
Category Product Management
Date: 07 Apr 2006
CPM: Kheng-Wah Koh VF Acc PM: Thomas Bartl
TPM: Zhang Shuai (Sean) VF Acc Project Mgr: Monika Reiss
PL-Ts: Lars Bonde VF Acc Sales: Stefan Hanika, Gary Vincent
Arjen Broeze BA: Gao Jie (Gina)
Sara Song

## Slide 2: Status update
Team visited Vodafone on 4 Apr with the key objective of securing Vodafone’s confidence in BenQ’s ability to deliver Jerry according to agreed schedule.
Jerry project team worked very hard to ensure that the Sw Sprint1 deliverables promised to VF are achieved on-time. An A1 PCB, Sprint1 software on a modified Aries and on PC Simulator was demonstrated to Vodafone.
Meeting went very well and we received very positive feedback from VF: “Yesterday's development review meeting in Düsseldorf greatly increased the confidence of myself and the team that we are on track in the Jerry SW development…”, Florian Pummer, VF Terminal PM
Agreement on commerical terms reached between GAM and VF. Contract in finalization stage.

## Slide 3: Quality Gate Rating Jerry 1/2 Status M1
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
Sales Fit
Volume: 150k till Jan.15, 2007 committed by VF (contract being finalized, not signed yet) vs. target 450k over lifecycle (forecast from GAM used in BC)
Sales margin: 11’9 € (=32.7 %) vs. 12’1 € (=33.4%) @M0
Price: launch 75 € , EOL 65 € , ASP 80.56 €
Profitability
PPC: 9’6 € (26.4%) vs. 10’4 € (28.9%) @M0
Time to Break-Even: 50% of the PLC
(LC: 12 months; DS: Oct. 2006; Break-even: Mar. 2007)
Direct R&D cost : 7’2 € vs. 9’0 € @M0
Volume risk -0’4 €, price risk -0’3 € impact on the PPC
Strategy Fit
Exclusive for Vodafone Simply
Sales channel: 100% operator
Required in-time DS by VF for the year-end Christmas business
QG
Rating Meeting: Mar.31, 2006 PSO support: Jing Wei

## Slide 4: Quality Gate Rating Jerry 2/2 Status M1
Time-to-Market
M0: Mar.16 (vs. Feb.23, 2006 @M0)
M1: Apr.6 (vs. Mar.31, 2006 @M0)
S25: Jul.31 (vs. Jul.18, 2006@M0 )
S3: Aug.23 (vs. Aug.16, 2006@M0)
DS: Oct.9 (vs. Sep.22, 2006 @M0)
S4: Nov.22 (vs. Nov.13, 2006 @M0)
Shift in DS was to accommodate VF’s complete test period - this DS date is agreed with VF.
Project Quality
Signatures complete
50% PPLs in BJ site relatively inexperienced as PL
Product Quality
Current estimated return rate:
8.5% (SW 3.1 % +HW 5.4 %) vs. 9 % (target as C class)
High risk from QM side:
  3-4 weeks potential delay in case of MD problems due to missing of 3rd prototype run
  Transfer of project from AAL to BJ before availability of first samples
Rating Meeting: Mar.31, 2006 PSO support: Jing Wei
Profitability
Project Quality
Sales Fit
Product Quality
Strategy
Fit
Time-to-Market
QG

## Slide 5
  Lifecycle:
  Current lifecycle is from Oct’06 to Sept’07, in total 12 months.
  Units:
  450K is an estimation by Vodafone account management.
  Potential Risk: One customer only.
  ASP:
  With NRE Price line: 75.00€ (Q4’06), 69.00€ (Q1’07), 69.00€ (Q2’07), 65.00€ (Q3’07).
  Current ASP 80.56€ has included the 4’5 € NRE by VF. According to Accounting Principle, such customer cash advance would be recorded into sales revenue, and it is reflected on higher price (15.00€ higher for the 1st 300K units).
  Current ASP is a bit higher than at M0, due to relatively more units sold in Q1’06, when the price is higher.
  HK:
  Current BOM declared by PE is 49.27€. Business Case BOM 50.26€ has included variant adder.
  Current BOM increases from M0, because of changes in housing requirements and user guides.
  Exchange rate EUR/USD = 1.20
  Opportunity: 0.27€ NES.
  Risk: User Guide concept to be finalized.VF requires special user guide. Current BOM has two user guides, however, one more user guides might be added (+0.7€/unit for one more).
  Other PRC:
  Therein 2.4% IPR risk.
  Service return rate increased from M0 4.5% to M1 8.5%, because Jerry is classified from A Class to C Class (SGold-lite, some new parts and a complete new user interface).
  R&D:
  Internal R&D has reduced from M0 9‘0 € to M1 7‘2 €.
  PPC:
  Target PPC was based on comparable M0 Business Case.
Analysis DS Business Case
  Break even on Direct R&D in Mar. 2007
Jerry – M1 Business Case
Notes: <number>
<footer>
<header>
<date/time>

## Slide 6: Risks - Impact vs M1 Business Case
Notes: <number>
<footer>
<header>
<date/time>

## Slide 7
Measures, Responsibles and Due Dates
Q-gate Axis | Measure | Status | Due Date | Responsible
Strategy Fit | No yellow/red rated items currently. |  |  | 
Sales Fit | Secure NRE and volume commitment by contract asap | Open | Early April | GAM, CPM
Profitability | Investigate on measures to reduce direct R&D cost without impacting TTM. Status: Reduction of R&D cost by 1.8mil, mainly in area of software. | Closed | Before M1 | PL-Ts, BA
Product Quality | QM: 3-4 weeks potential delay in case of MD problems due to missing of 3rd prototype run. Risk is managed by ensuring close communication links with experienced supplier and having MD PL on-site during B1 and B2 runs. AAL to BJ project handover planning was already made in Feb workshop: Ensure minimal progress impact when project transferred from AAL to BJ by phasing in BJ staff in project asap. Arrange visa and support for BJ staff to station in AAL throughout the whole handover phase. | Open Open | April April | Arjen B., Sara S, Lars B. Arjen B., Sara S, Lars B.
TTM | No yellow/red rated items currently. |  |  | 
Project Quality | Provide adequate project training for Beijing PPLs before May | Open | May | PD Line Managers
Others |  |  |  | 

## Slide 8
Decision Proposals in case of yellow Q-Gate
We propose to declare M1 milestone and Go ahead with the project.
Jerry is part of a “package deal” and is a strategic project with Vodafone.
Sufficient measures for most yellow rated issues are prepared for project to continue.

## Slide 9: Backup

## Slide 10
Special buttons enable user to access the commonly used features easily.
Easy to use User Interface designed to Vodafone Simply specification.
Large display allow the older aged users to view numbers and messages with no difficulty.
Bundled Desktop charger makes experience of charging the mobile as simple and familiar as charging a home cordless phone. Bundled headset enables user to have long conversation comfortably.
CORE CATEGORY: Affordable Quality
CONSUMER SEGMENT: Reassurance, VF’s APU/MB
THEME POSITION: Convenience
Consumer Value prop.
Simplicity – easy to use mobile phone for practical consumers.
Selling prop.
Gender: f/m = 50:50
Age Focus: >40
WE, EE, Australia/NZ
Income: mid
Lifestage: middle-aged, empty nesters
Demo-
graphics
VF’s Adult Personal User (APU): Manage a hectic life and want to be in control. Value driven - cautious money managers who rely on tried and trusted brands
VF’s Mature Basic: Typically older aged, empty nesters
Lifesyle
Target Group (Who)?
Jerry is part of a “package deal” for Vodafone together with Kestrel and Merlin. Support the growth of Vodafone Simply customer base with Jerry.
Strategy &
History
My phone should not be complicated and have too many features that I don’t use frequently.
It should be convenient & contains self-explaining features.
I need a mobile for security/emergencies and family contact, it is not core to my life and I only used it when away from fixed line.
I’m value driven - cautious money managers who rely on tried and trusted brands
I have low technology engagement.
Selling & Value Proposition (What)?
Target Group Benefits (Why)?
Product Story Target Group & Key Product Arguments
Emotional
Functional
Consumer Positioning
Notes: <number>
<footer>
<header>
<date/time>