## Version_1.0
M a s t e r J o b P r o f i l e
Basic data | OrgEinheit/Ort | ICM MP
| Function Area | Project Management | Management
Operational Field
| Functional descript. | Junior Project Manager (JPM) | Project Manager (PMT) | Senior Project Manager (SPM) | Project Director (PDir)
| Corporate | Regionalgesellschaft
| PL-functions | PD: (Hardware: PPL HW, PPL HW P; Software: PL-C) | PM: PM, BO-PL, GPM SCM: PL-SCM (Supply Chain Mgmt.) PD: PL-HW, PL-HW P, PL-SW, PL-SW P, PL MD, PL MD P, PL ST PPM: OM | PM: SPM, PL-T S&M: PDM PPM: SPM | PM: SPM with A-Projects PPM: PGM
| Objectives of the function ( Mission) | The Junior Project Manager leads a part of the whole project within PD or SCM organisation (Hardware: PPL HW, PPL HW P; Software: PL-C) with the aim to | The Project Manager PM, PL-T, PL-SCM (Supply Chain Management), PL-BO, PL-HW, PL-HW P, PL-SW, PL-SW P lead teams with the aim to | The SPM drives, coordinates and represents the whole project up to Milestone M5, makes project decisions, leads REA Team, with the aim to | The Project director leads SPM teams with the aim to
execute projects within the quality framework ( time, budget, functionalities) ensure success in terms of economic results, reaching Time to Market and ensuring at least the planned profit of the business case. supports standard solutions and reduces variants wherever possible
Tasks / Area of Responsibility | R e s p o n s i b i l i t y A r e a / T a s k s
|  | Junior Project Manager (JPM) | Project Manager (PMT) | Senior Project Manager (SPM) | Project Director (PDir)
| Results-Responsibility | Regionalgesellschaft
|  | Responsible for planning and execution of defined parts of technical implementation according to M1 agreements (schedule, HK, features, etc.) | Responsible for planning and execution of technical implementation (PL-T, PL-SW, PL-SW P, PL-HW, PL-HW P) or implementation in production(PL-SCM) including costs, quality,TTM, to ensure the business case | acts as entrepreneur on the level of decision making takes the profit and loss responsibility for the project, including responsibility for TTM, business case, market launch, production and logistics control up to M5
| Customer Management |  | supports SPM and PDir concerning good and strong customer relationship. | Reflects actions, opinion and feedback of customers actively and supports a good and strong customer relationship together with Sales / S&M. Provides recommendations and decisions to customers based on thorough understanding of customers' business and operational environment. Provides consulting support to customer in his decision making. Involves customer inputs in the decision making process. Supports customer to reach his goal and is his "support partner" to ensure that solutions fit to his overall strategy and feasible to carry out in his overall business environment, Knowledge about the business and customers eg. Market, competition, strategy, business processes and decision makers.
| Partner-management | # intgrates qualified / competent subcontractors/partners right in time # defines the requirements and project specific framework to subcontractor/partners (quality, timeframe, methods and processes, quality standards, provisions and acceptance modalities) # monitors the performance of subcontractors / partners and escalates in case of problem with regard to quality and cooperation
# develops solution strategy in case of problem with subcontractor / partners and realizes them # signs back-to-back agreement with subcontractors / partners. # negotiates requirements and fulfillment of project specific conditions with subcontractor /partners
| Finance-management | # is familiar with the established procedures for steering and controlling financial aspects of the project. # knows the economic indicators ( scorecards) of projects and considers them in a regular project calculations and review. # interpretes the financial figures of the project in respect to project progress, develops and uses steering instruments.
# communicates regularly with the (project) commercial / accountant and able to report at any time financial figures and status of the project.
| Human resource-management | # plans the necessary human resources for the project ( qualitative : competencies/skills, Quantitative : head count) # provides resources, ensures placement and optimal use. # ensures target oriented and open communication within the project team # agrees on individual targets with project employees and defines responsibilities to the right / competent employees. # coaches the team / individual team member and provides performance feedback to individual and to the team during the project. # conducts staff dialogue to identify gap between the actual and required competencies (knowledge, experience and capabilites) with respect to actual project targets, suggests necessary training and development measurements ( together with the line manager of the employee) # at the end of every project, provides individual feedback to employees ( together with the line manager) on topics like performance, behaviour, recommends future development plan.
Business-development in the current project
# develops and realizes strategies to continue and/or strengthen the business with the customer. # co-operates withSales / S&M to explore further business possibilities
| Consumer Marketing | # Knowledge about Markets, market segmentation, 4P (product, price, place, promotion) # creates customer oriented products # Price as part of the product, target costing
|  |  |  | # positioning of product, marketing based on technical and emotional elements | # positioning of product, marketing based on technical and emotional elements
| Contract Management | # estimates the consequences of changes in requirements / delivery items / services with respect to the cost, project plan, profit realization
| Change Management | # evaluates influence of Change Requests (costs, time to market, resources)
|  |  |  | develops together with Sales the strategy for claiming / defence at customer side, and ensures consequent implementation. | develops together with Sales the strategy for claiming / defence at customer side, and ensures consequent implementation.
| Rights and Liability | # Knowledge about know-how protection and product liability in Germany and other concerned countries (e.g. China, Brasil) # knowledge and awareness, which information/documentation/software/prototypes can be given to which subcontractor/partner/customer or other Siemens internal involved departments
| Risk Management | # knows risk factors - collects the relevant data and makes them available. # estimates the influences and risks in the project on a continuous basis and evaluates their implication (eg. contract risks, costs, technical and organisational risks, internal / external staffing, influence on business case, and handling of change requests). # evaluates the risk of involved subcontractors / partners and country-specific influences (customer/market, suppliers) # develops the appropriate strategy to reduce the risk of the project and realizes them # knowledge about product quality and quality assurance
| Planning | # defines the project targets in cooperation with responsible manager ( cost, timeframe, functionality) and prepares a project plan # fine-tunes workpackages # resource planning # project schedule # project documentation # project organisation # interface management # structure and procedures of configuration management # mobile phone cost and development budget planning and control for responsible project part # defines procedure and requirements regarding quality management (test concept, test performance, follow up of open issues)
# plans the strategy to ensure business case and production quantity, is responsible for economic and sufficient component material supply (together with GS), economic finished phones in stock, and low stock waste at M5
Project controlling and reporting
# uses established procedures and processes for the project controlling reporting to have an actual overview on project at any time. # controls on a regular basis the project status with regard to technical commercial as well as qualitative targets. Also monitors processes and result quality # ensures cost forecasting, realizes discripancies in the project at a early stage, identifies causes for the problems and eliminates them effectively # informs regularly management and project team about the project status # organises the acceptance of the milestones for his responsible project part
| Project conclusion | Development Project: # manages the acceptance of Milestone S4 (finish of development process) and M5 (SPM, PDir for whole lifecycle) according to TTM, inlcuding validation and verification # responsible for completion of project documentation and for their proper storage # ensures the reusability of the project results and experiences by final reviews and lessons learnt documentation /workshops # checks at M5 if business case was fulfilled/exceeded.
| Corporate Networking | # uses the available resources and tools in the organisation # Detects new resources and uses them actively for information, knowledge, experiences, should be project focussed and entreprenuer ( eg. Knowledge management system- share net) # open and target oriented commnucation about information, knowledge and experiences from the project ( within the across the groups) # prepares information, knowledge and experiences internally and across the project groups for lessons learnt, best practice sharing
# ensures and enables the establishment of corporate networking and knowledge management
| Personal development : Responsibility and initiative | # assesses own personality realistically, knows his strengths and weaknesses as well as own limitations. # actively seeks feedback ( e.g. from employees and managers) and takes this as opportunity for the further development # takes the responsibility and initiative for own further development # uses all available sources for further education. (e.g. PM@Siemens Academy). # uses the possibility to learn from others and exchanges experiences.
# takes the responsibility to coach new PM colleagues from other projects
| Purchasing and Logistcs | # knows Siemens Corporate logistic policies and puts them into practice # is familiar with the internal and internaltional rules ( ZRG, export sanctions, INCOTERMS) and uses them # knows basics of supply chain management and orders / control their use # knows the global procurement policy and complies with rules, structure and processes
# plans the strategy for local purchasing, together with the responsible manager and procurement department and puts it in place. Cooperates closely with experts
Competencies
Knowledge | Knowledge
| Corporate | Regionalgesellschaft
| Technical Knowledge | expert knowledge about MP product processes, predevelopment and platform activities, expert knowledge about R&D controlling activities in project realisation, tools and information for managing projects
| communication | Intercultural communication skills (especially China and Brasil, if employees of these countries are involved)
| Languages | English fluently, especially for internal reporting, and for projects with participants outside of Germany
| methods | Project management methods regarding tasks and areas of responsibilties, Project Management Tools, Decision methods
| Technologien: |  |  | advanc. | niedrig
Experience
| Professional experience | technical MP knowledge in 2-3 years of professional experience in development or supply chain or sales or other comparable functions.
| Project experience | Has Minimum 1 year responsibility of cooperating in the project. | Has Minimum 1 year responsibility of cooperating in the project. | Has minimum 2 years experience in successfully leading MP projects. | Has minimum 6 years experience in successfully leading MP projects
| Leadership experience | Has responsibility for employees at least for one year. | Has responsibility for employees at least for one year. | Has successfully led project teams at least for 2 years. | Has successfully led project teams at least for 6 years.
| Intercultural experience | Has worked and lived abroad ; Recommended : cooperated in international teams | Has worked and lived abroad ; Recommended : cooperated in international teams | Has worked and lived abroad : Mandatory Has worked in international teams : Mandatory
| Ergebnisorientierung [Drive] | Veränderungsfähigkeit [Drive] |  | Strategisches Denken [Focus] | Networking Skills [Impact]
Capabilities | Which of the following capabilites are the most relevant for this function ? ( select 6 out of 17)
| Human resource-management | Drive: Result Orientation Decision Making ability Initiative Creativity Ability for Changes | Focus: Analytic Ablities Planning and Organizing skills Learning Ability Strategic Thinking | Impact: Assertiveness Communication Skills Customer Orientation Networking Skills | Guide: Coaching and Mentoring Empathy Motivation Ability Teamworking ability
Additional Requirements
Additions