## Slide 1: PLT Masterplan concept
Planning Office
11 January 2006
Primavera project planning

## Slide 2: Purpose
This document describes the concept of the “PLT master plan” template used for product project planning in Primavera.

## Slide 3: Structure in Primavera
Part projects
PLT Master Plan
?
?
?
WBS: PLT target plan
WBS: Bottom-up plan
M0
M1
S4/M3
WBS: Control milestones
Level of effort
Remaining work
Completed
Legend
Baseline
Baseline milestone
Control milestone

## Slide 4: PLT Master Plan Description
The PLT-Master Plan consists of:
-Control Milestones: A WBS showing the M and S milestones. Those milestones are the control milestones.
-PLT target plan: A WBS section for PLT target planning to be used by the PLT as a quick way to get a overview of the project delivery timeline.
-Bottom-up plan: A WBS section showing a high level overview (milestone and main activities) connected/linked to the detailed part project plans.
The valid project plan is:
-Before M0: The WBS “PLT target plan” is the main project plan for the period M0 – M3/S4.
-From M0 to M1: The WBS “Bottom-up plan” is the main project plan for the period M0 to M1.
The WBS “PLT target plan” decides the duration for the period M1 – M3/S4.
-After M1: The WBS “bottom-up plan” is the main project plan for the period M1 – M3/S4.
Archive:
- From M0 to finish Copy of the “PLT target plan’s” - the PLT’s reference and scenario planning projects.
The PLT Master Plan is always the overall project plan through the project lifecycle. At the first step the plan is based on the PLT target plan, later the bottom-up plan linked to the part project plans are used.

## Slide 5: Before M0
Part projects
PLT Master Plan
WBS: PLT target plan
Task dependent
Legend
M0
M1
S4/M3
WBS: Control milestones
Milestone floating
Milestone fixed

## Slide 6: ”Before M0” description
Before M0 the PLT is working with the “PLT target plan” which includes the milestones form M0 to M3/S4 and some pre-defined major activities.
The PLT can via re-estimation of the pre defined duration or via modification a) of the pre-defined activities calculate when the product can be delivered.
The “PLT target plan” is the plan made by the PLT to achieve management approval to continue further project planning before M0.
The defined “PLT target plan” is a target for the team, when the PPL’s starts the detailed planning until M0.
a) This should be avoided but if this is done the Primavera Planning Coordinator need to modify the “Bottom-up plan” to be equivalent with the PLT target plan.

## Slide 7: From M0 to M1
Part Projects
M0
M1
S4/M3
WBS: PLT target plan
WBS: Bottom-up plan
PLT Master Plan
?
?
?
?
?
?
?
?
?
?
M0
M0
M1
WBS: Control milestones
M1
Level of effort
Remaining work
Completed
Legend
Baseline
Baseline milestone
Control milestone

## Slide 8: “From M0 to M1” description
Deviations in the detailed plan of the part projects milestones M0 – M1 will be reflected in the “Bottom-up plan” with the baseline as reference.
Deviations of the M1 date will also be seen in the Control Milestone section. The milestones in the period M1 – M3/S4 will be moved proportionally.

## Slide 9: After M1
S4/M3
S4/M3
Part Projects
M1
PLT Master Plan
?
?
?
?
WBS: PLT target plan can be found at the Project archive
WBS: Bottom-up plan
M1
M0
Level of effort
Remaining work
Completed
M0
?
Legend
M0
M1
WBS: Control milestones
Baseline
Baseline milestone
Control milestone

## Slide 10: ”After M1” description
Deviations in the detailed plan of the part projects milestones M1 – M3/S4 will be reflected in the “Bottom-up plan” with the baseline as reference.
Deviations of the main milestone dates will also be seen in the Control Milestone section.
If the PLT need to do some major re-planning until M3/S4 the “PLT target plan” (or a copy of it) in the archive area can be used for scenario planning.