## Slide 1: PLT Masterplan guide
Planning Office
11 January 2006
Primavera project planning

## Slide 2: Purpose
This guide describes the template for PLT master plan in Primavera, i.e. the structure of the template and how to use it. It is intended for PLT’s and Planning Coordinators.

## Slide 3: PLT master planning - role description
M@
M0
M3/S4
M1
On PLT request the product projects are in Primavera.
PLT prepare the “PLT target plan in the PLT master plan and calculate the product delivery time.
PPL’s who do tasks within the phase M0-M1 prepare the detail plans for M0-M1 and make rough resource planning for M1 to S4/M3.
The project plans are updated on weekly base. Deviations in the detailed plan will be reflected in the Control milestones of the bottom up plan in the PLT master plan.
All PPL’s who do have tasks within the project phase M1-M3/S4 prepare the detail plan for M1-M3/S4
The Planning Coordinator prepare the PLT master plan to pass M0.
The Primavera project plans are updated by PLT and PPL’s on weekly base. Deviations in the detailed plan will be reflected in the Control milestones of the bottom up plan in the PLT master plan.
If re-planning of the project is needed the PLT will be able to do his/her scenario planning in the PLT target plan before involvement of PPL’s and after wards ask the PPL’s to make their detailed re-planning.
The Planning Coordinator support the PLT and PPL’s
PLT
PPL
Planning Coordinator
The Planning Coordinator prepare the PLT master plan to pass M1.
The project plans are updated on weekly base. Deviations in the detailed plan will be reflected in the Control milestones of the PLT master plan.
The project plans are updated on weekly base. Deviations in the detailed plan will be reflected in the Control milestones of the PLT master plan.
On a PLT request the PPL make detailed re-planning.

## Slide 4: Structure in Primavera
Part projects
PLT Master Plan
?
?
?
WBS: PLT target plan
WBS: Bottom-up plan
M0
M1
S4/M3
WBS: Control milestones
Level of effort
Remaining work
Completed
Legend
Baseline
Baseline milestone
Control milestone

## Slide 5: PLT Master Plan Description
The PLT Master Plan is always the overall project plan through the project lifecycle. At the first step the plan is based on the PLT target plan, later the bottom-up plan linked to the part project plans are used.
The PLT-Master Plan consists of:
Control Milestones: A WBS showing the M and S milestones. Those milestones are the control milestones.
PLT target plan: A WBS section for PLT target planning to be used by the PLT as a quick way to get a overview of the project delivery timeline.
Button-up plan: A WBS section showing a high level overview (milestone and main activities) connected/linked to the detailed part project plans.
The valid project plan is:
Before M0: The WBS “PLT target plan” is the main project plan for the period M0 – M3/S4.
From M0 to M1: The WBS “Bottom-up plan” is the main project plan for the period M0 to M1. The WBS “PLT target plan” decides the duration for the period M1 – M3/S4.
After M1: The WBS “Bottom-up plan” is the main project plan for the period M1 – M3/S4.
Archive:
From M0 to finish: Copy of the “PLT target plan’s” - the PLT’s reference and scenario planning projects.

## Slide 6: Before M0
Part projects
PLT Master Plan
WBS: PLT target plan
M0
M1
S4/M3
WBS: Control milestones
Level of effort
Remaining work
Completed
Legend
Baseline
Baseline milestone
Control milestone

## Slide 7: ”Before M0” description
Before M0 the PLT is working with the “PLT target plan” which includes the milestones form M0 to M3/S4 and some pre-defined major activities.
The PLT can via re-estimation of the pre defined duration or via modification a) of the pre-defined activities calculate when the product can be delivered.
The “PLT target plan” is the plan made by the PLT to achieve management approval to continue further project planning before M0.
The defined “PLT target plan” is a target for the team, when the PPL’s starts the detailed planning until M0.
a) This should be avoided but if this is done the Primavera Planning Coordinator need to modify the “Bottom-up plan” to be equivalent with the PLT target plan.

## Slide 8: Detailed M0 to M1 planning before M0 gate
PLT Master Plan
M0
M1
S4/M3
WBS: PLT target plan
WBS: bottom up plan
?
?
?
?
?
“M1-M1” Link to be established
Copied to the projects archive aria
Delete afterwards M0 to M1 activities
M0
M0
M1
WBS: Control milestones
Part Projects
PPL prepare detail planning of the relevant part projects
Level of effort
Remaining work
Completed
Legend
Baseline
Baseline milestone
Control milestone

## Slide 9: Detailed M0 to M1 planning before M0 gate - description
The PPL’s from the part projects who have development tasks within the M0 to M1 phase prepares their detailed planning within the M0 to M1 phases and assign rough planning resource for M1 to S4/M3, 2 to 3 weeks before M0 gate.
The result of the detailed planning can be seen in the WBS named “bottom up plan”.
When the M0 to M1 detailed planning has finished by the PPL’s the PLT compare this with the PLT target plan and analysis if the project can continue.
At the M0 gate the control milestone M1 of the bottom up plan are linked to M1 of the “PLT target plan” to show deviations caused by the detailed planning.
As the tasks of the PLT target plan will not be started and finished and to avoid the PLT target plan will move along the data date the activities from M0 to M1 must be removed. Before the planning coordinator is doing this the WBS “PLT target plan” is copied to an empty project called “PLT target plan” in the projects EPS archive aria – this is done to keep the original “PLT target plan” as reference for the PLT and also allowing the PLT to do scenario planning at a later time.
The milestone M0 and S0 in the WBS “bottom up plan” and the milestones from S15 to M3/S4 in the WBS “ PLT target plan” are then the reported milestones.

## Slide 10: Detailed M1 to M3/S4 planning before M1 gate
M1
S4/M3
PLT Master Plan
?
?
?
?
?
WBS: PLT target plan
WBS: bottom up plan
M1
S4/M3
M0
?
?
?
?
PPL prepare detail planning of the relevant part projects
?
Link to be deleted
WBS to be moved to the EPS archive of the Project
M0
M0
M1
WBS: Control milestones
Part Projects
Level of effort
Remaining work
Completed
Legend
Baseline
Baseline milestone
Control milestone

## Slide 11: Detailed M1 to M3/S3 planning before M1 gate - description
3-4 weeks before M1 all the PPL’s who do have tasks within the project phase M1-M3/S4 prepare the detailed plan. (During this planning period constraint dates can temporary be assigned to the bottom up control milestone).
The PLT recalculate the product delivery time. The result can be found in the WBS “bottom up plan” as this do have links to the part projects established.
The Project Planner modify the PLT master plan i.e. remove M1 links and the WBS containing “PLT target plan” is moved to the project archive as reference.
The milestones in the WBS “bottom up plan” are linked to control milestones.

## Slide 12: After M1
S4/M3
S4/M3
Part Projects
M1
PLT Master Plan
?
?
?
?
WBS: PLT target plan can be found at the Project Archive
WBS: Bottom-up plan
M1
M0
M0
?
M0
M1
WBS: Control milestones
Level of effort
Remaining work
Completed
Legend
Baseline
Baseline milestone
Control milestone

## Slide 13: ”After M1” description
Deviations in the detailed plan of the part projects milestones M1 – M3/S4 will be reflected in the “Bottom-up plan”.
Deviations of the main milestone dates will also be seen in the Control Milestone section.
If the PLT need to do some major re-planning until M3/S4 the “PLT target plan” (or a copy of it) in the archive area can be used for scenario planning.