## Jerry Overall
Plan : Overall
| Project Name: Jerry Overall |  |  |  | Planner: Jiang Hui Wen Date: 2006-2-28
[6 empty] | The board outline is only 80% fixed. Purpose is to have a first test of the HW circuits. PCB maturity must be B1 except EMC/ESD, Audio/Acustic, Display and Antenna | Board outline/stack up/screw towers are 100% fixed. PCB maturity must be B1+ except EMC/ESD, Audio/Acustic, Display and Antenna. |  |  |  |  | PCB is compliat over full temperature range | [7 empty] | Final prototype B2.
Department | Location | Contact Person | Function | Tele | Email | A1 | A1+ |  |  |  |  | B1 | [7 empty] | B2
[6 empty] | Single PCB Populated | single PCB not populated | panel ( * 6 PCB ) not populated | panel ( * 6 PCB ) populated | boards populated with function | boards w/o function | single PCB not populated | panel ( * 6 PCB ) not populated | panel ( * 6 PCB ) populated | boards populated with function | boards w/o function | Internaltiona Variant |  | Special | single PCB not populated | panel ( * 6 PCB ) not populated | panel ( * 6 PCB ) populated | boards populated with function | boards w/o function | Internaltiona Variant |  | Special
[17 empty] | DV1 | [7 empty] | DV1
[10 empty] | BV1 |  |  |  |  | BV1 |  | with hole | w/o hole NA |  |  |  |  | BV1 |  | with hole | w/o hole NA
China Site | BJ |  | PL-T
China Site | BJ | Zhang Shuai | PM | +86 10 6474-8800 ext 7313 | Shai.Zhang@benq.com
China Site | BJ | Wu Yu Jin | BB | +86 10 6474-8800 ext8794 | yujin.wu@benq.com |  |  |  |  | 2 |  | 2 |  |  | 22 |  | 22 |  |  | 2 |  |  | 22 |  | 28 |  |  | Variant definition
China Site | BJ | Li Jian | RF | +86 10 6474-8800 ext8205 | jian.lee@benq.com |  |  | 1 |  | 13 |  |  | 1 |  | 14 |  | 18 |  |  |  | 1 |  | 8 |  | 16 |  |  |  |  | DV1 | BV1
China Site | BJ | Peter Loeber | EA | +86 10 6474-8800 ext7865 | peter.lober@benq.com |  |  |  |  | 8 |  |  |  |  | 5 |  | 12 | [5 empty] | 5 |  | 20 |  |  | Housing | Color
China Site | BJ | Yang Yong Qiang | SW | +86 10 6474-8800 ext8285 | yongqiang.yang@benq.com |  |  |  |  | 6 | [6 empty] | 42 | [7 empty] | 24 |  |  |  | Supplier
China Site | BJ | xxx | L1 | xxxx | xxxx | [22 empty] | Display | Supplier
China Site | BJ | Yang LI | ST1 | +86 10 6474-8800 ext7566 | li.yang@benq.com | [11 empty] | 41 | [7 empty] | 41 |  |  | Keypad | Supplier
China Site | BJ | Wei Xue Kai | ST2 | +86 10 6474-8800 ext8059 | XueKai.Wei@benq.com |  |  |  |  | 4 | [6 empty] | 33 | [7 empty] | 52 |  |  | Metal dome foil | Supplier
China Site | BJ | Wu Li Bo | LPD/FPC | +86 10 6474-8800 ext7518 | LiBo.Wu@benq.com |  |  | 1 |  | 1 |  |  | 1 |  | 1 |  | 5 |  |  |  | 1 |  | 1 |  | 5 |  |  | Battery | Supplier
China Site | BJ | Thomas Bartel | PQA | +49 (89) 722-40029 | thomas.bartel.ext@benq.com | [11 empty] | 13 | [7 empty] | 25 |  |  | Vibra | Supplier
China Site | BJ | Zhang Qiu Ping | SW QA | +86 10 64748800-8046 | QiuPing.Zhang@benQ.com | [11 empty] | 2 | [7 empty] | 2
China Site | BJ | Jiang Hui wen | ST2/Prototype | +86 10 6474-8800 ext 8668 | huiwen.jiang@benq.com | 6 |  |  |  | 3 | [6 empty] | 10 | [7 empty] | 15 |  |  | Radio part(B6E) | Supplier
Subtotal | [5 empty] | 6 | 0 | 2 | 0 | 37 | 0 | 2 | 2 | 0 | 42 | 0 | 198 | 0 | 0 | 2 | 2 | 0 | 36 | 0 | 228 | 0 | 0 | Speaker | Supplier
China Site | SHA | Li Jian Hong | MD | +86 10 6474-8800 ext 7087 | JianHong.Li@benq.com | 0 |  |  |  | 2 | [17 empty] | Mic | Supplier
China Site | SHA | Shen Xiao Zhong | CCQ QM | +86 21 61012713 | xiaozhong.shen@benq.com | [19 empty] | 81 |  |  | PMU | Supplier
China Site | SHA | Gong Jing Wen | LCM3 | +86021-61012679 | jingwen.gong@benq.com |  |  | 2 | 2 | 18 |  |  | 8 | 5 | 14 | 6 | 17 |  |  |  | 4 | 6 | 25 | 9 | 27 |  |  | Flash | Supplier
China Site | SHA | Hu Xian Gui | SQM | +86021-61011903 | xiangui.hu@benq.com | [11 empty] | 1 | [7 empty] | 5 |  |  | PSRAM | Supplier
Subtotal | [5 empty] | 0 | 0 | 2 | 2 | 20 | 0 | 0 | 8 | 5 | 14 | 6 | 18 | 0 | 0 | 0 | 4 | 6 | 25 | 9 | 113 | 0 | 0 | PCB | Supplier
China Site | KLF | Thomas Krokowski | PAS/Field test | +49 (2842) 95-4659 | thomas.krokowski@benq.com | [11 empty] | 3 | [7 empty] | 156
Denmark Site | KLF | Katharina Hilker | LCM3 |  |  | 10 | 1 | 2 | 5 | 17 | 10 | 1 | 2 | 1 | 26 | 16 | 54 |  |  | 1 | 2 | 1 | 28 | 7 | 65
Denmark Site | KLF | Jens Riedel | LCM1
Subtotal | [5 empty] | 10 | 1 | 2 | 5 | 17 | 10 | 1 | 2 | 1 | 26 | 16 | 57 | 0 | 0 | 1 | 2 | 1 | 28 | 7 | 221 | 0 | 0
China Site | MCH | Steven Mueller | Safety Lab (EN60950) | +49 89 / 722 - 22505 F33 | steven.mueller@siemens.com | [19 empty] | 3
Denmark Site | MCH | Thomas Bartl |  |  |  | 1
Denmark Site | MCH | Clemens Lutch
Denmark Site | MCH | Thorsten Lange | AD |  |  | 0 | [11 empty] | 8 | [7 empty] | 20
Denmark Site | MCH | Andreas Michael Mairhof | AD | [14 empty] | 1 | [7 empty] | 4
Subtotal | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 24 | 0
China Site | AAL | Brian Mortensen | SW QA | +45 7219 5787 | brian.mortensen@benq.com | [11 empty] | 2 | [7 empty] | 2
Denmark Site | AAL | Lars Bonde | PLT |  |  | 1 |  |  |  | 10 | [6 empty] | 10 | [7 empty] | 10
Denmark Site | AAL | Flemming Bach Kristensen | BB |  |  | 21 |  |  |  | 22 | [6 empty] | 23 | [7 empty] | 15
Denmark Site | AAL | Michael Brammer | RF |  |  | 5 |  |  |  | 5 | [6 empty] | 5 | [7 empty] | 5
Denmark Site | AAL | Christian Primdahl Nielsen | ME |  |  | 1 |  |  |  | 5 | [6 empty] | 5 | [7 empty] | 5
Denmark Site | AAL | Arne Bisgaard Kristensen | EA |  |  | 5 |  |  |  | 10 |  |  |  |  | 5 |  | 15 | [5 empty] | 3 |  | 10
Denmark Site | AAL | Poul Søndergaard | PQA
Denmark Site | AAL | Allan Hansen | SW |  |  | 9 |  |  |  | 20 | [6 empty] | 20 | [7 empty] | 20
Denmark Site | AAL
Denmark Site | AAL
Denmark Site | AAL | Henning Boll | CC |  |  | 0 |  |  |  | 0 | [6 empty] | 2 | [7 empty] | 15
Denmark Site | AAL | Flemming Kokholm | ST |  |  | 1 |  |  |  | 1 | [6 empty] | 1 | [7 empty] | 1
Subtotal | [5 empty] | 43 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 5 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 83 | 0 | 0
Total | [5 empty] | 60 | 1 | 6 | 7 | 147 | 10 | 3 | 12 | 6 | 87 | 22 | 356 | 9 | 0 | 3 | 8 | 7 | 92 | 16 | 648 | 24 | 0
[6 empty] | 60 |  |  | 199 |  |  |  |  | 145 |  |  | 365 |  |  |  |  | 150 |  |  | 672