## Sheet1
Jerry effort estimation
Component / Task | Effort (man months) | Comments | Period from/to | Skills | From Site/Company | Proposed Person | On Site BJ | PL-C in SGoldLite platform
C_apbas | 32 | UI flow, look&feel | start Feb. or March | MMI Developer SGL or SG2 with knowledge in respective component | SISL (4) |  | no | Li Kang (lik)
C_apcnct | 4 | removing features | 1 month before S25 | MMI Developer SGL or SG2 with knowledge in respective component | KLF |  | no | Stefan Guhl (guhl)
C_apidc | 50 | might be higher | start Feb. or March | MMI Developer SGL or SG2 with knowledge in respective component | Bej (2), PSE Vienna (5) |  | no | Fu Meng Ruo (fum)
C_apmm | 4 | removing features | 1 month before S25 | MMI Developer SGL or SG2 with knowledge in respective component | Bej |  |  | Li Kang (lik)
C_apMMS | 16 |  | start Feb. or March | MMI Developer SGL or SG2 with knowledge in respective component | PSE NJ (2) |  | no | Zhou Yi (zhouyi)
C_apmsg | 16 |  | start Feb. or March | MMI Developer SGL or SG2 with knowledge in respective component | PSE NJ or SISL (2) |  |  | Li Kang (lik)
C_appim | 25 |  | start Feb. or March | MMI Developer SGL or SG2 with knowledge in respective component | PSE NJ or SISL (3) |  |  | Yi Jing (yijing)
C_appImail | 0 |  | start Feb. or March | MMI Developer SGL or SG2 with knowledge in respective component |  |  |  | Dirk Henneberger (henneber)
C_appIMPS | 0 |  | start Feb. or March | MMI Developer SGL or SG2 with knowledge in respective component |  |  |  | Jobst Gercke (gerckej)
C_AppMenu | 2 | removing FlexMenu | start Feb. or March | MMI Developer SGL or SG2 with knowledge in respective component | Bej |  |  | Klaus Staudenmaier (staudenmaierk)
C_ApPoC | 0 |  | start Feb. or March | MMI Developer SGL or SG2 with knowledge in respective component |  |  |  | Yu Jian Feng (yuji)
C_apreui | 6 | 2 Man * 3 Month | start Feb. or March | MMI Developer SGL or SG2 with knowledge in respective component | Bej |  |  | Wu Ying Yu (wuyingyu)
C_Avatar | 0 |  | start Feb. or March | MMI Developer SGL or SG2 with knowledge in respective component |  |  |  | Kusum Pawa (pawak)
C_browser | 4 | remove browser | 1 month before S25 | MMI Developer SGL or SG2 with knowledge in respective component | Bej, KLF support |  |  | Jörg Könning (koenning)
C_coapi | 4 |  | start Feb. or March | MMI Developer SGL or SG2 with knowledge in respective component | PSE NJ |  |  | Ge Dong Xu (gedo)
C_cojava | 4 | remove Java | start Feb. or March | MMI Developer SGL or SG2 with knowledge in respective component | Bej |  |  | Yang Yong Qiang (yangy)
C_couios | 8 |  | asap | MMI Developer SGL or SG2 with knowledge in respective component | Bej |  |  | Li Kang (lik)
C_DoJa | 0 |  | start Feb. or March | MMI Developer SGL or SG2 with knowledge in respective component |  |  |  | Yang Yong Qiang (yangy)
C_JavaApps | 0 |  | start Feb. or March | MMI Developer SGL or SG2 with knowledge in respective component |  |  |  | Rodrigo Sanctos de Miranda (mirandaro)
C_JavaAppsExtern | 0 |  | start Feb. or March | MMI Developer SGL or SG2 with knowledge in respective component |  |  |  | Liu Lin Yan (liul)
C_mobsim | 4 | add keys, adapt display size, feature set | asap (setup PCMMI) | MMI Developer SGL or SG2 with knowledge in respective component | PSE NJ |  |  | Li Kang (lik)
C_mopi | 2 | support for developers |  | MMI Developer SGL or SG2 with knowledge in respective component | Bej |  |  | Walter Stroell (stroellw)
C_security | 1 |  |  | MMI Developer SGL or SG2 with knowledge in respective component | Mch |  |  | Massimo Albani (albanim)
C_servims | 0 |  |  | MMI Developer SGL or SG2 with knowledge in respective component |  |  |  | Yu Jian Feng (yuji)
C_servPoC | 0 |  |  | MMI Developer SGL or SG2 with knowledge in respective component |  |  |  | Yu Jian Feng (yuji)
C_SipRtp | 0 |  |  | MMI Developer SGL or SG2 with knowledge in respective component |  |  |  | Yu Jian Feng (yuji)
Object Server | 2 |  |  | MMI Developer SGL or SG2 with knowledge in respective component | Aal
Device Layer | 25 |  | PL complete time, 4-5 Dev until End April, 1 Dev complete time | Arch, PL, Dev. | PL, (Arch), Dev: Aal (6) | Jakob Bro Nielsen | depends on HW location
CoreIntegrationTeam + IM | 36 | 20 (DL only) + 4*4 MMI | IM complete time, CIT from April |  | Aal (4) | Partly same people like for implementation | yes | Zhu Si Xing (zhus)
Customization | 2 | only one customer, no variants |  |  | Bej |  |  | Chai Chun Qian (chaichunqian)
DSP | 0 | no changes expected | [5 empty] | Ercan Eren (erene)
PC-Tools | 2 | MPM not clarified |  |  | Mch, Manaos |  |  | Katrin Hartmann (hartmannk)
Protocol Stack | 4 | 1 TAM, support from IFX | Complete time |  | Aal or Ulm | Stefan Niedermeier (?) |  | Stefan Niedermeier (niedermeiers)
CM | 10 | 1 person + 2 months consultant | Complete time |  | Aal (1) |  | yes
Smoke Test | 8 | 1 SM leader + interns | Complete time |  | Bej
BM | 20 | 2-3 BMs | Complete time |  | PSE NJ (1), Aal (1) |  | yes
MMI Spec |  | Do we need internal MMI spec?
RM | 12 | 1 RM + 1 MMI clarifications | Complete time |  | Bej (1), Aal or SISL
ST
Component Test |  | assumption: only unit and system test
PL | 24 | 4 PLs (1 DL (see above), 2 MMI, 1 PL-SW) | Complete time |  | Bej
Architects | 16 | 1 DL (see above), 2 MMI | Complete time |  | Bej
Effort sum | 343